## Projects
Ensure that every other table is connected to this one via one to many relationship
Project ID | Project | Location
543341 | Dalkeith | 200 High St, Dalkeith EH22 1AZ, United Kingdom
346321 | Lasswade | 5 Elm Row, Lasswade EH18 1AG, United Kingdom
678426 | Roslin | 9 Main St, Roslin EH25 9LD, United Kingdom

## Cost Summary
Project ID | Category | Value
543341 | Project Value (ex VAT) | 100000000
543341 | Contractor Valuations | 50000000
543341 | Change Cost [To date] | 480000
543341 | £ Monies remaining | 49520000
346321 | Project Value (ex VAT) | 80000000
346321 | Contractor Valuations | 35000000
346321 | Change Cost [To date] | 650000
346321 | £ Monies remaining | 44350000
678426 | Project Value (ex VAT) | 1200000000
678426 | Contractor Valuations | 720000000
678426 | Change Cost [To date] | 320000
678426 | £ Monies remaining | 479680000

## Client Items
Project ID | ID | Item | Budget | Spend to Date
543341 | 1 | FF+E | 11355 | 7905
543341 | 2 | IT/AV | 21564 | 13221
543341 | 3 | Contingency | 11899 | 11899
543341 | 4 | Fees | 16710 | 13413
543341 | 5 | Nett Total £ | 61528 | 46186
543341 | 6 | VAT | 12305 | 9237 | VAT is 20%
346321 | 1 | FF+E | 25333 | 19638
346321 | 2 | IT/AV | 16515 | 20804
346321 | 3 | Contingency | 16878 | 11306
346321 | 4 | Fees | 25200 | 22328
346321 | 5 | Nett Total £ | 83926 | 74076
346321 | 6 | VAT | 16785.2 | 14815.2 | VAT is 20%
678426 | 1 | FF+E | 19132 | 7838
678426 | 2 | IT/AV | 14040 | 3846
678426 | 3 | Contingency | 14081 | 8751
678426 | 4 | Fees | 20419 | 16878
678426 | 5 | Nett Total £ | 67672 | 37313
678426 | 6 | VAT | 13534.4 | 7462.6 | VAT is 20%

## Issue Register
The same categories as risks and early warnings
Project ID | Date Raised | Category | Issue Title | Description and Impact | Status | Cost | Mitigation | Action by Date | Owner
543341 | 2019-10-24 | Technical | Delivery of Units | Reputational damage implicated when units not achieved. | Open | 12391 | Managed through commZZCee reports and press releases by ZTMand IINC. | 2022-12-31 | Mikayla Downs
543341 | 2019-10-29 | Technical | Client Resource | Lack of Client resource and not skill set, results in delayed response of responding to their actions and increase delay and cost to Programme | Open | 8868 | ZTMresource their slowing rates | 2019-12-31 | Aryana Fitzpatrick
543341 | 2019-11-04 | Legal | Legal Resources | Lack of legal resource results in contract award dates not being achieved, thus resulting in a delayed start. | Closed | 2325 | ZTMto appoint dedicated person and point of escalation to have legal matters dealt with as priority. | 2019-12-01 | Mikayla Vaughn
543341 | 2019-10-30 | Commercial Risks | Delivery Resource | Client delivery resource are not aligned with the Programme Vision and strategic priorities, thus nullifying conflict in ideas | Open | 6396 | The approved blueprint will detail all processes and should be read by everyone involved in the programme and complied with at all times. | 2020-01-01 | Aryana Fitzpatrick
543341 | 2019-10-27 | Technical | Resource | Lack of legal resource to advise on Developers ZZC - financial model | Open | 1064 |  | 2019-12-01 | Alexis Herrera
346321 | 2019-11-02 | Commercial Risks | Budget | Reduction in units on all direct sites will increase pressure on resources. | Open | 11860 |  | 2022-01-01 | Mikayla Downs
346321 | 2019-11-02 | Legal | BUW funding | HAG funding applications can only be made for units completed. None of the projects are programmed to have units completed by this date. | Open | 11335 |  | 2020-01-01 | Alexis Herrera
346321 | 2019-11-09 | Technical | Delayed site entry for Contractor |  | Closed | 1000 |  | 2022-12-31 | Mikayla Vaughn
346321 | 2019-10-20 | Legal | Incorporation of MHP and roof | Additional costs incurred should these be signed off. | Closed | 32400 | Full review of proposals submZZCed by PKS. | 2019-12-31 | Madelyn Davila
678426 | 2019-11-03 | Legal | Specification is defined and won't align with programme subsequently tendered |  | Open | 300 |  | 2019-12-01 | Aryana Fitzpatrick
678426 | 2019-10-22 | Commercial Risks | Construction works have started and no Employers Agent in place |  | Open | 12200 |  | 2020-01-01 | Mikayla Vaughn
678426 | 2019-11-04 | Technical | Scope of works to Ave | Scope is yet to be defined as resurfacing is not currently included. | Open | 7000 |  | 2019-12-01 | Mikayla Vaughn
678426 | 2019-11-07 | Technical | Additional ground works | Additional works to be undertaken and unchartered services have been identified on site | Closed | 4000 |  | 2022-01-01 | Mikayla Vaughn

## Change Control
Client Decision Required - date by which client decision is required Date of Decision - actual date of client decision. If empty it means that the client did not confirm the decision Budget (Gross) for Change Control is budget for all change control items Value of Change Request (Gross) displays the percantage of total change control budget that specific item will require
Project ID | Change ID | Change Title | Description of Change | Reason for Change | Priority | Date Raised | Budget (Gross) for Change Control | Change Control Cost | Value of Change Request (Gross) | Programme Impact (No of days) | Any Other Implications | Funding | Confirm Approved / Rejected / Pending | Client Decision Required | Date of Decision | Status | Comments | Owner
543341 | 5 | Vault Removal in Basemant | Vault removal required to basement. Previously concealed and flagged as subject to survey once revealed by enabling works. | Construction Discovery | Urgent (Finalise within a week) | 2018-10-19 | 5000000 | 645716 | 12.91% | 4 |  | Contingency | Rejected | 2020-01-06 |  | Client Review | TBC | Elisa Jenkins
543341 | 15 | Further ME – Reduce waterproof concrete thickness | Reduce ground floor slab thickness where possible. Initial sub-contractor advice is to reduce from 200mm throughout to:- 150mm everywhere else | Contractor Claim | Moderate (Finalise within 2/3 weeks) | 2018-01-09 | 5000000 | 807515 | 16.15% | 4 |  | Risk | Rejected | 2020-01-11 | 2020-01-19 | Complete | TBC | Tyson Santiago
346321 | 12 | Site clearance of redundant materials from previous contracts | Site Clearance of (previous contract) redundant materials and the existing turnstile | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2018-05-02 | 5000000 | 844593 | 16.89% | 3 |  | Existing Provisional Sum | Approved | 2020-01-25 | 2020-02-27 | Complete | TBC | Elisa Jenkins
346321 | 14 | Unchartered CI Pipe | Unchartered cast iron pipe uncovered - trial holes investigation works over demolish pipe | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2017-06-12 | 5000000 | 194846 | 3.897% | 7 |  | Risk | Rejected | 2020-02-24 | 2020-03-14 | Complete | TBC | Litzy Ross
346321 | 22 | Clock tower entrance existing substructure | Removal of a larger than anticipated support structure beneath the existing entrance staircase at the basement. | Construction Discovery | Low (Finalise within 4/6 weeks) | 2018-01-31 | 5000000 | 657544 | 13.15% | 0 |  | Existing Provisional Sum | Approved | 2020-01-16 | 2020-03-26 | Complete | TBC | Mikayla Vaughn
346321 | 32 | Archaeological watching brief | Provision of archaeological watching brief and report | Construction Discovery | Low (Finalise within 4/6 weeks) | 2017-10-13 | 5000000 | 969770 | 19.4% | 9 |  | Contingency | Approved | 2020-01-26 | 2020-03-04 | Complete | TBC | Madelyn Davila
678426 | 3 | Elevation amendments | Design changes to the elevation of following omission of the new extension | User Request | Urgent (Finalise within a week) | 2018-09-11 | 5000000 | 454787 | 9.096% | 0 |  | Risk | Approved | 2020-03-01 |  | Client Review | TBC | Mikayla Vaughn
678426 | 7 | ME - omit vent trench to end | Omit external concrete trench construction and waterproofing in lieu of internal solution | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-04-21 | 5000000 | 654151 | 13.08% | 9 |  | Existing Provisional Sum | Rejected | 2020-01-27 | 2020-02-02 | Complete | TBC | Alexis Herrera
678426 | 11 | ME - omit vent trench to end | TBC | User Request | Urgent (Finalise within a week) | 2017-04-20 | 5000000 | 193618 | 3.872% | 3 |  | Risk | Rejected | 2020-01-08 | 2020-02-08 | Complete | TBC | Litzy Ross
678426 | 15 | Rot works - Retreatment of works due to water ingress | TBC | Construction Discovery | Urgent (Finalise within a week) | 2018-06-25 | 5000000 | 908425 | 18.17% | 12 |  | Existing Provisional Sum | Approved | 2020-03-22 |  | Initiation | TBC | Aryana Fitzpatrick
678426 | 19 | Off site storage of hansen materials | TBC | TBC | Moderate (Finalise within 2/3 weeks) | 2017-09-20 | 5000000 | 188864 | 3.777% | 13 |  | Contingency | Approved | 2020-01-26 | 2020-02-01 | Complete | TBC | Mattie Jenkins
678426 | 23 | Addition of gable restrain straps at high evel in the knuckles | TBC | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2017-10-26 | 5000000 | 173842 | 3.477% | 7 |  | Contingency | Pending | 2020-03-04 |  | Client Review | TBC | Kasen Archer
678426 | 27 | Modular wiring alternative (Value Engineering) | It is porposed to change the specified traditional wiring system to a modular system to benefit cost. | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-11-20 | 5000000 | 791150 | 15.82% | 4 |  | Existing Provisional Sum | Rejected | 2020-01-06 |  | Client Review | TBC | Elisa Jenkins
678426 | 31 | Event Space Service Trench amendments | Amendment to the service trench depth at the end of the event space | Design Development | Urgent (Finalise within a week) | 2017-11-13 | 5000000 | 642535 | 12.85% | 13 |  | Contingency | Approved | 2020-01-15 | 2020-02-28 | Complete | TBC | Alexis Herrera
543341 | 2 | CP Heat Exchanger | Addition of heat exchanger incoming , requested after issue of tender. | User Request | Urgent (Finalise within a week) | 2017-10-07 | 5000000 | 850792 | 17.02% | 15 |  | Risk | Approved | 2020-01-12 | 2020-02-11 | Complete | None | Tyson Santiago
543341 | 3 | Catering Layout | Adjust wall and door positions to suit basement layouts, requested after issue of tender. | Design Development | Urgent (Finalise within a week) | 2017-10-17 | 5000000 | 545469 | 10.91% | 10 |  | Existing Provisional Sum | Pending | 2020-01-20 |  | DT Comment | Rescinded as superded | Mikayla Downs
543341 | 13 | Additional Ground Investigation | Undertake cable percussive bores and rotary drilling as noted on the attached overmarks. Allow for measurement of fracture spacing to assist with the planning rock excavation methods and techniques. The main purpose of the investigation is to provide further ground information which may help to rationalise the existing substructure design for the extensions. | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2017-09-30 | 5000000 | 502877 | 10.06% | 16 |  | Contingency | Pending | 2020-01-11 |  | Initiation | TBC | Mattie Jenkins
543341 | 16 | Site Vermin Control | Pigeons have been nesting in the existing building, creating a build-up of fouling. There are also a number of dead pigeons around the site. The fouling is a particular problem in the partially complete. George Smith have requested a quotation from Indor for a detailed assessment and proposal to manage this problem. Please find attached proposal from the company. Their proposal is to carry out a one off Bird Shoot and to undertake a Pest Bird Clearance and Disinfection | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2017-04-29 | 5000000 | 553502 | 11.07% | 7 |  | Existing Provisional Sum | Pending | 2020-01-01 |  | DT Comment | TBC | Elisa Jenkins
543341 | 18 | 6.5.1 Insurance | Expenditure of provisional | User Request | Moderate (Finalise within 2/3 weeks) | 2018-09-04 | 5000000 | 554876 | 11.1% | 3 |  | Risk | Approved | 2020-01-18 | 2020-01-26 | Complete | TBC | Mikayla Downs
543341 | 20 | Revert to previous stair drawings | The stair design in the basement extensions are to revert back to the design noted within the originally issued tendered information | Contractor Claim | Moderate (Finalise within 2/3 weeks) | 2018-08-01 | 5000000 | 24489 | 0.4898% | 13 |  | Contingency | Approved | 2020-01-23 | 2020-02-13 | Complete | TBC | Tyson Santiago
543341 | 21 | Proposed reduction in sample / testing requirements | ME proposal for reduced testing and mock-ups. | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-07-04 | 5000000 | 58992 | 1.18% | 15 |  | Risk | Approved | 2020-02-03 | 2020-02-15 | Complete | TBC | Mikayla Downs
543341 | 23 | Removal of stored materials | Removal and storage of preserved items within existing building | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2017-08-16 | 5000000 | 998737 | 19.97% | 8 |  | Contingency | Pending | 2020-01-20 |  | Initiation | TBC | Litzy Ross
346321 | 11 | Additional Hoarding to basemant | Repair/replacement of the existing | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2018-10-11 | 5000000 | 697858 | 13.96% | 16 |  | Contingency | Rejected | 2020-01-12 |  | Client Review | TBC | Aryana Fitzpatrick
543341 | 9 | Enlarged plant space - Transformer Room Alteration | Additional plant area to gain additional around electrical services plant. & Inclusion of fire rated enclosure within the plant area. | User Request | Moderate (Finalise within 2/3 weeks) | 2018-02-13 | 5000000 | 684975 | 13.7% | 16 |  | Contingency | Rejected | 2020-01-22 | 2020-02-19 | Complete | TBC | Kira Watson
543341 | 10 | Value engineering item - Design changes to site works where the tree is to be removed | Change consequential to Tender Stage VE taken to remove existing elm; to rationalise geometry of path, replacement tree planting in JHLordance with planning condition and omit all structure related to elm root protection: Omit | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2017-05-30 | 5000000 | 336103 | 6.722% | 6 |  | Risk | Rejected | 2020-01-31 | 2020-02-08 | Complete | TBC | Charity Gutierrez
543341 | 11 | Value engineering item - slate to be used in lieu of slate in certain areas | Slate to be used in lieu slate in certain areas of the roofing. | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-01-15 | 5000000 | 545690 | 10.91% | 11 |  | Existing Provisional Sum | Pending | 2020-01-05 |  | Initiation | TBC | Kasen Archer
543341 | 14 | Water contamination testing | Hand digging in the locations shown on the attached file and provide water pipe specification report | Design Error | Moderate (Finalise within 2/3 weeks) | 2018-09-29 | 5000000 | 978299 | 19.57% | 1 |  | Contingency | Rejected | 2020-01-04 | 2020-01-17 | Complete | TBC | Elisa Jenkins
346321 | 2 | Value Engineering - Retaining wall | TBC | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2017-08-13 | 5000000 | 260561 | 5.211% | 9 |  | Existing Provisional Sum | Pending | 2020-02-16 |  | Contractor Comment | TBC | Charity Gutierrez
346321 | 3 | M&E Value Engineering - Alternative extract fan proposal | Alternative extract fan proposal | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-11-23 | 5000000 | 91084 | 1.822% | 7 |  | Existing Provisional Sum | Rejected | 2020-01-04 | 2020-02-11 | Complete | TBC | Mattie Jenkins
346321 | 4 | M&E Value Engineering - Radiator specification change | Alternative radiator specification | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2017-12-10 | 5000000 | 252366 | 5.047% | 5 |  | Existing Provisional Sum | Pending | 2020-01-04 |  | DT Comment | TBC | Tyson Santiago
346321 | 5 | M&E Value Engineering - Alternative lighting proposals | Alternative lighting specification | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-07-12 | 5000000 | 442652 | 8.853% | 12 |  | Risk | Rejected | 2020-02-02 | 2020-03-19 | Complete | TBC | Alexis Herrera
346321 | 6 | M&E Value Engineering - Alternative data cabling | Alternative data cabling specification | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-08-17 | 5000000 | 368798 | 7.376% | 5 |  | Risk | Rejected | 2020-01-16 | 2020-02-25 | Complete | TBC | Alexis Herrera
346321 | 7 | M&E Value Engineering - Reduced tank sizes | Reduced water tank sizes | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2017-06-28 | 5000000 | 987181 | 19.74% | 0 |  | Risk | Rejected | 2020-03-09 | 2020-03-17 | Complete | TBC | Kasen Archer
346321 | 8 | M&E Value Engineering - Alternative floor boxes | Alternative floor box specification | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2017-05-28 | 5000000 | 313952 | 6.279% | 8 |  | Contingency | Rejected | 2020-01-08 | 2020-01-21 | Complete | TBC | Mikayla Vaughn
346321 | 9 | M&E Value Engineering - Transformer | Inclusion of fire rated enclosure within the plant area. This area will cheifly house the 2*transformers and panel board. | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-03-04 | 5000000 | 908111 | 18.16% | 7 |  | Contingency | Rejected | 2020-01-06 | 2020-01-19 | Complete | TBC | Tyson Santiago
346321 | 10 | M&E Value Engineering - deletion of smoke extract fans in roof | Deletion of smoke extract fans in the basement | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-09-06 | 5000000 | 937436 | 18.75% | 15 |  | Risk | Rejected | 2020-01-14 | 2020-02-02 | Complete | TBC | Mikayla Vaughn
346321 | 19 | Additional Asbestos removal to windows | Additional asbestos removals identified during the course of the asbestos strip out works | Value Engineer | Low (Finalise within 4/6 weeks) | 2017-07-27 | 5000000 | 585653 | 11.71% | 12 |  | Contingency | Pending | 2020-01-05 |  | Contractor Comment | TBC | Alexis Herrera
346321 | 20 | Uplift of salvaged stone from Sir Robert McAlpine's storage facility | Uplift of salvaged stone from Mitch storage facility | Value Engineer | Low (Finalise within 4/6 weeks) | 2017-10-17 | 5000000 | 346192 | 6.924% | 9 |  | Contingency | Approved | 2020-01-04 | 2020-01-23 | Complete | TBC | Charity Gutierrez
346321 | 26 | Ward end steel removal | Carry out the pier reinstatement/steel removal to the ward ends as per the methodology and details noted in the attachments appended. | Construction Discovery | Low (Finalise within 4/6 weeks) | 2017-09-18 | 5000000 | 632261 | 12.65% | 15 |  | Contingency | Approved | 2020-01-03 | 2020-01-13 | Complete | TBC | Mikayla Downs
346321 | 27 | Internal masonry repairs | Internal masonry repairs as per workstream requirements | Construction Discovery | Low (Finalise within 4/6 weeks) | 2018-07-10 | 5000000 | 984567 | 19.69% | 13 |  | Contingency | Approved | 2020-01-28 | 2020-02-25 | Complete | TBC | Mikayla Vaughn
346321 | 28 | Underpinning changes following further on site investigations | Additional underpinning requirements identified on site over and above those noted at tender | Construction Discovery | Low (Finalise within 4/6 weeks) | 2018-11-06 | 5000000 | 366219 | 7.324% | 15 |  | Risk | Approved | 2020-02-14 | 2020-02-27 | Complete | TBC | Mattie Jenkins
346321 | 34 | Vault removals in the corridor | TBC | Provisional Sum Not Adequate | Low (Finalise within 4/6 weeks) | 2017-05-29 | 5000000 | 462083 | 9.242% | 15 |  | Existing Provisional Sum | Approved | 2020-01-18 | 2020-01-31 | Complete | TBC | Mikayla Vaughn
346321 | 35 | Proposed removal of chimneys | Removal of the existing chimneys and associated reinstatement of the roof structure and finishes | Value Engineer | Low (Finalise within 4/6 weeks) | 2018-08-05 | 5000000 | 303878 | 6.078% | 14 |  | Contingency | Approved | 2020-02-19 |  | Contractor Comment | TBC | Mikayla Downs
543341 | 1 | Additional IT Risers for Resilience | Additional IT riser | User Request | Low (Finalise within 4/6 weeks) | 2018-07-12 | 5000000 | 50000 | 1% | 1 |  | Contingency | Rejected | 2020-01-12 | 2020-01-30 | Complete | TBC | Madelyn Davila
543341 | 4 | Omit Floor Removals Carried Out in the Enabling Works |  | Value Engineer | Urgent (Finalise within a week) | 2018-10-17 | 5000000 | 629765 | 12.6% | 3 |  | Contingency | Rejected | 2020-01-01 | 2020-01-04 | Complete | TBC | Charity Gutierrez
543341 | 6 | Building control requirements – Smoke Barriers and Adjustment to Walls and Doors | Smoke barriers adjustment to walls and doors | Legislative Change | Moderate (Finalise within 2/3 weeks) | 2018-04-17 | 5000000 | 566204 | 11.32% | 3 |  | Contingency | Rejected | 2020-01-06 | 2020-02-11 | Complete | TBC | Tyson Santiago
543341 | 7 | Fire stopping and cavity barrier details. | Fire stopping and cavity barrier details. | Legislative Change | Moderate (Finalise within 2/3 weeks) | 2017-11-27 | 5000000 | 554298 | 11.09% | 8 |  | Contingency | Rejected | 2020-01-01 | 2020-01-16 | Complete | TBC | Elisa Jenkins
543341 | 8 | Historic balustrades require infill detail. | Infill details are required to the historic balustrades | Contractor Claim | Moderate (Finalise within 2/3 weeks) | 2018-11-07 | 5000000 | 910855 | 18.22% | 16 |  | Risk | Pending | 2020-01-24 |  | DT Comment | TBC | Mattie Jenkins
543341 | 12 | Addition of bat slates boxes | Provision of bat boxes in the elevations; locations to be confirmed | Contractor Claim | Moderate (Finalise within 2/3 weeks) | 2018-11-13 | 5000000 | 427509 | 8.55% | 13 |  | Existing Provisional Sum | Rejected | 2020-01-09 | 2020-01-15 | Complete | TBC | Mikayla Downs
543341 | 19 | Additional induction loop requirements | Requirement for additional induction loops identified. Note: Not design development, building control equirement | Design Development | Moderate (Finalise within 2/3 weeks) | 2018-12-25 | 5000000 | 705216 | 14.1% | 7 |  | Risk | Pending | 2020-01-27 |  | QS Comment | TBC | Mikayla Downs
543341 | 24 | Further ME – Reduce specification of event space roof build-up | 1. Omit acoustic mat 2. Remove second (upper) layer of waterproofing | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2017-05-16 | 5000000 | 50666 | 1.013% | 10 |  | Risk | Rejected | 2020-01-03 | 2020-01-05 | Complete | TBC | Mattie Jenkins
543341 | 25 | Further ME – Reduction to internal door heights | Reduce internal door heights to circa 200 doors. | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-09-26 | 5000000 | 896853 | 17.94% | 14 |  | Contingency | Rejected | 2020-03-01 | 2020-03-09 | Complete | TBC | Tyson Santiago
346321 | 17 | Potential ME to delete screed following alternative waterproofing methdoology | TBC | Value Engineer | Low (Finalise within 4/6 weeks) | 2017-11-30 | 5000000 | 373151 | 7.463% | 2 |  | Risk | Approved | 2020-01-14 | 2020-01-16 | Complete | TBC | Mikayla Downs
346321 | 21 | Amendments to screeds and wall linings | TBC | Value Engineer | Low (Finalise within 4/6 weeks) | 2018-09-26 | 5000000 | 433138 | 8.663% | 11 |  | Existing Provisional Sum | Pending | 2020-01-26 |  | DT Comment | TBC | Kira Watson
346321 | 23 | Event Space kitchen Electrical Design | TBC | Design Development | Low (Finalise within 4/6 weeks) | 2018-07-26 | 5000000 | 873685 | 17.47% | 9 |  | Contingency | Approved | 2020-02-09 | 2020-02-23 | Complete | TBC | Madelyn Davila
346321 | 24 | Remove several of the protective devices | TBC | Value Engineer | Low (Finalise within 4/6 weeks) | 2018-01-17 | 5000000 | 198549 | 3.971% | 10 |  | Contingency | Approved | 2020-02-22 |  | QS Comment | TBC | Mikayla Vaughn
346321 | 25 | Services - Review of cost neutral adjustments | TBC | Value Engineer | Low (Finalise within 4/6 weeks) | 2017-10-11 | 5000000 | 735537 | 14.71% | 4 |  | Existing Provisional Sum | Approved | 2020-03-02 | 2020-03-13 | Complete | TBC | Tyson Santiago
346321 | 29 | Alternative smoke vent solution in turrets | Re-design/simplification of the smoke vent solution in the wing turrets that was proposed at tender stage. | Value Engineer | Low (Finalise within 4/6 weeks) | 2018-06-30 | 5000000 | 932780 | 18.66% | 13 |  | Risk | Pending | 2020-01-10 |  | DT Comment | TBC | Charity Gutierrez
678426 | 1 | Substation layout changes | Incorporation of comments received from UoE | User Request | Urgent (Finalise within a week) | 2017-07-03 | 5000000 | 815579 | 16.31% | 1 |  | Risk | Approved | 2020-01-07 | 2020-02-01 | Complete | TBC | Mikayla Downs
678426 | 2 | Stair nosing | TBC | User Request | Moderate (Finalise within 2/3 weeks) | 2018-08-15 | 5000000 | 811275 | 16.23% | 13 |  | Existing Provisional Sum | Approved | 2020-01-08 | 2020-01-09 | Complete | TBC | Kasen Archer
678426 | 4 | User group future proofing - drainage runs and pop ups | Future proofing identified following user group consultations - provision of additional drainage pop up locations and change in ground floor construction methodology | User Request | Moderate (Finalise within 2/3 weeks) | 2018-09-06 | 5000000 | 201390 | 4.028% | 16 |  | Existing Provisional Sum | Approved | 2020-01-05 | 2020-01-21 | Complete | TBC | Kira Watson
678426 | 6 | Strip of existing stairs | Confirmation of scope of existing stair flights to be stripped back for inspection | Design Development | Moderate (Finalise within 2/3 weeks) | 2017-10-14 | 5000000 | 361025 | 7.221% | 12 |  | Risk | Approved | 2020-01-14 | 2020-01-19 | Complete | TBC | Kasen Archer
678426 | 8 | Lightboxes | Revised as developed. | Value Engineer | Urgent (Finalise within a week) | 2018-12-23 | 5000000 | 597533 | 11.95% | 6 |  | Contingency | Pending | 2020-02-19 |  | DT Comment | TBC | Mikayla Downs
678426 | 10 | Basement | TBC | User Request | Urgent (Finalise within a week) | 2018-06-18 | 5000000 | 492567 | 9.851% | 8 |  | Existing Provisional Sum | Rejected | 2020-01-25 | 2020-03-30 | Complete | TBC | Mikayla Downs
678426 | 12 | Double height space vs new intermediate floor | Proposal to omit the structure to form the double height space and provide a new intermediate floor structure | User Request | Urgent (Finalise within a week) | 2018-02-20 | 5000000 | 536449 | 10.73% | 16 |  | Risk | Approved | 2020-01-04 |  | QS Comment | TBC | Kasen Archer
678426 | 14 | Bricking up of vents below windows | TBC | Design Development | Urgent (Finalise within a week) | 2017-07-20 | 5000000 | 383700 | 7.674% | 12 |  | Existing Provisional Sum | Approved | 2020-02-20 | 2020-03-06 | Complete | TBC | Elisa Jenkins
678426 | 16 | Omission of the extension and associated fit out | TBC | Design Development | Moderate (Finalise within 2/3 weeks) | 2018-11-29 | 5000000 | 937783 | 18.76% | 9 |  | Contingency | Approved | 2020-01-12 | 2020-02-22 | Complete | TBC | Aryana Fitzpatrick
678426 | 18 | Heating installation - MT circuit invertors | TBC | Design Development | Low (Finalise within 4/6 weeks) | 2018-05-16 | 5000000 | 915256 | 18.31% | 8 |  | Risk | Approved | 2020-02-03 | 2020-03-13 | Complete | TBC | Madelyn Davila
678426 | 20 | Future proofing - raised floor provision | Addition of a raised floor within suit the future proofing requirements identified by the users. As a result dwarf walls will need to be removed to facilitate this change. The slab will also change from suspended to slab on hard. | Design Development | Moderate (Finalise within 2/3 weeks) | 2018-08-17 | 5000000 | 737996 | 14.76% | 2 |  | Contingency | Rejected | 2020-02-13 | 2020-02-20 | Complete | TBC | Mikayla Vaughn
678426 | 22 | Lift overrun steelwork | TBC | Design Development | Moderate (Finalise within 2/3 weeks) | 2017-12-27 | 5000000 | 310337 | 6.207% | 2 |  | Contingency | Approved | 2020-01-01 | 2020-01-02 | Complete | TBC | Mikayla Vaughn
678426 | 24 | Masonry repairs at peen/gable to ward | TBC | Design Development | Moderate (Finalise within 2/3 weeks) | 2018-12-14 | 5000000 | 994317 | 19.89% | 15 |  | Risk | Approved | 2020-02-20 | 2020-03-31 | Complete | TBC | Mikayla Downs
678426 | 26 | Specification change | TBC | Construction Discovery | Urgent (Finalise within a week) | 2018-08-28 | 5000000 | 864013 | 17.28% | 2 |  | Contingency | Approved | 2020-01-02 | 2020-01-04 | Complete | TBC | Madelyn Davila
678426 | 28 | User groupe future proofing - IT requirements update | TBC | User Request | Urgent (Finalise within a week) | 2017-07-07 | 5000000 | 901884 | 18.04% | 0 |  | Contingency | Rejected | 2020-01-23 | 2020-02-05 | Complete | TBC | Mattie Jenkins
678426 | 30 | Plaster change (Value Engineering) | Change of finish to the existing masonry external walls. The tendered solution of diathonite render will be replaced with a calcium silicate board lining on metal framing with lime skim coat finish | Value Engineer | Urgent (Finalise within a week) | 2017-08-23 | 5000000 | 449298 | 8.986% | 3 |  | Risk | Rejected | 2020-02-04 | 2020-02-19 | Complete | TBC | Kira Watson
678426 | 32 | Vent louvres - Future proofing | For future proofing purposes it has been proposed that the number of louvres to the vent towers are increased. All based on the numbers shown on the latest. | User Request | Urgent (Finalise within a week) | 2018-05-23 | 5000000 | 182671 | 3.653% | 8 |  | Risk | Approved | 2020-01-03 |  | DT Comment | TBC | Mikayla Vaughn
678426 | 34 | Mobile Generator Set Connection Point | UoE requst to provide costs for incorporating additional electrical equipment within Switchboard in plant room. |  | Moderate (Finalise within 2/3 weeks) | 2017-10-12 | 5000000 | 632586 | 12.65% | 16 |  | Contingency | Approved | 2020-01-10 | 2020-02-20 | Complete | TBC | Madelyn Davila
543341 | 22 | Update of the existing fabric layout following the post strip re-survey of the building | TBC | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-03-17 | 5000000 | 137438 | 2.749% | 4 |  | Risk | Rejected | 2020-02-05 | 2020-03-07 | Complete | TBC | Kasen Archer
678426 | 5 | Paving reclamation | Removal and storage of existing internal paving in the corridors per drawings. | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2017-12-04 | 5000000 | 168104 | 3.362% | 3 |  | Contingency | Approved | 2020-01-24 | 2020-01-31 | Complete | TBC | Aryana Fitzpatrick
678426 | 9 | Level 87 pavillions | Revised programme for implementation of ME. The pavillions provide further cost saving in addition to savings taken at tender for retention of stone links. | Value Engineer | Urgent (Finalise within a week) | 2017-05-15 | 5000000 | 170624 | 3.412% | 13 |  | Contingency | Approved | 2020-02-02 | 2020-03-14 | Complete | TBC | Mattie Jenkins
678426 | 13 | Addition of changing places toilet | TBC | User Request | Moderate (Finalise within 2/3 weeks) | 2018-01-06 | 5000000 | 375838 | 7.517% | 15 |  | Risk | Rejected | 2020-02-13 | 2020-03-02 | Complete | TBC | Charity Gutierrez
678426 | 17 | Confirmation of lift power supply requirements | TBC | Design Development | Low (Finalise within 4/6 weeks) | 2017-06-12 | 5000000 | 711351 | 14.23% | 6 |  | Existing Provisional Sum | Rejected | 2020-01-13 | 2020-03-30 | Complete | TBC | Aryana Fitzpatrick
678426 | 21 | Door relocation at the entrance and associated fire door relocation | TBC | Design Development | Moderate (Finalise within 2/3 weeks) | 2017-12-05 | 5000000 | 771892 | 15.44% | 2 |  | Contingency | Pending | 2020-02-01 |  | Initiation | TBC | Mikayla Vaughn
678426 | 25 | Valley alteration to suit resurvey | TBC | Design Development | Urgent (Finalise within a week) | 2017-04-30 | 5000000 | 253931 | 5.079% | 0 |  | Existing Provisional Sum | Approved | 2020-01-04 | 2020-01-24 | Complete | TBC | Mattie Jenkins
678426 | 29 | Lift Supply update | Reduction in size of electrical supplies for lifts. | Design Development | Moderate (Finalise within 2/3 weeks) | 2017-09-15 | 5000000 | 935888 | 18.72% | 2 |  | Risk | Pending | 2020-01-08 |  | DT Comment | TBC | Charity Gutierrez
678426 | 33 | Floor remedial works efficiency changes | Rationalisation of the timber floor repairs. In areas where significant patching is required, the proposal is to omit the patching and upgrade the plywood overlay from 6mm to 18mm thick to span over any voids | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2017-09-09 | 5000000 | 390562 | 7.811% | 7 |  | Contingency | Approved | 2020-01-02 | 2020-01-06 | Complete | TBC | Alexis Herrera
543341 | 17 | Drainage rationalisation | Change alignment to mitigate deep excavation works close to existing building and existing boundary. Discussed between Smith John on site and over phone. | Design Development | Moderate (Finalise within 2/3 weeks) | 2018-05-24 | 5000000 | 994633 | 19.89% | 7 |  | Contingency | Rejected | 2020-01-01 | 2020-01-10 | Complete | TBC | Mattie Jenkins
346321 | 1 | Further ME – Reduce number of opening vents to façade | Omit opening vents in lieu of fixed insulated aluminium panels as per Further ME – Opening vents reduction | Value Engineer | Moderate (Finalise within 2/3 weeks) | 2018-11-08 | 5000000 | 935217 | 18.7% | 8 |  | Existing Provisional Sum | Rejected | 2020-01-24 | 2020-02-29 | Complete | TBC | Mikayla Vaughn
346321 | 13 | Bulging Wall Rectification and Delay | Additional temporary works requirements required to stabilise and monitor the bulging walls | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2018-01-10 | 5000000 | 705323 | 14.11% | 15 |  | Contingency | Rejected | 2020-01-03 | 2020-02-02 | Complete | TBC | Madelyn Davila
346321 | 15 | Trial holes and protection of services at SE corner | Additional works required to the uncharted existing services at the corner of the site | Construction Discovery | Moderate (Finalise within 2/3 weeks) | 2018-01-18 | 5000000 | 838725 | 16.77% | 8 |  | Risk | Rejected | 2020-01-03 | 2020-01-08 | Complete | TBC | Madelyn Davila
346321 | 16 | Additional waterproofing | Additional waterproofing required to additional walls left insitu from (predominantly in knuckles) | Provisional Sum Not Adequate | Moderate (Finalise within 2/3 weeks) | 2017-11-20 | 5000000 | 582383 | 11.65% | 0 |  | Contingency | Approved | 2020-01-01 | 2020-01-05 | Complete | TBC | Madelyn Davila
346321 | 18 | Piling changes (deletion of piling to of existing building) | Change in the foundation strategy at the northern extensions (change from piling of mass fill/pad foundations) | Value Engineer | Low (Finalise within 4/6 weeks) | 2017-06-16 | 5000000 | 246947 | 4.939% | 5 |  | Contingency | Approved | 2020-01-06 | 2020-01-09 | Complete | TBC | Tyson Santiago
346321 | 30 | External Works Discoveries | Grubbing/breaking up and removal. No. concrete pad foundations (c/w steel column bases) | Construction Discovery | Low (Finalise within 4/6 weeks) | 2017-04-21 | 5000000 | 596069 | 11.92% | 13 |  | Contingency | Approved | 2020-01-08 | 2020-01-27 | Complete | TBC | Elisa Jenkins
346321 | 31 | High level steel removals | As per Contract Instructiopn additional works required to remove steel beams at high level, through each knuckle. | Construction Discovery | Low (Finalise within 4/6 weeks) | 2018-11-23 | 5000000 | 722163 | 14.44% | 8 |  | Contingency | Approved | 2020-01-18 | 2020-01-28 | Complete | TBC | Kasen Archer
346321 | 33 | Additional steel required at wing | Permanent steelwork in Roof top valley. Removal of temporary support structures and install of steel member to carry roof | Design Development | Low (Finalise within 4/6 weeks) | 2018-04-15 | 5000000 | 698520 | 13.97% | 3 |  | Risk | Approved | 2020-01-19 | 2020-01-22 | Complete | TBC | Charity Gutierrez
346321 | 36 | Water ingress prevention measures | Installation of bunds where water has been penetratinig the existing building. | Construction Discovery |  | 2017-08-20 | 5000000 | 718997 | 14.38% | 1 |  | Contingency | Approved | 2020-01-10 | 2020-01-12 | Complete | TBC | Litzy Ross

## Early Warnings
The same categories as risks and issues
Project ID | EW No. | Title | Category | Notification of | Issue Date | Cost Implications | Effect on Programme | Client Acknowledgement | RAG Rating | Owner
543341 | 1 | FI/MI - Updated Site Red line boundary at Greenferns | Legal | Following appointment the boundary and area has varied resulting in delay to procurement and programme resulting in abortive works. | 2019-12-19 | 10747 | YES | NO | RED | Aryana Fitzpatrick
346321 | 1 | FI/MI – Revised Procurement and Programme | Commercial Risks | Early warning to highlight variation of procurement and programme to scope. | 2019-12-06 | 41685 | NO | YES | GREEN | Charity Gutierrez
678426 | 1 | Delayed appointment of surveys | Technical | Failure to appoint topographic surveys has delayed programme | 2020-01-15 | 22071 | YES | YES | AMBER | Alexis Herrera
543341 | 2 | Impact of busy market on Ground Investigations | Technical | Ground Investigation works may be impacted as OL contractors have advised that market is exceptionally busy at present. | 2020-01-10 | 12104 | YES | YES | GREEN | Kira Watson
346321 | 2 | Housing Mix uncertainty | Technical | Ongoing uncertainty associated with the unit mix to be delivered is likely to impact programme for issue of consultant. | 2019-12-26 | 42640 | YES | TBC | RED | Mikayla Vaughn
678426 | 2 | Change in Developer IMM scope | Commercial Risks | The scope of the Developer now envisaged diverges significantly from that provided at the outset of the commission, necessitating a complete redrafting rather than updating and reissue of the Dynamic Purchasing provided upon appointment. It is likely that this will also impact the scope of, and extent of assessment activity required, increasing associated timescales and costs. | 2019-12-19 | 36254 | NO | TBC | GREEN | Alexis Herrera

## Decision Required Log
The focus should be placed on outstanding decisions
Project ID | ID | Date | Description | Decision | Date for Action | Status
543341 | 1 | 2019-09-17 | Project Briefs- Project Brief Paper tabled | If no comments received by 7th of May | 2019-10-11 | Outstanding
543341 | 2 | 2019-09-27 | Resource commitments to improve JHLes | Ongoing | 2019-10-08 | Outstanding
543341 | 3 | 2019-10-31 | Surveys- instruction to procced on original basis as timeframe to procure will affect procurement of Consultants | Approved | 2019-12-03 | Approved
543341 | 4 | 2019-09-11 | Procurement Legal Advisor to be appointed to advise on Developer | Outstanding | 2019-09-22 | Outstanding
543341 | 5 | 2019-11-01 | Procurement Paper 001 signed off | To be discussed at Procurement Workshop and update post | 2019-11-16 | Outstanding
543341 | 6 | 2019-10-21 | Johnathan Belford to advise on Financial Models | Outstanding | 2019-11-29 | Outstanding
346321 | 1 | 2019-08-01 | Delegated Authority to be agreed | Delegated Authority | 2019-09-05 | Approved
346321 | 2 | 2019-10-22 | conditions (Consultants + Contractors) to be forward | Ongoing | 2019-11-06 | Outstanding
346321 | 3 | 2019-10-22 | CCF 9, 11, 14 to be signed off | Agreed at Feb Board | 2019-11-03 | Outstanding
346321 | 4 | 2019-10-30 | Commercial Information sought from Programme Board | Approved- Information provided after Feb Board | 2019-11-23 | Approved
678426 | 1 | 2019-11-06 | MLI to complete Form 310, this will allow payment | Ongoing | 2019-11-30 | Outstanding
678426 | 2 | 2019-11-07 | Dalkeith change in roof specification - option to be decided | Ongoing | 2019-12-10 | Outstanding
678426 | 3 | 2019-11-07 | Project briefs - to be decided if 23% units should be fully ZTM | Approved at Programme Board | 2019-12-08 | Approved
678426 | 4 | 2019-11-07 | Technical standards to be decided | To be signed off on at Programme Board | 2019-11-26 | Outstanding
678426 | 5 | 2019-11-11 | Procurement Paper 001 to be signed off | Ongoing | 2019-11-21 | Outstanding

## Action Log
Project ID | Action ID | Date Added | Action Title | Action Details | Status Update | Target Closure Date | Status | RAG | CAL Status
543341 | Act001 | 2020-01-17 | Project Documnentation | Obtain Coppies of all relevant project Documents for Review | Meeting invite issued 01/02/2020 | 2020-02-01 | Open | Red | FALSE
543341 | Act002 | 2020-01-17 | Project Sponsor Engagement | Meeting to be set up | Meeting invite issued 10/02/2020 | 2020-02-10 | Open | Red | FALSE
543341 | Act003 | 2020-01-17 | Programme Development | Full planned dates to be reviewed | Meeting invite issued 04/03/2020 | 2020-03-04 | Open | Green | FALSE
543341 | Act004 | 2020-01-17 | Review of Design Team Tender | Tender retruns for anaylisis | Meeting invite issued 11/03/2020 | 2020-03-11 | Open | Green | FALSE
346321 | Act001 | 2020-01-17 | Project Documnentation | Obtain Coppies of all relevant project Documents for Review | Meeting invite issued 12/02/2020 | 2020-02-12 | Open | Amber | FALSE
346321 | Act002 | 2020-01-17 | Project Sponsor Engagement | Meeting to be set up | Meeting invite issued 30/01/2020 | 2020-01-30 | Open | Red | FALSE
346321 | Act003 | 2020-01-17 | Programme Development | full planned dates to be reviewed | Meeting invite issued 08/02/2020 | 2020-02-08 | Open | Green | FALSE
346321 | Act004 | 2020-01-17 | Review of Design Team Tender | Tender retruns for anaylisis | Meeting invite issued 31/01/2020 | 2020-01-31 | Open | Red | FALSE
678426 | Act001 | 2020-01-17 | Project Documnentation | Obtain Coppies of all relevant project Documents for Review | Meeting invite issued 19/02/2020 | 2020-02-19 | Open | Red | FALSE
678426 | Act002 | 2020-01-17 | Project Sponsor Engagement | Meeting to be set up | Meeting invite issued 29/02/2020 | 2020-02-29 | Open | Amber | FALSE
678426 | Act003 | 2020-01-17 | Programme Development | full planned dates to be reviewed | Meeting invite issued 08/03/2020 | 2020-03-08 | Open | Green | FALSE
678426 | Act004 | 2020-01-17 | Review of Design Team Tender | Tender retruns for anaylisis | Meeting invite issued 28/01/2020 | 2020-01-28 | Open | Amber | FALSE

## General Risk Register
Likelihood * Impact = Risk Score Risk Score: 1-7 GREEN, 8-15 AMBER, 16 - 25 RED If there is no action data it means risk is not yet mitigated The same categories as Early Warnings and issues The postmitigated cost includes premitigated cost
Project ID | Date Raised | Category | Risk Title | Threat/Opportunity | Risk Description | Effect of Risk | Project Stage | Status | Likelihood | Impact | Risk Score | Cost | Risk Control Measures | Action by Date | Mitigated Likelihood | Mitigated Impact | Mitigated Risk Score | Mitigated Cost | Owner
543341 | 2019-10-28 | Technical | ACM | Threat | Further volumes of ACMs could be detected. | Health implications to those working with/area of the site. Reputational damage for KOL. | 5 | Closed | 4 | 5 | 20 | 6356 | Low level of ACMs identified, KOL H&S advisor has not identified any definitive legislation for use of material. Fairhurst have developed strategy for use. | 2019-12-13 | 3 | 5 | 15 | 15046 | Tyson Santiago
543341 | 2019-10-28 | Legal | Potential exposure to asbestos in excess of the levels anticipated – workforce and members of the public. | Threat | Potential health impact for those in the area of the site, or working on the site. | Health implications, reputational damage. | 5 | Closed | 4 | 5 | 20 | 5718 | Contractor to follow RAMS and report if material visibly identified. | 2019-12-06 | 2 | 3 | 6 | 11342 | Tyson Santiago
543341 | 2019-10-28 | Commercial Risks | Earthwork strategy | Threat | KLOSmay have insufficient detail contained within Earthwork strategy including the use of stockpile materials that contain asbestos. | Delay to KLOSstarting on site. | 5 | Closed | 4 | 4 | 16 | 2571 | Fairhurst design w/c 4th October will ensure efficient use of material to minimise waste offsite and use the contaminated material safely. | 2020-02-06 | 2 | 2 | 16 | 11869 | Mikayla Vaughn
543341 | 2019-10-28 | Technical | Heat & Power delivery of MONH offsite. | Threat | MONH offsite construction programme to be developed and align with ACW's programme of works.CV+K /KOL have no input to manage Heat and Power works, this increases the risk. MONH may experience issues during installation that may impact KLOSprogramme. | Impact on KOL Edinburgh Programme out with KWC's control. | 5 | Closed | 3 | 5 | 15 | 12096 | Workshops being held between design team and KLOSto progress design timeously. | 2020-01-30 | 3 | 3 | 9 | 21282 | Aryana Fitzpatrick
543341 | 2019-10-28 | Commercial Risks | Completion date for offsite culvert works | Threat | KLOShave previously advised of a delay to the completion date of the offsite culvert works. | Delay to programme/ EoT claim | 5 | Closed | 4 | 3 | 12 | 991 | Monitor progress and prompt response to TQ's. | 2019-12-03 | 4 | 3 | 12 | 7434 | Alexis Herrera
678426 | 2019-10-28 | Technical | Plant and vehicle movements, including site deliveries through a residential area and nearby school and nursery. | Threat | Risk of plant being left onsite over night. Large vehicles moving during school hours. | Health & Safety incidents more likely to occur | 5 | Open | 3 | 4 | 12 | 3373 | Ensure areas of movement are contained and appropriate signage in place. Limit deliveries to site to evenings and weekends where possible. | 2020-02-17 | 2 | 2 | 4 | 9227 | Madelyn Davila
678426 | 2019-10-28 | Legal | Unidentified/ unchartered services. | Threat | Risk of unchartered services being identified on the site | May delay KLOSand/ or sectional completion dates | 5 | Open | 3 | 4 | 12 | 3154 | Contractor to highlight unchartered services | 2019-12-30 | 2 | 3 | 6 | 12561 | Charity Gutierrez
678426 | 2019-11-26 | Technical | Phased parking | Threat | 10% of the units are completed, then 10% of the approved parking spaces should be available prior to occupation of those units. ACWs current proposed programme does not comply with this planning condition. | KLOSmay have to re sequence works/delayed KOLess to units | 5 | Open | 3 | 4 | 12 | 11951 | KLOSare reviewing programme | 2020-01-23 | 2 | 3 | 6 | 20894 | Litzy Ross
678426 | 2019-11-26 | Technical | Timber Kit TQ's | Threat | Design team are currently responding to TQ's required by the timber kit sub-contractor. The sub-contractor requires all responses by 27/11/2019 | Impact on KOL Edinburgh Programme out with ACW's control. | 5 | Open | 3 | 4 | 12 | 7284 | Timber-kit sub-contractor has sent detailed email stating all information required. | 2020-01-31 | 2 | 4 | 8 | 16914 | Elisa Jenkins
678426 | 2019-10-28 | Legal | Unforeseen ground conditions | Threat | The site is a brown field site, therefore there is a chance KLOScould encounter unforeseen ground conditions. | Increase in cost. | 5 | Closed | 3 | 3 | 9 | 14046 | KLOSto report as they encounter unforeseen ground conditions. |  |  |  | 0 |  | Kasen Archer
678426 | 2019-10-28 | Legal | Technical Query response times | Threat | TQ's are not responded to, by design team in a timely manner. | KWC's programme is delayed due to lack of information provided by Design Team. | 5 | Closed | 3 | 3 | 9 | 12953 | IINC to monitor TQ response time and chase for responses. Fortnightly design team meetings will highlight urgent technical queries. | 2020-01-30 | 2 | 2 | 4 | 21534 | Kira Watson
543341 | 2019-10-28 | Commercial Risks | Contractor Progress | Threat | Post tender KLOSprogramme showed an extended duration of 4 weeks. | Delay to completion date | 5 | Closed | 2 | 4 | 8 | 2368 | KLOShave provided revised programme taking cognisance of earthworks strategy. | 2020-02-25 | 2 | 4 | 8 | 9186 | Mattie Jenkins
543341 | 2019-10-28 | Legal | Late changes to design introduced by KOL | Threat | Late changes from KOL may add cost and delay programme | Impact start dates and programme | 5 | Closed | 2 | 4 | 8 | 9443 | Late/evolving client changes during RIBA Stage 5-6 to be monitored. | 2020-02-22 | 2 | 4 | 8 | 15691 | Mikayla Vaughn
543341 | 2019-10-28 | Legal | Heat & Power delivery of MONH | Threat | Detailed design and costs not provided by Heat and Power for provision of MONH. | Delay KLOSdelivery until detailed design concluded. Impact SAP calculations | 5 | Closed | 2 | 3 | 6 | 5168 | Workshops being held between design team, progress design timeously. | 2019-12-28 | 2 | 2 | 4 | 11290 | Aryana Fitzpatrick
543341 | 2019-10-28 | Commercial Risks | Mild winter | Opportunity | May KOLelerate building on site. | Moderate temperatures may allow site activities to progress | 5 | Open | 2 | 3 | 6 | 11576 | Forecast for moderate winter in 2019 at this time | 2019-12-20 | 2 | 3 | 6 | 17028 | Aryana Fitzpatrick
543341 | 2019-10-28 | Legal | Systems | Threat | A new communication system is being used for the project (SharePoint). | Information or 'reply by' dates are missed or team members fail to use the system efficiently. | 5 | Closed | 2 | 3 | 6 | 7796 | Training to be provided details of how to utilise SharePoint. IINC to monitor usage and lead by example. |  |  |  | 0 |  | Aryana Fitzpatrick
346321 | 2019-10-28 | Commercial Risks | Landscape requirements | Opportunity | KOL are investigating ways of reducing green space maintenance cost. | Increase / reduce the cost of ACWs works but reduce long term cost to KOL | 5 | Closed | 3 | 2 | 6 | 9049 | KOL to provide details of changes required following workshop. |  |  |  | 0 |  | Mikayla Downs
346321 | 2019-10-28 | Legal | RCC approval requires revised bellmouth | Threat | Instruction to proceed with Bellmouth is issued late. | Delay to CREXcommencing formation of site entrance on site. | 5 | Closed | 3 | 2 | 6 | 10806 | Fairhurst to provide updated Bellmouth drawing/ co-ordinates ASAP. |  |  |  | 0 |  | Madelyn Davila
346321 | 2019-10-28 | Technical | Utilities Quotations | Threat/Opportunity | Utilities quotes are to be refreshed, the cost might have increased since the original quotation was received. | Change to cost | 5 | Closed | 3 | 2 | 6 | 4464 | Utilities quotations are currently being refreshed. Review opportunity / risk again when new quotations received. |  |  |  | 0 |  | Mikayla Downs
346321 | 2019-10-28 | Commercial Risks | Delay to Statutory Approvals | Threat | Delayed responses from statutory bodies may delay programme | May delay CREXand/ or sectional completion dates | 5 | Open | 2 | 3 | 6 | 12575 | Maintaining regular liaison with Building Control, Planning and Roads Dept. | 2019-12-04 | 2 | 2 | 4 | 21811 | Litzy Ross
346321 | 2019-10-28 | Technical | Neighbours complaints | Threat | The site location is in a dense residential area in close proximity to construction activities. There is a chance of neighbours raising nuisance complaints i.e. noise, dust and vibration. | Potential reputational damage to KOL. | 5 | Open | 3 | 1 | 3 | 2016 | Inform neighbours of progress on site and provide advance notice of noisy works. | 2020-01-04 | 1 | 2 | 2 | 8381 | Aryana Fitzpatrick
346321 | 2019-10-28 | Commercial Risks | Site Security | Threat | The site is located in a densely populated residential social housing area. | Safety and reputational damage. | 5 | Open | 3 | 1 | 3 | 1839 | Ensure site security systems are maintained and reviewed as works progress. |  |  |  | 0 |  | Litzy Ross

## Employee List
Name | Position
Mattie Jenkins | PM
Tyson Santiago | PM
Mikayla Vaughn | PM
Madelyn Davila | PM
Aryana Fitzpatrick | PM
Litzy Ross | PM
Mikayla Downs | PM
Alexis Herrera | Assistant PM
Charity Gutierrez | Assistant PM
Kasen Archer | Assistant PM
Kira Watson | Assistant PM
Elisa Jenkins | Assistant PM

## RFI Register
If date repplied is blank then items is still awaiting client decision
Project ID | TQ Ref No. | Subject | Date Received | Decision Due | Date Replied | Instruction required? | Reason Instruction Required | Approval to issue Instruction received? | Date Instruction Issued | Comments | Status
543341 | 001 | Station / bench mark points for Drainage | 2019-07-16 | 2020-01-29 | 2020-03-13 | No |  |  |  |  | Closed
543341 | 002 | Manhole covers Identification | 2019-07-16 | 2020-04-26 | 2020-12-15 | No |  |  |  |  | Open
543341 | 003 | Swale levels | 2019-07-16 | 2019-12-12 |  | No |  |  |  |  | Closed
543341 | 004 | Setting out information Stronsay park swale section | 2019-07-17 | 2019-09-28 |  | No |  |  |  |  | Closed
543341 | 005 | Reinstatement Requirements | 2019-07-29 | 2020-04-19 | 2020-12-12 | Yes | Additional works | DA recevied verbal from MH | 2019-08-13 |  | Closed
543341 | 006 | Trench reinstatement in carriageway | 2019-07-22 | 2020-04-01 | 2020-04-12 | No |  |  |  |  | Open
543341 | 007 | Swale Overflowing | 2019-07-30 | 2020-01-17 |  | No |  |  |  |  | Closed
543341 | 008 | Swale Crossing | 2019-07-29 | 2020-02-02 | 2018-12-12 | No |  |  |  |  | Closed
543341 | 009 | Road construction | 2019-08-01 | 2019-12-18 | 2018-04-12 | No |  |  |  |  | Open
543341 | 010 | Provisional sum for tree replacement in WoQ | 2019-08-01 | 2019-11-17 | 2019-12-17 | Yes | Removal of Scope | Sent email to MH | 2019-09-10 |  | Closed
543341 | 011 | Moving of manhole 8 | 2019-08-05 | 2020-03-18 |  | No | Change to the works | AWAITING KOLP TO ISSUSE DRAWING. CHASED 01/10/19 |  |  | Closed
543341 | 012 | Invert levels | 2019-08-12 | 2019-10-11 | 2020-05-31 | Yes | Change to the works | Sent email to MH | 2019-09-10 |  | Open
543341 | 013 | Scoot loops for traffic lights | 2019-08-13 | 2020-05-27 | 2018-12-12 | Yes | Excluded from BoQ | DA recevied verbal from MH | 2019-08-23 |  | Closed
543341 | 014 | Deep watermain | 2019-08-19 | 2019-10-22 |  | Yes | Change to the works | DA recevied verbal from MH | 2019-08-23 |  | Open
543341 | 015 | Conflict with domestic foul & storm drainage | 2019-08-22 | 2019-10-01 | 2020-06-14 | Yes | Revised drawings issued | Sent email to MH | 2019-09-12 |  | Closed
543341 | 016 | MH 4 / Cast Iron Pipe | 2019-08-28 | 2020-04-05 | 2020-07-11 | Yes | Change to the works | Sent email to MH | 2019-08-30 |  | Open
543341 | 017 | MH 4 / DIVERT | 2019-08-29 | 2020-04-17 | 2020-06-05 | No | Change to the works | Sent email to MH |  |  | Closed
543341 | 018 | Road Long | 2019-09-09 | 2020-01-20 |  | Yes | Additional works | Sent email to MH | 2019-09-12 |  | Closed
543341 | 019 | Excavation and Replacing Kerb Log Kerb | 2019-09-11 | 2020-05-07 | 2020-09-23 | Yes |  | Sent email to MH | 2019-10-03 |  | Closed
543341 | 020 | New NMNess, permits etc | 2019-09-12 | 2019-11-17 | 2020-02-13 | No |  |  |  |  | Open
346321 | 001 | Stock Pile | 2019-09-12 | 2020-02-17 |  | No |  |  |  | No response issued, answered under TQ023 | Closed
346321 | 002 | QueDA on levels | 2019-09-27 | 2019-11-06 | 2019-12-31 | No |  |  |  |  | Closed
346321 | 003 | MH&P | 2019-09-30 | 2019-11-11 | 2020-02-05 | No |  |  |  | KOLP advised closed | Closed
346321 | 004 | Earthworks Strategy Cut and Fill | 2019-09-30 | 2019-12-01 | 2020-09-16 | No |  |  |  | With JHYG | Open
346321 | 005 | Existing Stockpile | 2019-09-30 | 2020-02-14 |  | No |  |  |  |  | Closed
346321 | 006 | Mains Services | 2019-09-30 | 2020-04-18 | 2020-06-19 | No |  |  |  |  | Open
346321 | 007 | Routes for Electrical Wiring within flats | 2019-09-30 | 2020-01-01 | 2020-07-09 | No |  |  |  |  | Closed
346321 | 008 | Position of HE and Routes for Plumbing and Heating Pipework within flats | 2019-09-30 | 2020-05-09 | 2020-05-14 | No |  |  |  |  | Open
346321 | 009 | Position of Mains services Incoming ducts including type and size to each stairwell in each block of flats | 2019-09-30 | 2019-10-31 | 2020-07-15 | No |  |  |  |  | Closed
346321 | 010 | Positions of Drainage Pop ups | 2019-09-30 | 2020-01-31 |  | No |  |  |  |  | Open
346321 | 011 | Type of Facing Brick | 2019-10-04 | 2020-01-17 | 2020-10-11 | No |  |  |  | KOLP advised closed | Closed
346321 | 012 | Manhole cover identification & frame & cover depth | 2019-07-26 | 2020-04-15 | 2021-02-01 | No |  |  |  |  | Closed
346321 | 013 | Cut & Fill Levels drawing & re use of site stockpile | 2019-10-09 | 2020-03-16 | 2020-07-19 | No |  |  |  |  | Closed
346321 | 014 | Bellmouth and Sewers | 2019-10-10 | 2020-04-16 |  | Yes | Change to the works |  | 2019-10-28 |  | Open
346321 | 015 | Road section. | 2019-10-16 | 2020-02-20 |  | No |  |  |  |  | Closed
346321 | 016 | Gas Main Location | 2019-10-17 | 2019-11-26 |  | Yes |  |  | 2019-10-28 |  | Closed
346321 | 017 | Form TWD NMNess spoil heap | 2019-07-16 | 2019-09-30 | 2020-03-18 | No |  |  |  | KOLP advised closed | Closed
346321 | 018 | Mortar Specification and Colour for Block work and Facing brick for both sub structure and superstructure works | 2019-07-16 | 2019-12-05 | 2020-03-25 | No |  |  |  |  | Open
346321 | 019 | Levels bet | 2019-07-16 | 2019-12-17 |  | Yes |  | DA recevied verbal from MH | 2019-10-28 |  | Closed
678426 | 001 | Drainage Materials | 2019-07-16 | 2020-02-05 | 2020-05-30 | No |  |  |  |  | Closed
678426 | 002 | Existing Drainage Foul Pipe | 2019-07-17 | 2020-01-17 | 2020-02-23 | Yes | Additional works | DA recevied verbal from MH | 2019-08-13 |  | Open
678426 | 003 | NPO for culvert works | 2019-07-29 | 2019-09-02 |  | Yes | Change to the works | DA recevied verbal from MH | 2019-08-13 |  | Closed
678426 | 004 | Revised BoQ item K732 | 2019-07-22 | 2019-10-22 | 2019-11-16 | Yes | Excluded from BoQ | DA recevied verbal from MH | 2019-08-23 |  | Closed
678426 | 005 | Additional Headwall Fencing | 2019-07-30 | 2020-03-17 | 2020-07-01 | Yes | New requset from NMN | Sent email to MH | 2019-09-10 |  | Open
678426 | 006 | Heras Fencing | 2019-07-29 | 2020-05-06 | 2020-07-04 | Yes | Update from NMN | Sent email to MH | 2019-09-12 |  | Closed
678426 | 007 | Additional Headwall Fencing | 2019-08-01 | 2020-03-26 | 2021-01-18 | Yes | N/A | Sent email to MH | 2019-10-02 |  | Closed
678426 | 008 | Traffic Loops | 2019-08-01 | 2020-03-17 | 2020-04-04 | Yes | N/A | Sent email to MH | 2019-10-02 |  | Open
678426 | 009 | Earthworks Strategy Document | 2019-08-05 | 2020-06-01 |  | Yes | N/A | ? | 2019-10-17 |  | Closed
678426 | 010 | Removal of Fly Tipping Debris from site | 2019-08-12 | 2020-05-09 | 2020-06-02 | No |  |  |  |  | Closed
678426 | 011 | DiscoveDA of Field Drain on site 281019 | 2019-08-13 | 2019-12-27 | 2020-02-08 | No |  |  |  |  | Closed
678426 | 012 | NBS spec VE Schedule | 2019-08-19 | 2020-02-20 | 2020-08-15 | No |  |  |  | Awaited - 25/11/2019 | Open
678426 | 013 | Pipe size | 2019-08-22 | 2020-02-19 | 2020-10-13 | No |  |  |  |  | Open
678426 | 014 | Existing Traps | 2019-08-28 | 2019-09-27 |  | No |  |  |  |  | Closed
678426 | 015 | Speed bump | 2019-08-29 | 2020-01-24 | 2020-03-14 | No |  |  |  | With NMN 22/11/2019 | Open
678426 | 016 | Body of water within site | 2019-09-09 | 2020-04-19 | 2020-12-03 | No |  |  |  |  | Closed
678426 | 017 | PQS Contamination comment | 2019-09-11 | 2020-01-21 |  | No |  |  |  | Draft instruction sent to Fairhurst and Langmuir & Hay | Open
678426 | 018 | Survey Stations | 2019-09-12 | 2019-11-03 | 2020-01-20 | No |  |  |  |  | Open
678426 | 019 | Dalkeith Road | 2019-09-12 | 2020-01-09 |  | No |  |  |  |  | Closed
678426 | 020 | Check on ground conditions and possible requirement for Dalkeith | 2019-09-27 | 2020-04-30 | 2021-02-09 | No |  |  |  |  | Open
678426 | 021 | Running Water Field Drain at proposed new road entrance from 1234 Road | 2019-09-30 | 2019-12-24 | 2020-08-12 | No |  |  |  |  | Open
678426 | 022 | Foul Connections | 2019-09-30 | 2020-02-04 |  | No |  |  |  |  | Closed
678426 | 023 | Excessive Top soil being discovered on site | 2019-09-30 | 2020-06-03 | 2020-08-02 | No |  |  |  |  | Closed
678426 | 024 | SGN Request to Lower Gas Main at 1234 Road as opposed to protecting existing gas main. | 2019-09-30 | 2020-04-12 | 2020-08-21 | No |  |  |  |  | Open

## Commercial Report
Project ID | ID | Description | Nr of Units | Current Development Cost (CD) | Cost per Unit | Spend to Date | Previous Month Spend to Date
543341 | 1 | Overall Budget | 400 | 350000000 | 875000 | 120000000 | 70000000
543341 | 2 | Grant Funding |  | 40000000
543341 | 3 | Additional Funding |  | 50000000
543341 | 4 | TOTAL | 400 | 440000000 | 875000 | 120000000 | 70000000
346321 | 1 | Overall Budget | 332 | 280000000 | 843373.494 | 45000000 | 28000000
346321 | 2 | Grant Funding |  | 70000000
346321 | 3 | Additional Funding |  | 60000000
346321 | 4 | TOTAL | 332 | 410000000 | 843373.494 | 45000000 | 28000000
678426 | 1 | Overall Budget | 460 | 360000000 | 782608.6957 | 100000000 | 72000000
678426 | 2 | Grant Funding |  | 70000000
678426 | 3 | Additional Funding |  | 60000000
678426 | 4 | TOTAL | 460 | 490000000 | 782608.6957 | 100000000 | 72000000

## RIBA Quality
Project ID | ID | Stage 0 | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Stage 6 | Stage 7
543341 | 1 | N/A | Medium | High | N/A | Medium | Medium | Low | Low
543341 | 2 | Low | Low | High | Low | Medium | N/A | N/A | Medium
543341 | 3 | Medium | High | Medium | Medium | Medium | Medium | High | Low
543341 | 4 | High | Low | N/A | N/A | N/A | High | N/A | High
543341 | 5 | Low | Low | High | N/A | Medium | High | High | Low
543341 | 6 | Low | N/A | High | High | N/A | High | Medium | High
543341 | 7 | N/A | High | Medium | N/A | N/A | Low | High | Medium
543341 | 8 | N/A | Medium | Medium | Medium | Medium | Low | N/A | Low
543341 | 9 | N/A | Low | Low | Low | N/A | Medium | N/A | Low
543341 | 10 | Medium | N/A | High | Medium | Low | High | High | High
543341 | 11 | N/A | N/A | Low | N/A | Medium | Medium | N/A | N/A
543341 | 12 | Medium | N/A | Low | N/A | Medium | High | Low | N/A
543341 | 13 | High | Low | N/A | Medium | Medium | Medium | Medium | N/A
543341 | 14 | Low | N/A | Low | Medium | Medium | Medium | Low | Low
543341 | 15 | Low | High | Medium | Low | Medium | N/A | Low | Medium
543341 | 16 | N/A | High | Medium | High | N/A | High | Low | High
543341 | 17 | High | Low | N/A | High | Medium | N/A | Low | Low
543341 | 18 | Medium | Medium | High | High | Medium | Medium | High | High
543341 | 19 | Low | High | High | Medium | Low | High | N/A | Medium
543341 | 20 | Medium | N/A | High | Medium | N/A | Medium | N/A | High
346321 | 1 | High | Low | Medium | N/A | Low | Medium | N/A | Low
346321 | 2 | High | Low | High | N/A | Medium | N/A | N/A | Low
346321 | 3 | N/A | High | Low | Low | Medium | High | Medium | Low
346321 | 4 | Medium | Low | Medium | High | Medium | High | Low | Medium
346321 | 5 | N/A | Medium | N/A | Low | Low | N/A | Low | N/A
346321 | 6 | Low | N/A | N/A | High | Medium | Low | Medium | Medium
346321 | 7 | N/A | N/A | Medium | High | High | N/A | Low | High
346321 | 8 | Medium | Low | N/A | High | N/A | High | Low | Medium
346321 | 9 | Low | N/A | N/A | High | Medium | High | High | High
346321 | 10 | N/A | Medium | High | N/A | N/A | Medium | Low | Low
346321 | 11 | High | N/A | High | N/A | Medium | Low | High | Low
346321 | 12 | High | High | N/A | N/A | High | Low | High | Low
346321 | 13 | Medium | Low | High | High | Low | Medium | Low | N/A
346321 | 14 | Low | High | N/A | Medium | Low | Low | High | Medium
346321 | 15 | High | Medium | Medium | High | Low | High | N/A | Medium
346321 | 16 | N/A | Medium | High | N/A | High | High | N/A | N/A
346321 | 17 | N/A | Medium | N/A | N/A | Low | Low | Low | Low
346321 | 18 | Medium | Medium | Medium | N/A | High | Medium | Low | High
346321 | 19 | Low | High | N/A | N/A | N/A | Low | High | Medium
346321 | 20 | N/A | Low | Medium | High | High | Low | N/A | Medium
678426 | 1 | Medium | High | High | High | Low | High | N/A | Medium
678426 | 2 | N/A | Medium | High | N/A | High | Medium | Low | High
678426 | 3 | High | N/A | N/A | Medium | Low | Medium | N/A | Medium
678426 | 4 | Low | Medium | High | Medium | Low | N/A | High | N/A
678426 | 5 | High | High | Medium | N/A | High | Medium | High | Medium
678426 | 6 | High | Medium | Medium | N/A | N/A | N/A | High | N/A
678426 | 7 | High | High | High | High | High | High | High | Low
678426 | 8 | High | N/A | High | High | High | High | Low | N/A
678426 | 9 | High | Medium | Medium | High | Low | N/A | High | N/A
678426 | 10 | High | High | High | High | Low | High | N/A | Low
678426 | 11 | N/A | Medium | N/A | High | N/A | Medium | Medium | Medium
678426 | 12 | Low | Low | N/A | Medium | High | Medium | High | N/A
678426 | 13 | Medium | Medium | High | High | Medium | Medium | High | N/A
678426 | 14 | Low | Low | Low | Low | Medium | Low | Low | N/A
678426 | 15 | N/A | N/A | High | Medium | High | N/A | N/A | High
678426 | 16 | N/A | Low | N/A | Low | Low | Medium | Low | N/A
678426 | 17 | High | High | Low | High | High | Low | Low | High
678426 | 18 | Low | Low | Medium | Low | Low | Low | Medium | Medium
678426 | 19 | N/A | Low | High | N/A | N/A | N/A | N/A | Medium
678426 | 20 | Low | Low | N/A | N/A | Low | High | Medium | Low

## Health and Safety
Project ID | Activity / Procedure / Element | Status | Severity | Priority | Comments
543341 | Is the form F10 on display? | Closed | 4 | 2
543341 | Is the emergency aid notice on display? | Closed | 3 | 4 | This information is displayed in the canteen area
543341 | Is the HSE what you should know poster on display? | Open | 4 | 1 |  | Severity Key: |  | Priority Key:
543341 | Is the employers liability insurance on display? | Closed | 1 | 3 |  | 1 | Significant or imminent danger arising from this item | 1 | Immediately (Now)
543341 | Is the public liability insurance on display? | Open | 3 | 4 |  | 2 | Total omission of documentation / control for this item | 2 | Promptly (Within 1 day)
543341 | Is the construction phase plan on site? | Open | 2 | 3 |  | 3 | Omission / concern for this item | 3 | Short term (Within 3 days)
543341 | Is the fire plan on site? | Closed | 4 | 4 |  | 4 | Minor omission / concern for this item | 4 | Long term (Within 7 days)
543341 | Is the accident book on site? | Open | 2 | 2
543341 | Is the visitors book on site? | Closed | 1 | 3 | Copy kept within site office and updated by the SM team
543341 | Is the safety induction register on site? | Closed | 4 | 4
543341 | Are the scaffolding register or scaf' tags on site? | Closed | 3 | 3
543341 | Are the plant inspection records on site? | Open | 4 | 1
543341 | Are the excavation inspection records on site? | Open | 1 | 4
543341 | Have they been undertaken and records retained? | Open | 3 | 1
543341 | Are they being carried out and retained? | Closed | 3 | 3
543341 | Are they being carried out, adhered to, and retained? | Closed | 3 | 3
543341 | Have procedures been developed (incl. for cabins)? | Closed | 4 | 4
543341 | Is there a means of raising the alarm? | Open | 2 | 1
543341 | Is the fire marshall / first aider identified? | Closed | 4 | 4
543341 | Are there adequate escape routes and are they kept clear? | Closed | 4 | 1 | Review check sheets available within Site Folders
543341 | Are flammables stored appropriately (inc LPG)? | Open | 2 | 2
543341 | Are naked flames and smoking prohibited in these areas? | Open | 4 | 2
543341 | Are there adequate procedures for the removal of waste? Is it removed safely? | Open | 4 | 3
543341 | Are there an adequate number / type of fire extinguishers? | Open | 3 | 4
543341 | Retrieving data. Wait a few seconds and try to cut or copy again. | Closed | 3 | 1
346321 | Is the form F10 on display? | Closed | 3 | 2
346321 | Is the emergency aid notice on display? | Open | 2 | 1 | This information is displayed in the canteen area
346321 | Is the HSE what you should know poster on display? | Closed | 2 | 2
346321 | Is the employers liability insurance on display? | Closed | 1 | 2
346321 | Is the public liability insurance on display? | Open | 3 | 4
346321 | Is the construction phase plan on site? | Open | 4 | 3
346321 | Is the fire plan on site? | Closed | 4 | 1
346321 | Is the accident book on site? | Closed | 4 | 3
346321 | Is the visitors book on site? | Closed | 3 | 4 | Copy kept within site office and updated by the SM team
346321 | Is the safety induction register on site? | Open | 2 | 2
346321 | Are the scaffolding register or scaf' tags on site? | Open | 4 | 1
346321 | Are the plant inspection records on site? | Open | 3 | 2
346321 | Are the excavation inspection records on site? | Open | 4 | 4
346321 | Have they been undertaken and records retained? | Open | 4 | 2
346321 | Are they being carried out and retained? | Open | 1 | 2
346321 | Are they being carried out, adhered to, and retained? | Open | 4 | 3
346321 | Have procedures been developed (incl. for cabins)? | Closed | 2 | 3
346321 | Is there a means of raising the alarm? | Open | 2 | 1
346321 | Is the fire marshall / first aider identified? | Closed | 4 | 3
346321 | Are there adequate escape routes and are they kept clear? | Open | 1 | 1 | Review check sheets available within Site Folders
346321 | Are flammables stored appropriately (inc LPG)? | Closed | 3 | 1
346321 | Are naked flames and smoking prohibited in these areas? | Open | 1 | 2
346321 | Are there adequate procedures for the removal of waste? Is it removed safely? | Open | 2 | 1
346321 | Are there an adequate number / type of fire extinguishers? | Open | 4 | 3
346321 | Retrieving data. Wait a few seconds and try to cut or copy again. | Closed | 3 | 3
678426 | Is the form F10 on display? | Open | 3 | 2
678426 | Is the emergency aid notice on display? | Open | 4 | 4 | This information is displayed in the canteen area
678426 | Is the HSE what you should know poster on display? | Open | 3 | 2
678426 | Is the employers liability insurance on display? | Open | 1 | 2
678426 | Is the public liability insurance on display? | Open | 4 | 4
678426 | Is the construction phase plan on site? | Closed | 2 | 3
678426 | Is the fire plan on site? | Closed | 4 | 1
678426 | Is the accident book on site? | Open | 4 | 4
678426 | Is the visitors book on site? | Closed | 3 | 1 | Copy kept within site office and updated by the SM team
678426 | Is the safety induction register on site? | Open | 3 | 2
678426 | Are the scaffolding register or scaf' tags on site? | Open | 1 | 1
678426 | Are the plant inspection records on site? | Closed | 4 | 2
678426 | Are the excavation inspection records on site? | Open | 1 | 2
678426 | Have they been undertaken and records retained? | Open | 4 | 2
678426 | Are they being carried out and retained? | Closed | 4 | 2
678426 | Are they being carried out, adhered to, and retained? | Open | 1 | 3
678426 | Have procedures been developed (incl. for cabins)? | Open | 4 | 2
678426 | Is there a means of raising the alarm? | Closed | 1 | 1
678426 | Is the fire marshall / first aider identified? | Open | 1 | 2
678426 | Are there adequate escape routes and are they kept clear? | Closed | 3 | 1 | Review check sheets available within Site Folders
678426 | Are flammables stored appropriately (inc LPG)? | Open | 2 | 1
678426 | Are naked flames and smoking prohibited in these areas? | Open | 2 | 4
678426 | Are there adequate procedures for the removal of waste? Is it removed safely? | Open | 1 | 2
678426 | Are there an adequate number / type of fire extinguishers? | Open | 2 | 3
678426 | Retrieving data. Wait a few seconds and try to cut or copy again. | Closed | 1 | 3

## Programme Scheldule
Project ID | Task Name | Start Date | Finish Date | Progress | RIBA Stage
543341 | Strategic Definition | 2019-01-11 | 2019-01-25 | 100 | RIBA Stage 0
543341 | Preparation and Brief | 2019-01-26 | 2019-02-15 | 100 | RIBA Stage 1
543341 | Concept Design | 2019-02-16 | 2019-03-06 | 100 | RIBA Stage 2
543341 | Developed Design | 2019-03-07 | 2019-03-21 | 100 | RIBA Stage 3
543341 | Technical Design | 2019-03-22 | 2019-04-19 | 100 | RIBA Stage 4
543341 | Construction | 2019-04-20 | 2019-05-18 | 26 | RIBA Stage 5
543341 | Handover and Close Out | 2019-05-19 | 2019-05-26 | 0 | RIBA Stage 6
543341 | Post-occupancy Evaluation | 2019-05-27 | 2019-06-14 | 0 | RIBA Stage 7
346321 | Strategic Definition | 2018-12-06 | 2018-12-23 | 100 | RIBA Stage 0
346321 | Preparation and Brief | 2018-12-24 | 2019-01-11 | 100 | RIBA Stage 1
346321 | Concept Design | 2019-01-12 | 2019-01-23 | 100 | RIBA Stage 2
346321 | Developed Design | 2019-01-24 | 2019-02-05 | 100 | RIBA Stage 3
346321 | Technical Design | 2019-02-06 | 2019-02-25 | 100 | RIBA Stage 4
346321 | Construction | 2019-02-26 | 2019-03-21 | 56 | RIBA Stage 5
346321 | Handover and Close Out | 2019-03-22 | 2019-04-18 | 0 | RIBA Stage 6
346321 | Post-occupancy Evaluation | 2019-04-19 | 2019-05-10 | 0 | RIBA Stage 7
678426 | Strategic Definition | 2019-02-02 | 2019-02-22 | 100 | RIBA Stage 0
678426 | Preparation and Brief | 2019-02-23 | 2019-03-12 | 100 | RIBA Stage 1
678426 | Concept Design | 2019-03-13 | 2019-03-27 | 100 | RIBA Stage 2
678426 | Developed Design | 2019-03-28 | 2019-04-04 | 100 | RIBA Stage 3
678426 | Technical Design | 2019-04-05 | 2019-04-12 | 100 | RIBA Stage 4
678426 | Construction | 2019-04-13 | 2019-04-26 | 34 | RIBA Stage 5
678426 | Handover and Close Out | 2019-04-27 | 2019-05-08 | 0 | RIBA Stage 6
678426 | Post-occupancy Evaluation | 2019-05-09 | 2019-05-23 | 0 | RIBA Stage 7

## CostX
This data is for all of the projects and cannot be separated into single projects
Code | Description | SubTotal | Current Spend | Code2 | Category | Cat1 | Cat2 | Cat3 | Cat4
0 | FACILITATING WORKS |  | 0 | A0 | 0 | 0 FACILITATING WORKS
0.1 | Toxic/hazardous/contaminated material treatment |  | 0 | A0.1 | 1 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment
0.1.1 | Toxic or hazardous material removal |  | 0 | A0.1.1 | 2 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.1 Toxic or hazardous material removal
0.1.1.1 | Toxic or hazardous material removal: details to be stated. |  | 0 | A0.1.1.1 | 3 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.1 Toxic or hazardous material removal | 0.1.1.1 Toxic or hazardous material removal: details to be stated.
0.1.1.2 | Toxic or hazardous chemical removal: details to be stated. |  | 0 | A0.1.1.2 | 3 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.1 Toxic or hazardous material removal | 0.1.1.2 Toxic or hazardous chemical removal: details to be stated.
0.1.2 | Contaminated land |  | 0 | A0.1.2 | 2 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.2 Contaminated land
0.1.2.1 | Contaminated ground material removal: details to be stated. |  | 0 | A0.1.2.1 | 3 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.2 Contaminated land | 0.1.2.1 Contaminated ground material removal: details to be stated.
0.1.2.2 | Contaminated ground material treatment: details to be stated. |  | 0 | A0.1.2.2 | 3 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.2 Contaminated land | 0.1.2.2 Contaminated ground material treatment: details to be stated.
0.1.3 | Eradication of plant growth |  | 0 | A0.1.3 | 2 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.3 Eradication of plant growth
0.1.3.1 | Eradication by dig and dump strategy: details to be stated. |  | 0 | A0.1.3.1 | 3 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.3 Eradication of plant growth | 0.1.3.1 Eradication by dig and dump strategy: details to be stated.
0.1.3.2 | Eradication by chemical treatment: details to be stated. |  | 0 | A0.1.3.2 | 3 | 0 FACILITATING WORKS | 0.1 Toxic/hazardous/contaminated material treatment | 0.1.3 Eradication of plant growth | 0.1.3.2 Eradication by chemical treatment: details to be stated.
0.2 | Major demolition works |  | 0 | A0.2 | 1 | 0 FACILITATING WORKS | 0.2 Major demolition works
0.2.1 | Demolition works |  | 0 | A0.2.1 | 2 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works
0.2.1.1 | Demolition of entire buildings: details to be stated. |  | 0 | A0.2.1.1 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.1 Demolition of entire buildings: details to be stated.
0.2.1.2 | Demolition of major parts of existing buildings: details to be stated. |  | 0 | A0.2.1.2 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.2 Demolition of major parts of existing buildings: details to be stated.
0.2.1.3 | Temporary propping to existing basement retaining walls: details, including type of material, whether single or double props, type of anchor blocks/foundations, to be stated. |  | 0 | A0.2.1.3 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.3 Temporary propping to existing basement retaining walls: details, including type of material, whether single or double props, type of anchor blocks/foundations, to be stated.
0.2.1.4 | Extra over temporary propping for providing wailings: details, including type of material, to be stated. |  | 0 | A0.2.1.4 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.4 Extra over temporary propping for providing wailings: details, including type of material, to be stated.
0.2.1.5 | Periodic technical inspections of temporary propping: details to be stated. |  | 0 | A0.2.1.5 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.5 Periodic technical inspections of temporary propping: details to be stated.
0.2.1.6 | Returning to site to reposition temporary props: details, including type of material, whether single or double props, type of anchor blocks/foundations (if new required), to be stated. |  | 0 | A0.2.1.6 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.6 Returning to site to reposition temporary props: details, including type of material, whether single or double props, type of anchor blocks/foundations (if new required), to be stated.
0.2.1.7 | Removal of temporary props: details to be stated. |  | 0 | A0.2.1.7 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.7 Removal of temporary props: details to be stated.
0.2.1.8 | Removal of wailings: details to be stated. |  | 0 | A0.2.1.8 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.8 Removal of wailings: details to be stated.
0.2.1.9 | Grubbing up of anchor blocks/foundations to temporary props and infilling voids: details, including type of filling material, size of void to be stated. | 50000 | 53997 | A0.2.1.9 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.1 Demolition works | 0.2.1.9 Grubbing up of anchor blocks/foundations to temporary props and infilling voids: details, including type of filling material, size of void to be stated.
0.2.2 | Soft strip works |  | 0 | A0.2.2 | 2 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.2 Soft strip works
0.2.2.1 | Preparatory to demolition: extent of works to be stated. |  | 0 | A0.2.2.1 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.2 Soft strip works | 0.2.2.1 Preparatory to demolition: extent of works to be stated.
0.2.2.2 | Preparatory to refurbishment: extent of works to be stated. |  | 0 | A0.2.2.2 | 3 | 0 FACILITATING WORKS | 0.2 Major demolition works | 0.2.2 Soft strip works | 0.2.2.2 Preparatory to refurbishment: extent of works to be stated.
0.3 | Temporary support to adjacent structures |  | 0 | A0.3 | 1 | 0 FACILITATING WORKS | 0.3 Temporary support to adjacent structures
0.3 | Temporary support to adjacent structures |  | 0 | A0.3 | 1 | 0 FACILITATING WORKS | 0.3 Temporary support to adjacent structures
0.3.1 | Temporary support to adjacent structures |  | 0 | A0.3.1 | 2 | 0 FACILITATING WORKS | 0.3 Temporary support to adjacent structures | 0.3.1 Temporary support to adjacent structures
0.3.1.1 | Support structures: details to be stated. |  | 0 | A0.3.1.1 | 3 | 0 FACILITATING WORKS | 0.3 Temporary support to adjacent structures | 0.3.1 Temporary support to adjacent structures | 0.3.1.1 Support structures: details to be stated.
0.3.1.2 | Taking down and repositioning support structures: details to be stated. |  | 0 | A0.3.1.2 | 3 | 0 FACILITATING WORKS | 0.3 Temporary support to adjacent structures | 0.3.1 Temporary support to adjacent structures | 0.3.1.2 Taking down and repositioning support structures: details to be stated.
0.3.1.3 | Periodic technical inspections of temporary support structures: details to be stated. |  | 0 | A0.3.1.3 | 3 | 0 FACILITATING WORKS | 0.3 Temporary support to adjacent structures | 0.3.1 Temporary support to adjacent structures | 0.3.1.3 Periodic technical inspections of temporary support structures: details to be stated.
0.3.1.4 | Removing support structures: details to be stated. |  | 0 | A0.3.1.4 | 3 | 0 FACILITATING WORKS | 0.3 Temporary support to adjacent structures | 0.3.1 Temporary support to adjacent structures | 0.3.1.4 Removing support structures: details to be stated.
0.4 | Specialist groundworks |  | 0 | A0.4 | 1 | 0 FACILITATING WORKS | 0.4 Specialist groundworks
0.4.1 | Site dewatering and pumping |  | 0 | A0.4.1 | 2 | 0 FACILITATING WORKS | 0.4 Specialist groundworks | 0.4.1 Site dewatering and pumping
0.4.1.1 | Site dewatering: details to be stated. |  | 0 | A0.4.1.1 | 3 | 0 FACILITATING WORKS | 0.4 Specialist groundworks | 0.4.1 Site dewatering and pumping | 0.4.1.1 Site dewatering: details to be stated.
0.4.2 | Soil stabilisation measures |  | 0 | A0.4.2 | 2 | 0 FACILITATING WORKS | 0.4 Specialist groundworks | 0.4.2 Soil stabilisation measures
0.4.2.1 | Soil stabilisation measures: details to be stated. |  | 0 | A0.4.2.1 | 3 | 0 FACILITATING WORKS | 0.4 Specialist groundworks | 0.4.2 Soil stabilisation measures | 0.4.2.1 Soil stabilisation measures: details to be stated.
0.4.3 | Ground gas venting measures |  | 0 | A0.4.3 | 2 | 0 FACILITATING WORKS | 0.4 Specialist groundworks | 0.4.3 Ground gas venting measures
0.4.3.1 | Ground gas venting: details to be stated. |  | 0 | A0.4.3.1 | 3 | 0 FACILITATING WORKS | 0.4 Specialist groundworks | 0.4.3 Ground gas venting measures | 0.4.3.1 Ground gas venting: details to be stated.
0.5 | Temporary diversion works |  | 0 | A0.5 | 1 | 0 FACILITATING WORKS | 0.5 Temporary diversion works
0.5.1 | Temporary diversion works |  | 0 | A0.5.1 | 2 | 0 FACILITATING WORKS | 0.5 Temporary diversion works | 0.5.1 Temporary diversion works
0.5.1.1 | Temporary diversion of drains: details to be stated. |  | 0 | A0.5.1.1 | 3 | 0 FACILITATING WORKS | 0.5 Temporary diversion works | 0.5.1 Temporary diversion works | 0.5.1.1 Temporary diversion of drains: details to be stated.
0.5.1.2 | Temporary diversion of services: details to be stated. |  | 0 | A0.5.1.2 | 3 | 0 FACILITATING WORKS | 0.5 Temporary diversion works | 0.5.1 Temporary diversion works | 0.5.1.2 Temporary diversion of services: details to be stated.
0.5.1.3 | Temporary diversion of waterways: details to be stated. |  | 0 | A0.5.1.3 | 3 | 0 FACILITATING WORKS | 0.5 Temporary diversion works | 0.5.1 Temporary diversion works | 0.5.1.3 Temporary diversion of waterways: details to be stated.
0.6 | Extraordinary site investigation works |  | 0 | A0.6 | 1 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works
0.6.1 | Archaeological investigation |  | 0 | A0.6.1 | 2 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.1 Archaeological investigation
0.6.1.1 | Excavation works: details to be stated. |  | 0 | A0.6.1.1 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.1 Archaeological investigation | 0.6.1.1 Excavation works: details to be stated.
0.6.1.2 | Temporary screens and the like: details to be stated. |  | 0 | A0.6.1.2 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.1 Archaeological investigation | 0.6.1.2 Temporary screens and the like: details to be stated.
0.6.1.3 | Attendance on archaeologists. |  | 0 | A0.6.1.3 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.1 Archaeological investigation | 0.6.1.3 Attendance on archaeologists.
0.6.2 | Reptile/wildlife mitigation measures |  | 0 | A0.6.2 | 2 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.2 Reptile/wildlife mitigation measures
0.6.2.1 | Physical reptile/wildlife mitigation measures: details to be stated. |  | 0 | A0.6.2.1 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.2 Reptile/wildlife mitigation measures | 0.6.2.1 Physical reptile/wildlife mitigation measures: details to be stated.
0.6.2.2 | Temporary fences, barriers and the like: details to be stated. |  | 0 | A0.6.2.2 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.2 Reptile/wildlife mitigation measures | 0.6.2.2 Temporary fences, barriers and the like: details to be stated.
0.6.2.3 | Attendance. |  | 0 | A0.6.2.3 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.2 Reptile/wildlife mitigation measures | 0.6.2.3 Attendance.
0.6.3 | Other extraordinary site investigation works |  | 0 | A0.6.3 | 2 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.3 Other extraordinary site investigation works
0.6.3.1 | Physical site investigation works: details to be stated. |  | 0 | A0.6.3.1 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.3 Other extraordinary site investigation works | 0.6.3.1 Physical site investigation works: details to be stated.
0.6.3.2 | Temporary screens, fences, barriers and the like: details to be stated. |  | 0 | A0.6.3.2 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.3 Other extraordinary site investigation works | 0.6.3.2 Temporary screens, fences, barriers and the like: details to be stated.
0.6.3.3 | Attendance. |  | 0 | A0.6.3.3 | 3 | 0 FACILITATING WORKS | 0.6 Extraordinary site investigation works | 0.6.3 Other extraordinary site investigation works | 0.6.3.3 Attendance.
1 | SUBSTRUCTURE |  | 0 | A1 | 0 | 1 SUBSTRUCTURE
1.1.1 | Standard foundations |  | 0 | A1.1.1 | 2 | 1 SUBSTRUCTURE |  | 1.1.1 Standard foundations
1.1.1.1 | Strip foundations: details, including depth of foundation, to be stated. | 750000 | 678357 | A1.1.1.1 | 3 | 1 SUBSTRUCTURE |  | 1.1.1 Standard foundations | 1.1.1.1 Strip foundations: details, including depth of foundation, to be stated.
1.1.1.2 | Isolated pad foundations: details, including size of and reinforcement rate (kg/m3) to pile cap, to be stated. |  | 0 | A1.1.1.2 | 3 | 1 SUBSTRUCTURE |  | 1.1.1 Standard foundations | 1.1.1.2 Isolated pad foundations: details, including size of and reinforcement rate (kg/m3) to pile cap, to be stated.
1.1.1.3 | Extra for disposal of contaminated excavated material: details to be stated. | 125000 | 116004 | A1.1.1.3 | 3 | 1 SUBSTRUCTURE |  | 1.1.1 Standard foundations | 1.1.1.3 Extra for disposal of contaminated excavated material: details to be stated.
1.1.2 | Specialist foundations |  | 0 | A1.1.2 | 2 | 1 SUBSTRUCTURE |  | 1.1.2 Specialist foundations
1.1.2 | Piled foundations: |  | 0 | A1.1.2 | 2 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations:
1.1.2.1 | Piling mats/platforms: details, including thickness of mat/platform (mm), to be stated. |  | 0 | A1.1.2.1 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.1 Piling mats/platforms: details, including thickness of mat/platform (mm), to be stated.
1.1.2.2 | Piling plant: details to be stated. |  | 0 | A1.1.2.2 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.2 Piling plant: details to be stated.
1.1.2.3 | Moving piling rig to pile position. |  | 0 | A1.1.2.3 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.3 Moving piling rig to pile position.
1.1.2.4 | Piles: details, including type, diameter (mm) and depth (m) of piles, to be stated. |  | 0 | A1.1.2.4 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.4 Piles: details, including type, diameter (mm) and depth (m) of piles, to be stated.
1.1.2.5 | Extra for pile casings or linings: details, including material, length (m), diameter (mm) and if permanent or temporary, to be stated. |  | 0 | A1.1.2.5 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.5 Extra for pile casings or linings: details, including material, length (m), diameter (mm) and if permanent or temporary, to be stated.
1.1.2.6 | Caissons: details, including type, diameter (mm) and depth (m) of caisson, to be stated. |  | 0 | A1.1.2.6 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.6 Caissons: details, including type, diameter (mm) and depth (m) of caisson, to be stated.
1.1.2.7 | Disposal of excavated material arising from piling. |  | 0 | A1.1.2.7 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.7 Disposal of excavated material arising from piling.
1.1.2.8 | Extra for breaking through obstructions. |  | 0 | A1.1.2.8 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.8 Extra for breaking through obstructions.
1.1.2.9 | Cutting off tops of concrete piles and preparing pile heads. |  | 0 | A1.1.2.9 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.9 Cutting off tops of concrete piles and preparing pile heads.
1.1.2.10 | Pile tests: details, including type of test, pile type, diameter of pile and number of piles to be stated. |  | 0 | A1.1.2.10 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.10 Pile tests: details, including type of test, pile type, diameter of pile and number of piles to be stated.
1.1.2.11 | Vibro-compacted columns: details, including size (mm) and length (m) of column, to be stated. |  | 0 | A1.1.2.11 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.11 Vibro-compacted columns: details, including size (mm) and length (m) of column, to be stated.
1.1.2.12 | Pile caps: details, including size of and reinforcement rate (kg/m3) to pile cap, to be stated. |  | 0 | A1.1.2.12 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.12 Pile caps: details, including size of and reinforcement rate (kg/m3) to pile cap, to be stated.
1.1.2.13 | Ground beams: details, including size of and reinforcement rate (kg/m3) to pile cap, to be stated. |  | 0 | A1.1.2.13 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Piled foundations: | 1.1.2.13 Ground beams: details, including size of and reinforcement rate (kg/m3) to pile cap, to be stated.
1.1.2 | Underpinning: |  | 0 | A1.1.2 | 2 | 1 SUBSTRUCTURE |  | 1.1.2 Underpinning:
1.1.2.14 | Underpinning: details to be stated. |  | 0 | A1.1.2.14 | 3 | 1 SUBSTRUCTURE |  | 1.1.2 Underpinning: | 1.1.2.14 Underpinning: details to be stated.
1.1.3 | Lofloor construction |  | 0 | A1.1.3 | 2 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction
1.1.3.1 | Lofloor construction: details to be stated. | 480000 | 462823 | A1.1.3.1 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.1 Lofloor construction: details to be stated.
1.1.3.2 | Extra over lofloor construction for forming ramps and the like: details to be stated. |  | 0 | A1.1.3.2 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.2 Extra over lofloor construction for forming ramps and the like: details to be stated.
1.1.3.3 | Extra over lofloor construction for forming of lift pits and the like: details, including the number and size (m) of lift pits, to be stated. |  | 0 | A1.1.3.3 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.3 Extra over lofloor construction for forming of lift pits and the like: details, including the number and size (m) of lift pits, to be stated.
1.1.3.4 | Extra over lofloor construction for forming swimming pool tanks and the like: details, including the size (m), to be stated. |  | 0 | A1.1.3.4 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.4 Extra over lofloor construction for forming swimming pool tanks and the like: details, including the size (m), to be stated.
1.1.3.5 | Retaining walls at changes in level: details, including thickness (mm), height (m) and reinforcement rate (kg/m3), to be stated. |  | 0 | A1.1.3.5 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.5 Retaining walls at changes in level: details, including thickness (mm), height (m) and reinforcement rate (kg/m3), to be stated.
1.1.3.6 | Designed joints: details, including height (mm), to be stated. | 4500 | 4775 | A1.1.3.6 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.6 Designed joints: details, including height (mm), to be stated.
1.1.3.7 | Drainage below ground: details, including average depth of trench (m), type and nominal size of pipe (mm), and materials for beds and haunchings/surrounds, to be stated. | 22500 | 22593 | A1.1.3.7 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.7 Drainage below ground: details, including average depth of trench (m), type and nominal size of pipe (mm), and materials for beds and haunchings/surrounds, to be stated.
1.1.3.8 | Gullies, floor outlets and the like: details to be stated. |  | 0 | A1.1.3.8 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.8 Gullies, floor outlets and the like: details to be stated.
1.1.3.9 | Internal manholes, catch-pits, petrol interceptors or the like: details to be stated. |  | 0 | A1.1.3.9 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.9 Internal manholes, catch-pits, petrol interceptors or the like: details to be stated.
1.1.3.10 | Testing of drainage installations. | 2250 | 2163 | A1.1.3.10 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.10 Testing of drainage installations.
1.1.3.11 | Commissioning of drainage installations. | 2250 | 2399 | A1.1.3.11 | 3 | 1 SUBSTRUCTURE |  | 1.1.3 Lofloor construction | 1.1.3.11 Commissioning of drainage installations.
1.1.4 | Basement excavation |  | 0 | A1.1.4 | 2 | 1 SUBSTRUCTURE |  | 1.1.4 Basement excavation
1.1.4.1 | Basement excavation: details, including average depth of excavation, to be stated. |  | 0 | A1.1.4.1 | 3 | 1 SUBSTRUCTURE |  | 1.1.4 Basement excavation | 1.1.4.1 Basement excavation: details, including average depth of excavation, to be stated.
1.1.4.2 | Disposal of excavated material: details to be stated. |  | 0 | A1.1.4.2 | 3 | 1 SUBSTRUCTURE |  | 1.1.4 Basement excavation | 1.1.4.2 Disposal of excavated material: details to be stated.
1.1.4.3 | Extra for disposal of contaminated excavated material: details to be stated. |  | 0 | A1.1.4.3 | 3 | 1 SUBSTRUCTURE |  | 1.1.4 Basement excavation | 1.1.4.3 Extra for disposal of contaminated excavated material: details to be stated.
1.1.4.4 | Earthwork support: details to be stated. |  | 0 | A1.1.4.4 | 3 | 1 SUBSTRUCTURE |  | 1.1.4 Basement excavation | 1.1.4.4 Earthwork support: details to be stated.
1.1.4.5 | Additional excavation: details to be stated. |  | 0 | A1.1.4.5 | 3 | 1 SUBSTRUCTURE |  | 1.1.4 Basement excavation | 1.1.4.5 Additional excavation: details to be stated.
1.1.5 | Basement retaining walls |  | 0 | A1.1.5 | 2 | 1 SUBSTRUCTURE |  | 1.1.5 Basement retaining walls
1.1.5 | Basement retaining walls: |  | 0 | A1.1.5 | 2 | 1 SUBSTRUCTURE |  | 1.1.5 Basement retaining walls:
1.1.5.1 | Basement retaining wall: details to be stated. |  | 0 | A1.1.5.1 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Basement retaining walls: | 1.1.5.1 Basement retaining wall: details to be stated.
1.1.5 | Embedded basement retaining walls: |  | 0 | A1.1.5 | 2 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls:
1.1.5.2 | Piling mats/platforms: details, including thickness of mat/platform (mm), to be stated. |  | 0 | A1.1.5.2 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.2 Piling mats/platforms: details, including thickness of mat/platform (mm), to be stated.
1.1.5.3 | Piling plant: details to be stated. |  | 0 | A1.1.5.3 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.3 Piling plant: details to be stated.
1.1.5.4 | Moving piling rig to pile position. |  | 0 | A1.1.5.4 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.4 Moving piling rig to pile position.
1.1.5.5 | Guide walls: details to be stated. |  | 0 | A1.1.5.5 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.5 Guide walls: details to be stated.
1.1.5.6 | Piles: details, including type, diameter (mm), depth (m), total length (m) and embedded length (m) of piles of piles, to be stated. |  | 0 | A1.1.5.6 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.6 Piles: details, including type, diameter (mm), depth (m), total length (m) and embedded length (m) of piles of piles, to be stated.
1.1.5.7 | Contiguous bored pile walls: details, including diameter (mm), depth (m), total length (m) and embedded length (m) of piles of piles, to be stated. |  | 0 | A1.1.5.7 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.7 Contiguous bored pile walls: details, including diameter (mm), depth (m), total length (m) and embedded length (m) of piles of piles, to be stated.
1.1.5.8 | Disposal of excavated material arising from piling. |  | 0 | A1.1.5.8 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.8 Disposal of excavated material arising from piling.
1.1.5.9 | Cutting off tops of concrete piles. |  | 0 | A1.1.5.9 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.9 Cutting off tops of concrete piles.
1.1.5.10 | Steel sheet piling: details, including total area (m2) and total driven area (m2) to be stated. |  | 0 | A1.1.5.10 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.10 Steel sheet piling: details, including total area (m2) and total driven area (m2) to be stated.
1.1.5.11 | Cutting off surplus lengths steel sheet piling. |  | 0 | A1.1.5.11 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.11 Cutting off surplus lengths steel sheet piling.
1.1.5.12 | Pile tests: details to be stated. |  | 0 | A1.1.5.12 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.12 Pile tests: details to be stated.
1.1.5.13 | Diaphragm walls: details, including depth of excavation, thickness (mm) of wall reinforcement rate (kg/m3), to be stated. |  | 0 | A1.1.5.13 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.13 Diaphragm walls: details, including depth of excavation, thickness (mm) of wall reinforcement rate (kg/m3), to be stated.
1.1.5.14 | Ground anchors: details, including type, to be stated. |  | 0 | A1.1.5.14 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.14 Ground anchors: details, including type, to be stated.
1.1.5.15 | Trimming and cleaning faces of piled and diaphragm walls. |  | 0 | A1.1.5.15 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.15 Trimming and cleaning faces of piled and diaphragm walls.
1.1.5.16 | Temporary works: details to be stated. |  | 0 | A1.1.5.16 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.16 Temporary works: details to be stated.
1.1.5.17 | Removal of temporary works: details to be stated. |  | 0 | A1.1.5.17 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.17 Removal of temporary works: details to be stated.
1.1.5.18 | Capping beams: details, including beam size (mm) and reinforcement rate (kg/m3), to be stated. |  | 0 | A1.1.5.18 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.18 Capping beams: details, including beam size (mm) and reinforcement rate (kg/m3), to be stated.
1.1.5.19 | Basement retaining wall components: details to be stated. |  | 0 | A1.1.5.19 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.19 Basement retaining wall components: details to be stated.
1.1.5.20 | Concrete applied by spray or gun: details, including thickness (mm), to be stated. |  | 0 | A1.1.5.20 | 3 | 1 SUBSTRUCTURE |  | 1.1.5 Embedded basement retaining walls: | 1.1.5.20 Concrete applied by spray or gun: details, including thickness (mm), to be stated.
2 | SUPERSTRUCTURE |  | 0 | A2 | 0 | 2 SUPERSTRUCTURE
2.1 | Frame |  | 0 | A2.1 | 1 | 2 SUPERSTRUCTURE | 2.1 Frame
2.1.1 | Steel frames |  | 0 | A2.1.1 | 2 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.1 Steel frames
2.1.1.1 | Structural steel frame, including fittings and fixings: details, including size of column grid (m), to be stated. |  | 0 | A2.1.1.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.1 Steel frames | 2.1.1.1 Structural steel frame, including fittings and fixings: details, including size of column grid (m), to be stated.
2.1.1.2 | Fire protection to steel frame: details to be stated. |  | 0 | A2.1.1.2 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.1 Steel frames | 2.1.1.2 Fire protection to steel frame: details to be stated.
2.1.1.3 | Factory applied paint systems: details to be stated. |  | 0 | A2.1.1.3 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.1 Steel frames | 2.1.1.3 Factory applied paint systems: details to be stated.
2.1.2 | Space frames/decks |  | 0 | A2.1.2 | 2 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.2 Space frames/decks
2.1.2.1 | Space frame/deck, including structural support framework, fittings and fixings: details to be stated. |  | 0 | A2.1.2.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.2 Space frames/decks | 2.1.2.1 Space frame/deck, including structural support framework, fittings and fixings: details to be stated.
2.1.2.2 | Fire protection to steel frame: details to be stated. |  | 0 | A2.1.2.2 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.2 Space frames/decks | 2.1.2.2 Fire protection to steel frame: details to be stated.
2.1.2.3 | Factory applied paint systems: details to be stated. |  | 0 | A2.1.2.3 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.2 Space frames/decks | 2.1.2.3 Factory applied paint systems: details to be stated.
2.1.3 | Concrete casings to steel frames |  | 0 | A2.1.3 | 2 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.3 Concrete casings to steel frames
2.1.3.1 | Column casings: details, including number of columns (nr), column size and type of formwork finish, to be stated. |  | 0 | A2.1.3.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.3 Concrete casings to steel frames | 2.1.3.1 Column casings: details, including number of columns (nr), column size and type of formwork finish, to be stated.
2.1.3.2 | Beam casings: details, including number of beams (nr), beam size and type of formwork finish, to be stated. |  | 0 | A2.1.3.2 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.3 Concrete casings to steel frames | 2.1.3.2 Beam casings: details, including number of beams (nr), beam size and type of formwork finish, to be stated.
2.1.4 | Concrete frames |  | 0 | A2.1.4 | 2 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.4 Concrete frames
2.1.4.1 | Columns: details, including number (nr) of columns, column size (mm), concrete grade, reinforcement rate (kg/m3) and type of formwork finish, to be stated. |  | 0 | A2.1.4.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.4 Concrete frames | 2.1.4.1 Columns: details, including number (nr) of columns, column size (mm), concrete grade, reinforcement rate (kg/m3) and type of formwork finish, to be stated.
2.1.4.2 | Beams: details, including number (nr) of beams, beam size (mm), reinforcement rate (kg/m3) and type of formwork finish, to be stated. |  | 0 | A2.1.4.2 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.4 Concrete frames | 2.1.4.2 Beams: details, including number (nr) of beams, beam size (mm), reinforcement rate (kg/m3) and type of formwork finish, to be stated.
2.1.4.3 | Walls: details, including thickness of wall (mm), concrete grade, reinforcement rate (kg/m3) and type of formwork finish, to be stated. |  | 0 | A2.1.4.3 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.4 Concrete frames | 2.1.4.3 Walls: details, including thickness of wall (mm), concrete grade, reinforcement rate (kg/m3) and type of formwork finish, to be stated.
2.1.4.4 | Extra over walls for forming openings in walls for doors, windows, screens and the like: details, including thickness of wall (mm), overall size of opening (m) and type of formwork finish, to be stated. |  | 0 | A2.1.4.4 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.4 Concrete frames | 2.1.4.4 Extra over walls for forming openings in walls for doors, windows, screens and the like: details, including thickness of wall (mm), overall size of opening (m) and type of formwork finish, to be stated.
2.1.4.5 | Designed joints: details to be stated. |  | 0 | A2.1.4.5 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.4 Concrete frames | 2.1.4.5 Designed joints: details to be stated.
2.1.5 | Timber frames |  | 0 | A2.1.5 | 2 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.5 Timber frames
2.1.5.1 | Timber frames: details to be stated. | 19125 | 18657 | A2.1.5.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.5 Timber frames | 2.1.5.1 Timber frames: details to be stated.
2.1.5.1 | Timber frames: details to be stated. | 21375 | 19449 | A2.1.5.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.5 Timber frames | 2.1.5.1 Timber frames: details to be stated.
2.1.5.1 | Timber frames: details to be stated. | 14625 | 13497 | A2.1.5.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.5 Timber frames | 2.1.5.1 Timber frames: details to be stated.
2.1.5.1 | Timber frames: details to be stated. | 27000 | 26402 | A2.1.5.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.5 Timber frames | 2.1.5.1 Timber frames: details to be stated.
2.1.5.1 | Timber frames: details to be stated. | 14625 | 14844 | A2.1.5.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.5 Timber frames | 2.1.5.1 Timber frames: details to be stated.
2.1.6 | Specialist frames |  | 0 | A2.1.6 | 2 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.6 Specialist frames
2.1.6.1 | Specialist frame: details to be stated. |  | 0 | A2.1.6.1 | 3 | 2 SUPERSTRUCTURE | 2.1 Frame | 2.1.6 Specialist frames | 2.1.6.1 Specialist frame: details to be stated.
2.2 | Upper floors |  | 0 | A2.2 | 1 | 2 SUPERSTRUCTURE | 2.2 Upper floors
2.2.1 | Floors |  | 0 | A2.2.1 | 2 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Floors
2.2.1 | Concrete floors: |  | 0 | A2.2.1 | 2 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Concrete floors:
2.2.1.1 | Suspended floor slabs: details, including thickness (mm); concrete strength (N/mm2), reinforcement rate (kg/m3) and type of formwork finish, to be stated. |  | 0 | A2.2.1.1 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Concrete floors: | 2.2.1.1 Suspended floor slabs: details, including thickness (mm); concrete strength (N/mm2), reinforcement rate (kg/m3) and type of formwork finish, to be stated.
2.2.1.2 | Edge formwork: details of formwork finish to be stated. |  | 0 | A2.2.1.2 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Concrete floors: | 2.2.1.2 Edge formwork: details of formwork finish to be stated.
2.2.1.3 | Designed joints: details to be stated. |  | 0 | A2.2.1.3 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Concrete floors: | 2.2.1.3 Designed joints: details to be stated.
2.2.1.4 | Surface treatments: details to be stated. |  | 0 | A2.2.1.4 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Concrete floors: | 2.2.1.4 Surface treatments: details to be stated.
2.2.1 | Precast/composite decking systems: |  | 0 | A2.2.1 | 2 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Precast/composite decking systems:
2.2.1.5 | Suspended floor slab: details, including type, thickness (mm), span (m) and loading (kN/m2), to be stated. |  | 0 | A2.2.1.5 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Precast/composite decking systems: | 2.2.1.5 Suspended floor slab: details, including type, thickness (mm), span (m) and loading (kN/m2), to be stated.
2.2.1 | Timber floors: |  | 0 | A2.2.1 | 2 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Timber floors:
2.2.1.6 | Timber floors: details to be stated. |  | 0 | A2.2.1.6 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Timber floors: | 2.2.1.6 Timber floors: details to be stated.
2.2.1 | Structural screeds: |  | 0 | A2.2.1 | 2 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Structural screeds:
2.2.1.7 | Structural screeds: details, including thickness (mm), reinforcement rate (kg/m3) and surface treatments, to be stated. |  | 0 | A2.2.1.7 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.1 Structural screeds: | 2.2.1.7 Structural screeds: details, including thickness (mm), reinforcement rate (kg/m3) and surface treatments, to be stated.
2.2.2 | Balconies |  | 0 | A2.2.2 | 2 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.2 Balconies
2.2.2.1 | Balconies: details, including floor area (m2) of balcony, to be stated. |  | 0 | A2.2.2.1 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.2 Balconies | 2.2.2.1 Balconies: details, including floor area (m2) of balcony, to be stated.
2.2.3 | Drainage to balconies |  | 0 | A2.2.3 | 2 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.3 Drainage to balconies
2.2.3.1 | Rainwater pipes: details to be stated. |  | 0 | A2.2.3.1 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.3 Drainage to balconies | 2.2.3.1 Rainwater pipes: details to be stated.
2.2.3.2 | Floor outlets: details to be stated. |  | 0 | A2.2.3.2 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.3 Drainage to balconies | 2.2.3.2 Floor outlets: details to be stated.
2.2.3.3 | Testing of installations. |  | 0 | A2.2.3.3 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.3 Drainage to balconies | 2.2.3.3 Testing of installations.
2.2.3.4 | Commissioning of installations. |  | 0 | A2.2.3.4 | 3 | 2 SUPERSTRUCTURE | 2.2 Upper floors | 2.2.3 Drainage to balconies | 2.2.3.4 Commissioning of installations.
2.3 | Roof |  | 0 | A2.3 | 1 | 2 SUPERSTRUCTURE | 2.3 Roof
2.3.1 | Roof structure |  | 0 | A2.3.1 | 2 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.1 Roof structure
2.3.1.1 | Roof structure - pitched roofs: details, including design loads (kN/m2), spans (m) and angle of pitch (degrees), to be stated. |  | 0 | A2.3.1.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.1 Roof structure | 2.3.1.1 Roof structure - pitched roofs: details, including design loads (kN/m2), spans (m) and angle of pitch (degrees), to be stated.
2.3.1.2 | Extra over roof structure - pitched roofs for forming dormer. |  | 0 | A2.3.1.2 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.1 Roof structure | 2.3.1.2 Extra over roof structure - pitched roofs for forming dormer.
2.3.1.3 | Prefabricated dormers: details to be stated. |  | 0 | A2.3.1.3 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.1 Roof structure | 2.3.1.3 Prefabricated dormers: details to be stated.
2.3.1.4 | Roof structure - flat roofs: details, including design loads (kN/m2) and spans (m), to be stated. |  | 0 | A2.3.1.4 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.1 Roof structure | 2.3.1.4 Roof structure - flat roofs: details, including design loads (kN/m2) and spans (m), to be stated.
2.3.2 | Roof coverings |  | 0 | A2.3.2 | 2 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings
2.3.2.1 | Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated. | 20000 | 18374 | A2.3.2.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.1 Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated.
2.3.2.1 | Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated. | 20000 | 19738 | A2.3.2.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.1 Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated.
2.3.2.1 | Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated. | 16000 | 14798 | A2.3.2.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.1 Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated.
2.3.2.1 | Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated. | 25000 | 26014 | A2.3.2.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.1 Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated.
2.3.2.1 | Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated. | 16000 | 16574 | A2.3.2.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.1 Roof coverings, non-structural screeds, thermal insulation, and surface treatments: details to be stated.
2.3.2.2 | Extra over roof coverings for coverings to dormers, including cladding to dormer cheeks. |  | 0 | A2.3.2.2 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.2 Extra over roof coverings for coverings to dormers, including cladding to dormer cheeks.
2.3.2.3 | Eaves, verge treatment to pitched roofs: details to be stated. |  | 0 | A2.3.2.3 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.3 Eaves, verge treatment to pitched roofs: details to be stated.
2.3.2.4 | Edge treatment to flat roofs: details stated. |  | 0 | A2.3.2.4 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.4 Edge treatment to flat roofs: details stated.
2.3.2.5 | Flashings: details to be stated. |  | 0 | A2.3.2.5 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.2 Roof coverings | 2.3.2.5 Flashings: details to be stated.
2.3.3 | Specialist roof systems |  | 0 | A2.3.3 | 2 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.3 Specialist roof systems
2.3.3.1 | Specialist roof systems: details to be stated. |  | 0 | A2.3.3.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.3 Specialist roof systems | 2.3.3.1 Specialist roof systems: details to be stated.
2.3.4 | Roof drainage |  | 0 | A2.3.4 | 2 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage
2.3.4.1 | Gutters: details to be stated. | 4000 | 3865 | A2.3.4.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.1 Gutters: details to be stated.
2.3.4.1 | Gutters: details to be stated. | 8000 | 8675 | A2.3.4.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.1 Gutters: details to be stated.
2.3.4.1 | Gutters: details to be stated. | 6400 | 6595 | A2.3.4.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.1 Gutters: details to be stated.
2.3.4.1 | Gutters: details to be stated. | 16000 | 15078 | A2.3.4.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.1 Gutters: details to be stated.
2.3.4.1 | Gutters: details to be stated. | 6400 | 5885 | A2.3.4.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.1 Gutters: details to be stated.
2.3.4.2 | Rainwater pipes: details to be stated. | 2500 | 2428 | A2.3.4.2 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.2 Rainwater pipes: details to be stated.
2.3.4.2 | Rainwater pipes: details to be stated. | 5000 | 4941 | A2.3.4.2 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.2 Rainwater pipes: details to be stated.
2.3.4.2 | Rainwater pipes: details to be stated. | 4000 | 3822 | A2.3.4.2 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.2 Rainwater pipes: details to be stated.
2.3.4.2 | Rainwater pipes: details to be stated. | 10000 | 10033 | A2.3.4.2 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.2 Rainwater pipes: details to be stated.
2.3.4.2 | Rainwater pipes: details to be stated. | 4000 | 4234 | A2.3.4.2 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.2 Rainwater pipes: details to be stated.
2.3.4.3 | Testing of installations. |  | 0 | A2.3.4.3 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.3 Testing of installations.
2.3.4.4 | Commissioning of installations. |  | 0 | A2.3.4.4 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.4 Roof drainage | 2.3.4.4 Commissioning of installations.
2.3.5 | Rooflights, skylights and openings |  | 0 | A2.3.5 | 2 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.5 Rooflights, skylights and openings
2.3.5.1 | Rooflights, skylights and openings: type and size to be stated. |  | 0 | A2.3.5.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.5 Rooflights, skylights and openings | 2.3.5.1 Rooflights, skylights and openings: type and size to be stated.
2.3.6 | Roof features |  | 0 | A2.3.6 | 2 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.6 Roof features
2.3.6.1 | Roof features: details to be stated. |  | 0 | A2.3.6.1 | 3 | 2 SUPERSTRUCTURE | 2.3 Roof | 2.3.6 Roof features | 2.3.6.1 Roof features: details to be stated.
2.4 | Stairs and ramps |  | 0 | A2.4 | 1 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps
2.4.1 | Stair/ramp structures |  | 0 | A2.4.1 | 2 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures
2.4.1.1 | Stair structures: details, including vertical rise of staircase, to be stated. | 1000 | 947 | A2.4.1.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.1 Stair structures: details, including vertical rise of staircase, to be stated.
2.4.1.1 | Stair structures: details, including vertical rise of staircase, to be stated. | 1000 | 902 | A2.4.1.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.1 Stair structures: details, including vertical rise of staircase, to be stated.
2.4.1.1 | Stair structures: details, including vertical rise of staircase, to be stated. | 1000 | 901 | A2.4.1.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.1 Stair structures: details, including vertical rise of staircase, to be stated.
2.4.1.1 | Stair structures: details, including vertical rise of staircase, to be stated. | 0 | 0 | A2.4.1.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.1 Stair structures: details, including vertical rise of staircase, to be stated.
2.4.1.1 | Stair structures: details, including vertical rise of staircase, to be stated. | 0 | 0 | A2.4.1.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.1 Stair structures: details, including vertical rise of staircase, to be stated.
2.4.1.2 | Ramp structures: details, including vertical rise of ramp, to be stated. | 0 | 0 | A2.4.1.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.2 Ramp structures: details, including vertical rise of ramp, to be stated.
2.4.1.2 | Ramp structures: details, including vertical rise of ramp, to be stated. | 0 | 0 | A2.4.1.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.2 Ramp structures: details, including vertical rise of ramp, to be stated.
2.4.1.2 | Ramp structures: details, including vertical rise of ramp, to be stated. | 0 | 0 | A2.4.1.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.2 Ramp structures: details, including vertical rise of ramp, to be stated.
2.4.1.2 | Ramp structures: details, including vertical rise of ramp, to be stated. | 1000 | 1013 | A2.4.1.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.2 Ramp structures: details, including vertical rise of ramp, to be stated.
2.4.1.2 | Ramp structures: details, including vertical rise of ramp, to be stated. | 1000 | 930 | A2.4.1.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.1 Stair/ramp structures | 2.4.1.2 Ramp structures: details, including vertical rise of ramp, to be stated.
2.4.2 | Stair/ramp finishes |  | 0 | A2.4.2 | 2 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes
2.4.2.1 | Stair finishes: details, including vertical rise of staircase, to be stated. | 800 | 786 | A2.4.2.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.1 Stair finishes: details, including vertical rise of staircase, to be stated.
2.4.2.1 | Stair finishes: details, including vertical rise of staircase, to be stated. | 800 | 875 | A2.4.2.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.1 Stair finishes: details, including vertical rise of staircase, to be stated.
2.4.2.1 | Stair finishes: details, including vertical rise of staircase, to be stated. | 800 | 778 | A2.4.2.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.1 Stair finishes: details, including vertical rise of staircase, to be stated.
2.4.2.1 | Stair finishes: details, including vertical rise of staircase, to be stated. | 0 | 0 | A2.4.2.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.1 Stair finishes: details, including vertical rise of staircase, to be stated.
2.4.2.1 | Stair finishes: details, including vertical rise of staircase, to be stated. | 0 | 0 | A2.4.2.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.1 Stair finishes: details, including vertical rise of staircase, to be stated.
2.4.2.2 | Ramp finishes: details, including vertical rise of ramp, to be stated. | 0 | 0 | A2.4.2.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.2 Ramp finishes: details, including vertical rise of ramp, to be stated.
2.4.2.2 | Ramp finishes: details, including vertical rise of ramp, to be stated. | 0 | 0 | A2.4.2.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.2 Ramp finishes: details, including vertical rise of ramp, to be stated.
2.4.2.2 | Ramp finishes: details, including vertical rise of ramp, to be stated. | 0 | 0 | A2.4.2.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.2 Ramp finishes: details, including vertical rise of ramp, to be stated.
2.4.2.2 | Ramp finishes: details, including vertical rise of ramp, to be stated. | 700 | 741 | A2.4.2.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.2 Ramp finishes: details, including vertical rise of ramp, to be stated.
2.4.2.2 | Ramp finishes: details, including vertical rise of ramp, to be stated. | 700 | 741 | A2.4.2.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.2 Stair/ramp finishes | 2.4.2.2 Ramp finishes: details, including vertical rise of ramp, to be stated.
2.4.3 | Stair/ramp balustrades and handrails |  | 0 | A2.4.3 | 2 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.3 Stair/ramp balustrades and handrails
2.4.3.1 | Wall handrails: details, including vertical rise of staircase or ramp, to be stated. |  | 0 | A2.4.3.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.3 Stair/ramp balustrades and handrails | 2.4.3.1 Wall handrails: details, including vertical rise of staircase or ramp, to be stated.
2.4.3.2 | Combined balustrades and handrails: details, including vertical rise of staircase or ramp, to be stated. |  | 0 | A2.4.3.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.3 Stair/ramp balustrades and handrails | 2.4.3.2 Combined balustrades and handrails: details, including vertical rise of staircase or ramp, to be stated.
2.4.4 | Ladders/chutes/slides |  | 0 | A2.4.4 | 2 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.4 Ladders/chutes/slides
2.4.4.1 | Ladders: details to be stated. |  | 0 | A2.4.4.1 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.4 Ladders/chutes/slides | 2.4.4.1 Ladders: details to be stated.
2.4.4.2 | Chutes: details to be stated. |  | 0 | A2.4.4.2 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.4 Ladders/chutes/slides | 2.4.4.2 Chutes: details to be stated.
2.4.4.3 | Slides: details to be stated. |  | 0 | A2.4.4.3 | 3 | 2 SUPERSTRUCTURE | 2.4 Stairs and ramps | 2.4.4 Ladders/chutes/slides | 2.4.4.3 Slides: details to be stated.
2.5 | External walls |  | 0 | A2.5 | 1 | 2 SUPERSTRUCTURE | 2.5 External walls
2.5.1 | External enclosing walls above ground level |  | 0 | A2.5.1 | 2 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level
2.5.1.1 | External walls: details to be stated. | 20000 | 19192 | A2.5.1.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.1 External walls: details to be stated.
2.5.1.1 | External walls: details to be stated. | 20000 | 18972 | A2.5.1.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.1 External walls: details to be stated.
2.5.1.1 | External walls: details to be stated. | 16000 | 14456 | A2.5.1.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.1 External walls: details to be stated.
2.5.1.1 | External walls: details to be stated. | 25000 | 22588 | A2.5.1.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.1 External walls: details to be stated.
2.5.1.1 | External walls: details to be stated. | 16000 | 15535 | A2.5.1.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.1 External walls: details to be stated.
2.5.1.2 | Extra over external walls for plinths, cornices, ornamental bands and the like: details to be stated. |  | 0 | A2.5.1.2 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.2 Extra over external walls for plinths, cornices, ornamental bands and the like: details to be stated.
2.5.1.3 | Extra over external walls for quoins: details to be stated. |  | 0 | A2.5.1.3 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.3 Extra over external walls for quoins: details to be stated.
2.5.1.4 | Extra over external walls for forming openings for windows: details, including overall size of opening (mm), to be stated. |  | 0 | A2.5.1.4 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.4 Extra over external walls for forming openings for windows: details, including overall size of opening (mm), to be stated.
2.5.1.5 | Extra over external walls for forming openings for external doors: details, including overall size of opening (mm), to be stated. |  | 0 | A2.5.1.5 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.5 Extra over external walls for forming openings for external doors: details, including overall size of opening (mm), to be stated.
2.5.1.6 | Extra over cladding or curtain walling system for integral photovoltaic panels: details, including overall size of opening (mm), to be stated. |  | 0 | A2.5.1.6 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.6 Extra over cladding or curtain walling system for integral photovoltaic panels: details, including overall size of opening (mm), to be stated.
2.5.1.7 | Extra over cladding or curtain walling system for integral opening vents and panels: details, including purpose of opening and overall size of opening (mm), to be stated. |  | 0 | A2.5.1.7 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.7 Extra over cladding or curtain walling system for integral opening vents and panels: details, including purpose of opening and overall size of opening (mm), to be stated.
2.5.1.8 | Projecting fins to cladding or curtain walling system: details, including overall size of panel (mm), to be stated. |  | 0 | A2.5.1.8 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.8 Projecting fins to cladding or curtain walling system: details, including overall size of panel (mm), to be stated.
2.5.1.9 | Extra over projecting fins for applied artwork: details to be stated. |  | 0 | A2.5.1.9 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.9 Extra over projecting fins for applied artwork: details to be stated.
2.5.1.10 | Safety barriers, handrails or combined balusters and handrails to facetted glazing or cladding systems: details to be stated. |  | 0 | A2.5.1.10 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.10 Safety barriers, handrails or combined balusters and handrails to facetted glazing or cladding systems: details to be stated.
2.5.1.11 | Finishes applied to external walls: details to be stated. |  | 0 | A2.5.1.11 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.1 External enclosing walls above ground level | 2.5.1.11 Finishes applied to external walls: details to be stated.
2.5.2 | External enclosing walls below ground level |  | 0 | A2.5.2 | 2 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.2 External enclosing walls below ground level
2.5.2.1 | External walls: details to be stated. |  | 0 | A2.5.2.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.2 External enclosing walls below ground level | 2.5.2.1 External walls: details to be stated.
2.5.2.2 | Extra over external walls for plinths, cornices, ornamental bands and the like: details to be stated. |  | 0 | A2.5.2.2 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.2 External enclosing walls below ground level | 2.5.2.2 Extra over external walls for plinths, cornices, ornamental bands and the like: details to be stated.
2.5.2.3 | Extra over external walls for quoins: details to be stated. |  | 0 | A2.5.2.3 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.2 External enclosing walls below ground level | 2.5.2.3 Extra over external walls for quoins: details to be stated.
2.5.2.4 | Extra over external walls for forming openings for windows: details, including overall size of opening (mm), to be stated. |  | 0 | A2.5.2.4 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.2 External enclosing walls below ground level | 2.5.2.4 Extra over external walls for forming openings for windows: details, including overall size of opening (mm), to be stated.
2.5.2.5 | Extra over external walls for forming openings for external doors: details, including overall size of opening (mm), to be stated. |  | 0 | A2.5.2.5 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.2 External enclosing walls below ground level | 2.5.2.5 Extra over external walls for forming openings for external doors: details, including overall size of opening (mm), to be stated.
2.5.2.6 | Finishes to external walls: details to be stated. |  | 0 | A2.5.2.6 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.2 External enclosing walls below ground level | 2.5.2.6 Finishes to external walls: details to be stated.
2.5.3 | Solar/rain screening |  | 0 | A2.5.3 | 2 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.3 Solar/rain screening
2.5.3.1 | Vertical solar/rain screening: details, including projection (mm), to be stated. |  | 0 | A2.5.3.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.3 Solar/rain screening | 2.5.3.1 Vertical solar/rain screening: details, including projection (mm), to be stated.
2.5.3.2 | Horizontal solar/rain screening: details to be stated. |  | 0 | A2.5.3.2 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.3 Solar/rain screening | 2.5.3.2 Horizontal solar/rain screening: details to be stated.
2.5.4 | External soffits |  | 0 | A2.5.4 | 2 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits
2.5.4.1 | External soffit: details to be stated. | 18000 | 18076 | A2.5.4.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.1 External soffit: details to be stated.
2.5.4.1 | External soffit: details to be stated. | 18000 | 17962 | A2.5.4.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.1 External soffit: details to be stated.
2.5.4.1 | External soffit: details to be stated. | 14400 | 14507 | A2.5.4.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.1 External soffit: details to be stated.
2.5.4.1 | External soffit: details to be stated. | 22500 | 23186 | A2.5.4.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.1 External soffit: details to be stated.
2.5.4.1 | External soffit: details to be stated. | 14400 | 14482 | A2.5.4.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.1 External soffit: details to be stated.
2.5.4.2 | Cornices, covings and the like: details to be stated. |  | 0 | A2.5.4.2 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.2 Cornices, covings and the like: details to be stated.
2.5.4.3 | Shadow gaps and the like: details to be stated. |  | 0 | A2.5.4.3 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.3 Shadow gaps and the like: details to be stated.
2.5.4.4 | JHLess hatches and the like: details to be stated. |  | 0 | A2.5.4.4 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.4 JHLess hatches and the like: details to be stated.
2.5.4.5 | Finishes applied to external soffits: details to be stated. |  | 0 | A2.5.4.5 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.4 External soffits | 2.5.4.5 Finishes applied to external soffits: details to be stated.
2.5.5 | Subsidiary walls, balustrades and proprietary balconies |  | 0 | A2.5.5 | 2 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies
2.5.5.1 | Walls: details to be stated. |  | 0 | A2.5.5.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.1 Walls: details to be stated.
2.5.5.2 | Walls forming planters: details to be stated. |  | 0 | A2.5.5.2 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.2 Walls forming planters: details to be stated.
2.5.5.3 | Combined balustrades and handrails: details to be stated. |  | 0 | A2.5.5.3 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.3 Combined balustrades and handrails: details to be stated.
2.5.5.4 | Wall mounted handrails: details to be stated. |  | 0 | A2.5.5.4 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.4 Wall mounted handrails: details to be stated.
2.5.5.5 | Parapet railings: details to be stated. |  | 0 | A2.5.5.5 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.5 Parapet railings: details to be stated.
2.5.5.6 | Proprietary bolt-on balconies: details to be stated. |  | 0 | A2.5.5.6 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.6 Proprietary bolt-on balconies: details to be stated.
2.5.5.7 | Rainwater pipes: details to be stated. |  | 0 | A2.5.5.7 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.7 Rainwater pipes: details to be stated.
2.5.5.8 | Floor outlets: details to be stated. |  | 0 | A2.5.5.8 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.8 Floor outlets: details to be stated.
2.5.5.9 | Testing of rainwater drainage installation. |  | 0 | A2.5.5.9 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.9 Testing of rainwater drainage installation.
2.5.5.10 | Commissioning of rainwater drainage installation. |  | 0 | A2.5.5.10 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.5 Subsidiary walls, balustrades and proprietary balconies | 2.5.5.10 Commissioning of rainwater drainage installation.
2.5.6 | Facade JHLess/cleaning systems |  | 0 | A2.5.6 | 2 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.6 Facade JHLess/cleaning systems
2.5.6.1 | Facade cleaning systems: details to be stated. |  | 0 | A2.5.6.1 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.6 Facade JHLess/cleaning systems | 2.5.6.1 Facade cleaning systems: details to be stated.
2.5.6.2 | Testing of installations. |  | 0 | A2.5.6.2 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.6 Facade JHLess/cleaning systems | 2.5.6.2 Testing of installations.
2.5.6.3 | Commissioning of installations. |  | 0 | A2.5.6.3 | 3 | 2 SUPERSTRUCTURE | 2.5 External walls | 2.5.6 Facade JHLess/cleaning systems | 2.5.6.3 Commissioning of installations.
2.6 | Windows and external doors |  | 0 | A2.6 | 1 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors
2.6.1 | External windows |  | 0 | A2.6.1 | 2 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows
2.6.1.1 | Windows: details, including overall size of opening (mm), to be stated. | 30000 | 29500 | A2.6.1.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.1 Windows: details, including overall size of opening (mm), to be stated.
2.6.1.1 | Windows: details, including overall size of opening (mm), to be stated. | 30000 | 31558 | A2.6.1.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.1 Windows: details, including overall size of opening (mm), to be stated.
2.6.1.1 | Windows: details, including overall size of opening (mm), to be stated. | 24000 | 25797 | A2.6.1.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.1 Windows: details, including overall size of opening (mm), to be stated.
2.6.1.1 | Windows: details, including overall size of opening (mm), to be stated. | 33000 | 30432 | A2.6.1.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.1 Windows: details, including overall size of opening (mm), to be stated.
2.6.1.1 | Windows: details, including overall size of opening (mm), to be stated. | 24000 | 25096 | A2.6.1.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.1 Windows: details, including overall size of opening (mm), to be stated.
2.6.1.2 | Louvers: details, including overall size of opening (mm), to be stated. |  | 0 | A2.6.1.2 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.2 Louvers: details, including overall size of opening (mm), to be stated.
2.6.1.3 | Shop fronts: details, including overall size of opening (mm), to be stated. |  | 0 | A2.6.1.3 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.3 Shop fronts: details, including overall size of opening (mm), to be stated.
2.6.1.4 | Roller shutters, sliding shutters, grilles and the like to window openings: details, including overall size of opening (mm), to be stated. |  | 0 | A2.6.1.4 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.1 External windows | 2.6.1.4 Roller shutters, sliding shutters, grilles and the like to window openings: details, including overall size of opening (mm), to be stated.
2.6.2 | External doors |  | 0 | A2.6.2 | 2 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors
2.6.2.1 | External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated. | 1100 | 1047 | A2.6.2.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.1 External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated.
2.6.2.1 | External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated. | 1100 | 1205 | A2.6.2.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.1 External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated.
2.6.2.1 | External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated. | 1100 | 1084 | A2.6.2.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.1 External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated.
2.6.2.1 | External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated. | 1100 | 1203 | A2.6.2.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.1 External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated.
2.6.2.1 | External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated. | 1100 | 1026 | A2.6.2.1 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.1 External doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated.
2.6.2.2 | Revolving doors: details, including overall size of opening (mm), to be stated. |  | 0 | A2.6.2.2 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.2 Revolving doors: details, including overall size of opening (mm), to be stated.
2.6.2.3 | Shop front doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated. |  | 0 | A2.6.2.3 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.3 Shop front doors: details, including type, number of door leaves (nr), size of each door leaf (mm) and overall size of opening (mm), to be stated.
2.6.2.4 | Roller shutters, sliding shutters and the like to external door openings: details, including overall size of opening (mm), to be stated. |  | 0 | A2.6.2.4 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.4 Roller shutters, sliding shutters and the like to external door openings: details, including overall size of opening (mm), to be stated.
2.6.2.5 | Garage doors: details, including overall size of opening (mm), to be stated. |  | 0 | A2.6.2.5 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.5 Garage doors: details, including overall size of opening (mm), to be stated.
2.6.2.6 | Canopies: details to be stated. |  | 0 | A2.6.2.6 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.6 Canopies: details to be stated.
2.6.2.7 | Grilles: details, including overall size of opening (mm), to be stated. |  | 0 | A2.6.2.7 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.7 Grilles: details, including overall size of opening (mm), to be stated.
2.6.2.8 | Architraves: details to be stated. |  | 0 | A2.6.2.8 | 3 | 2 SUPERSTRUCTURE | 2.6 Windows and external doors | 2.6.2 External doors | 2.6.2.8 Architraves: details to be stated.
2.7 | Internal walls and partitions |  | 0 | A2.7 | 1 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions
2.7.3 | Walls and partitions |  | 0 | A2.7.3 | 2 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions
2.7.3.1 | Internal walls: details, including thickness, to be stated. | 10000 | 10175 | A2.7.3.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.1 Internal walls: details, including thickness, to be stated.
2.7.3.1 | Internal walls: details, including thickness, to be stated. | 10000 | 9674 | A2.7.3.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.1 Internal walls: details, including thickness, to be stated.
2.7.3.1 | Internal walls: details, including thickness, to be stated. | 8000 | 7866 | A2.7.3.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.1 Internal walls: details, including thickness, to be stated.
2.7.3.1 | Internal walls: details, including thickness, to be stated. | 12000 | 11803 | A2.7.3.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.1 Internal walls: details, including thickness, to be stated.
2.7.3.1 | Internal walls: details, including thickness, to be stated. | 8000 | 7723 | A2.7.3.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.1 Internal walls: details, including thickness, to be stated.
2.7.3.2 | Extra over internal walls for forming openings in walls for internal doors and the like: details, including overall size of opening (mm), to be stated. |  | 0 | A2.7.3.2 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.2 Extra over internal walls for forming openings in walls for internal doors and the like: details, including overall size of opening (mm), to be stated.
2.7.3.3 | Fixed partitions: details, including thickness, to be stated. |  | 0 | A2.7.3.3 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.3 Fixed partitions: details, including thickness, to be stated.
2.7.3.4 | Extra over fixed partitions for forming openings in partitions for internal doors and the like: details, including overall size of opening (mm), to be stated. |  | 0 | A2.7.3.4 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.3 Walls and partitions | 2.7.3.4 Extra over fixed partitions for forming openings in partitions for internal doors and the like: details, including overall size of opening (mm), to be stated.
2.7.4 | Balustrades and handrails |  | 0 | A2.7.4 | 2 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.4 Balustrades and handrails
2.7.4.1 | Combined balustrades and handrails: details to be stated. |  | 0 | A2.7.4.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.4 Balustrades and handrails | 2.7.4.1 Combined balustrades and handrails: details to be stated.
2.7.5 | Moveable room dividers |  | 0 | A2.7.5 | 2 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.5 Moveable room dividers
2.7.5.1 | Moveable room dividers and partitions: details, including height (in m), to be stated. |  | 0 | A2.7.5.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.5 Moveable room dividers | 2.7.5.1 Moveable room dividers and partitions: details, including height (in m), to be stated.
2.7.6 | Cubicles |  | 0 | A2.7.6 | 2 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.6 Cubicles
2.7.6.1 | Cubicles: details to be stated. |  | 0 | A2.7.6.1 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.6 Cubicles | 2.7.6.1 Cubicles: details to be stated.
2.7.6.2 | Fixed partitions: details, including thickness, to be stated. |  | 0 | A2.7.6.2 | 3 | 2 SUPERSTRUCTURE | 2.7 Internal walls and partitions | 2.7.6 Cubicles | 2.7.6.2 Fixed partitions: details, including thickness, to be stated.
2.8 | Internal doors |  | 0 | A2.8 | 1 | 2 SUPERSTRUCTURE | 2.8 Internal doors
2.8.1 | Internal doors |  | 0 | A2.8.1 | 2 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors
2.8.1.1 | Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated. | 1600 | 1678 | A2.8.1.1 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.1 Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.1 | Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated. | 1600 | 1627 | A2.8.1.1 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.1 Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.1 | Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated. | 1200 | 1211 | A2.8.1.1 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.1 Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.1 | Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated. | 2000 | 2145 | A2.8.1.1 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.1 Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.1 | Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated. | 1200 | 1175 | A2.8.1.1 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.1 Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.2 | Fire resisting doors: details, including type, number of door leaves (nr), fire rating (hours), size of each door leaf (mm), and overall size of opening (mm), to be stated. |  | 0 | A2.8.1.2 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.2 Fire resisting doors: details, including type, number of door leaves (nr), fire rating (hours), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.3 | Door sets: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated. |  | 0 | A2.8.1.3 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.3 Door sets: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.4 | Composite door and sidelights/over panel units: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated. |  | 0 | A2.8.1.4 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.4 Composite door and sidelights/over panel units: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
2.8.1.5 | Roller shutters, sliding shutters, grilles and the like: details, including overall size of opening (mm), to be stated. |  | 0 | A2.8.1.5 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.5 Roller shutters, sliding shutters, grilles and the like: details, including overall size of opening (mm), to be stated.
2.8.1.6 | Architraves: details to be stated. |  | 0 | A2.8.1.6 | 3 | 2 SUPERSTRUCTURE | 2.8 Internal doors | 2.8.1 Internal doors | 2.8.1.6 Architraves: details to be stated.
3 | INTERNAL FINISHES |  | 0 | A3 | 0 | 3 INTERNAL FINISHES
3.1 | Wall Finishes |  | 0 | A3.1 | 1 | 3 INTERNAL FINISHES | 3.1 Wall Finishes
3.1.1 | Wall Finishes |  | 0 | A3.1.1 | 2 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes
3.1.1.1 | Finishes to walls and columns: details to be stated. | 4500 | 4673 | A3.1.1.1 | 3 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes | 3.1.1.1 Finishes to walls and columns: details to be stated.
3.1.1.1 | Finishes to walls and columns: details to be stated. | 4500 | 4654 | A3.1.1.1 | 3 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes | 3.1.1.1 Finishes to walls and columns: details to be stated.
3.1.1.1 | Finishes to walls and columns: details to be stated. | 3000 | 3283 | A3.1.1.1 | 3 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes | 3.1.1.1 Finishes to walls and columns: details to be stated.
3.1.1.1 | Finishes to walls and columns: details to be stated. | 5400 | 5582 | A3.1.1.1 | 3 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes | 3.1.1.1 Finishes to walls and columns: details to be stated.
3.1.1.1 | Finishes to walls and columns: details to be stated. | 3000 | 3277 | A3.1.1.1 | 3 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes | 3.1.1.1 Finishes to walls and columns: details to be stated.
3.1.1.2 | Picture rails, dado rails and the like: details to be stated. |  | 0 | A3.1.1.2 | 3 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes | 3.1.1.2 Picture rails, dado rails and the like: details to be stated.
3.1.1.3 | Proprietary impact and bumper guards, protection strips, corner protectors and the like: details to be stated. |  | 0 | A3.1.1.3 | 3 | 3 INTERNAL FINISHES | 3.1 Wall Finishes | 3.1.1 Wall Finishes | 3.1.1.3 Proprietary impact and bumper guards, protection strips, corner protectors and the like: details to be stated.
3.2 | Floor Finishes |  | 0 | A3.2 | 1 | 3 INTERNAL FINISHES | 3.2 Floor Finishes
3.2.1 | Finishes to floors |  | 0 | A3.2.1 | 2 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors
3.2.1.1 | Finishes to floors: details to be stated. | 9000 | 9019 | A3.2.1.1 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.1 Finishes to floors: details to be stated.
3.2.1.1 | Finishes to floors: details to be stated. | 18000 | 19489 | A3.2.1.1 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.1 Finishes to floors: details to be stated.
3.2.1.1 | Finishes to floors: details to be stated. | 22500 | 21119 | A3.2.1.1 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.1 Finishes to floors: details to be stated.
3.2.1.1 | Finishes to floors: details to be stated. | 16200 | 14581 | A3.2.1.1 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.1 Finishes to floors: details to be stated.
3.2.1.1 | Finishes to floors: details to be stated. | 22500 | 21967 | A3.2.1.1 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.1 Finishes to floors: details to be stated.
3.2.1.2 | Specialist flooring systems: details to be stated. |  | 0 | A3.2.1.2 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.2 Specialist flooring systems: details to be stated.
3.2.1.3 | Skirtings and the like: details to be stated. |  | 0 | A3.2.1.3 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.3 Skirtings and the like: details to be stated.
3.2.1.4 | Mat wells and mats: details to be stated. |  | 0 | A3.2.1.4 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.4 Mat wells and mats: details to be stated.
3.2.1.5 | Finishes to swimming pool tanks, including tank linings: details to be stated. |  | 0 | A3.2.1.5 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.5 Finishes to swimming pool tanks, including tank linings: details to be stated.
3.2.1.6 | Line markings: details to be stated. |  | 0 | A3.2.1.6 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.6 Line markings: details to be stated.
3.2.1.7 | Numeral and symbols: details to be stated. |  | 0 | A3.2.1.7 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.1 Finishes to floors | 3.2.1.7 Numeral and symbols: details to be stated.
3.2.2 | Raised JHLess floors |  | 0 | A3.2.2 | 2 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.2 Raised JHLess floors
3.2.2.1 | Raised JHLess floor systems: details to be stated. |  | 0 | A3.2.2.1 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.2 Raised JHLess floors | 3.2.2.1 Raised JHLess floor systems: details to be stated.
3.2.2.2 | Skirtings and the like: details to be stated. |  | 0 | A3.2.2.2 | 3 | 3 INTERNAL FINISHES | 3.2 Floor Finishes | 3.2.2 Raised JHLess floors | 3.2.2.2 Skirtings and the like: details to be stated.
3.3 | Ceiling Finishes |  | 0 | A3.3 | 1 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes
3.3.1 | Finishes to ceilings |  | 0 | A3.3.1 | 2 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings
3.3.1.1 | Finishes to ceilings: details to be stated. | 3000 | 3169 | A3.3.1.1 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.1 Finishes to ceilings: details to be stated.
3.3.1.1 | Finishes to ceilings: details to be stated. | 6000 | 6035 | A3.3.1.1 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.1 Finishes to ceilings: details to be stated.
3.3.1.1 | Finishes to ceilings: details to be stated. | 7500 | 7399 | A3.3.1.1 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.1 Finishes to ceilings: details to be stated.
3.3.1.1 | Finishes to ceilings: details to be stated. | 5400 | 5819 | A3.3.1.1 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.1 Finishes to ceilings: details to be stated.
3.3.1.1 | Finishes to ceilings: details to be stated. | 7500 | 7558 | A3.3.1.1 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.1 Finishes to ceilings: details to be stated.
3.3.1.2 | Cornices, covings and the like: details to be stated. | 1000 | 950 | A3.3.1.2 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.2 Cornices, covings and the like: details to be stated.
3.3.1.2 | Cornices, covings and the like: details to be stated. | 1000 | 1052 | A3.3.1.2 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.2 Cornices, covings and the like: details to be stated.
3.3.1.2 | Cornices, covings and the like: details to be stated. | 1200 | 1303 | A3.3.1.2 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.2 Cornices, covings and the like: details to be stated.
3.3.1.2 | Cornices, covings and the like: details to be stated. | 1500 | 1543 | A3.3.1.2 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.2 Cornices, covings and the like: details to be stated.
3.3.1.2 | Cornices, covings and the like: details to be stated. | 1200 | 1246 | A3.3.1.2 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.1 Finishes to ceilings | 3.3.1.2 Cornices, covings and the like: details to be stated.
3.3.2 | False ceilings |  | 0 | A3.3.2 | 2 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.2 False ceilings
3.3.2.1 | False ceilings: details to be stated. |  | 0 | A3.3.2.1 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.2 False ceilings | 3.3.2.1 False ceilings: details to be stated.
3.3.2.2 | Cornices, covings and the like: details to be stated. |  | 0 | A3.3.2.2 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.2 False ceilings | 3.3.2.2 Cornices, covings and the like: details to be stated.
3.3.2.3 | JHLess hatches and the like: details to be stated. |  | 0 | A3.3.2.3 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.2 False ceilings | 3.3.2.3 JHLess hatches and the like: details to be stated.
3.3.3 | Demountable suspended ceilings |  | 0 | A3.3.3 | 2 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.3 Demountable suspended ceilings
3.3.3.1 | Demountable suspended ceilings: details to be stated. |  | 0 | A3.3.3.1 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.3 Demountable suspended ceilings | 3.3.3.1 Demountable suspended ceilings: details to be stated.
3.3.3.2 | Shadow gaps and the like: details to be stated. |  | 0 | A3.3.3.2 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.3 Demountable suspended ceilings | 3.3.3.2 Shadow gaps and the like: details to be stated.
3.3.3.3 | JHLess hatches and the like: details to be stated. |  | 0 | A3.3.3.3 | 3 | 3 INTERNAL FINISHES | 3.3 Ceiling Finishes | 3.3.3 Demountable suspended ceilings | 3.3.3.3 JHLess hatches and the like: details to be stated.
4 | FITTINGS, FURNISHINGS AND EQUIPMENT |  | 0 | A4 | 0 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT
4.1.1 | General fittings, furnishings and equipment |  | 0 | A4.1.1 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment
4.1.1.1 | Fittings: details to be stated. | 2000 | 1922 | A4.1.1.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment | 4.1.1.1 Fittings: details to be stated.
4.1.1.1 | Fittings: details to be stated. | 2000 | 1894 | A4.1.1.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment | 4.1.1.1 Fittings: details to be stated.
4.1.1.1 | Fittings: details to be stated. | 2000 | 2029 | A4.1.1.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment | 4.1.1.1 Fittings: details to be stated.
4.1.1.1 | Fittings: details to be stated. | 2000 | 1828 | A4.1.1.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment | 4.1.1.1 Fittings: details to be stated.
4.1.1.1 | Fittings: details to be stated. | 2000 | 2162 | A4.1.1.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment | 4.1.1.1 Fittings: details to be stated.
4.1.1.2 | Furnishings: details to be stated. |  | 0 | A4.1.1.2 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment | 4.1.1.2 Furnishings: details to be stated.
4.1.1.3 | Equipment: details to be stated. |  | 0 | A4.1.1.3 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.1 General fittings, furnishings and equipment | 4.1.1.3 Equipment: details to be stated.
4.1.2 | Domestic kitchen fittings and equipment |  | 0 | A4.1.2 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment
4.1.2.1 | Kitchen units: details to be stated. | 1500 | 1602 | A4.1.2.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment | 4.1.2.1 Kitchen units: details to be stated.
4.1.2.1 | Kitchen units: details to be stated. | 1500 | 1497 | A4.1.2.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment | 4.1.2.1 Kitchen units: details to be stated.
4.1.2.1 | Kitchen units: details to be stated. | 1500 | 1642 | A4.1.2.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment | 4.1.2.1 Kitchen units: details to be stated.
4.1.2.1 | Kitchen units: details to be stated. | 1500 | 1602 | A4.1.2.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment | 4.1.2.1 Kitchen units: details to be stated.
4.1.2.1 | Kitchen units: details to be stated. | 1500 | 1490 | A4.1.2.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment | 4.1.2.1 Kitchen units: details to be stated.
4.1.2.2 | Kitchen appliances: details to be stated. |  | 0 | A4.1.2.2 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment | 4.1.2.2 Kitchen appliances: details to be stated.
4.1.2.3 | Waste bins, towel rails, storage racks and other JHLessories: details to be stated. |  | 0 | A4.1.2.3 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.2 Domestic kitchen fittings and equipment | 4.1.2.3 Waste bins, towel rails, storage racks and other JHLessories: details to be stated.
4.1.3 | Special purpose fittings, furnishings and equipment |  | 0 | A4.1.3 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.3 Special purpose fittings, furnishings and equipment
4.1.3.1 | Fittings: details to be stated. |  | 0 | A4.1.3.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.3 Special purpose fittings, furnishings and equipment | 4.1.3.1 Fittings: details to be stated.
4.1.3.2 | Furnishings: details to be stated. |  | 0 | A4.1.3.2 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.3 Special purpose fittings, furnishings and equipment | 4.1.3.2 Furnishings: details to be stated.
4.1.3.3 | Equipment: details to be stated. |  | 0 | A4.1.3.3 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.3 Special purpose fittings, furnishings and equipment | 4.1.3.3 Equipment: details to be stated.
4.1.4 | Signs/notices |  | 0 | A4.1.4 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.4 Signs/notices
4.1.4.1 | Component: details to be stated. |  | 0 | A4.1.4.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.4 Signs/notices | 4.1.4.1 Component: details to be stated.
4.1.5 | Works of art |  | 0 | A4.1.5 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.5 Works of art
4.1.5.1 | Objects d'art and other ornamental features: details to be stated. |  | 0 | A4.1.5.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.5 Works of art | 4.1.5.1 Objects d'art and other ornamental features: details to be stated.
4.1.5.2 | Decorative features and panels: details to be stated. |  | 0 | A4.1.5.2 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.5 Works of art | 4.1.5.2 Decorative features and panels: details to be stated.
4.1.6 | Non-mechanical and non-electrical equipment |  | 0 | A4.1.6 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.6 Non-mechanical and non-electrical equipment
4.1.6.1 | Equipment: details to be stated. |  | 0 | A4.1.6.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.6 Non-mechanical and non-electrical equipment | 4.1.6.1 Equipment: details to be stated.
4.1.6.2 | Removable ladders and the like: details to be stated. |  | 0 | A4.1.6.2 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.6 Non-mechanical and non-electrical equipment | 4.1.6.2 Removable ladders and the like: details to be stated.
4.1.7 | Internal planting |  | 0 | A4.1.7 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.7 Internal planting
4.1.7.1 | Plant and shrub beds: details to be stated. |  | 0 | A4.1.7.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.7 Internal planting | 4.1.7.1 Plant and shrub beds: details to be stated.
4.1.7.2 | Plant containers: details to be stated. |  | 0 | A4.1.7.2 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.7 Internal planting | 4.1.7.2 Plant containers: details to be stated.
4.1.7.3 | Trees: details to be stated. |  | 0 | A4.1.7.3 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.7 Internal planting | 4.1.7.3 Trees: details to be stated.
4.1.7.4 | Tree planters: details to be stated. |  | 0 | A4.1.7.4 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.7 Internal planting | 4.1.7.4 Tree planters: details to be stated.
4.1.8 | Bird and vermin control |  | 0 | A4.1.8 | 2 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.8 Bird and vermin control
4.1.8.1 | Wires, nets, traps and the like: details to be stated. |  | 0 | A4.1.8.1 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.8 Bird and vermin control | 4.1.8.1 Wires, nets, traps and the like: details to be stated.
4.1.8.2 | Electronic and sonic system: details to be stated. |  | 0 | A4.1.8.2 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.8 Bird and vermin control | 4.1.8.2 Electronic and sonic system: details to be stated.
4.1.8.3 | Bird repellent coatings: details to be stated. |  | 0 | A4.1.8.3 | 3 | 4 FITTINGS, FURNISHINGS AND EQUIPMENT |  | 4.1.8 Bird and vermin control | 4.1.8.3 Bird repellent coatings: details to be stated.
5 | SERVICES |  | 0 | A5 | 0 | 5 SERVICES
5.1 | Sanitary installations |  | 0 | A5.1 | 1 | 5 SERVICES | 5.1 Sanitary installations
5.1.1 | Sanitary appliances |  | 0 | A5.1.1 | 2 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances
5.1.1.1 | Sanitary appliance: details to be stated. | 500 | 474 | A5.1.1.1 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances | 5.1.1.1 Sanitary appliance: details to be stated.
5.1.1.1 | Sanitary appliance: details to be stated. | 500 | 484 | A5.1.1.1 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances | 5.1.1.1 Sanitary appliance: details to be stated.
5.1.1.1 | Sanitary appliance: details to be stated. | 500 | 483 | A5.1.1.1 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances | 5.1.1.1 Sanitary appliance: details to be stated.
5.1.1.1 | Sanitary appliance: details to be stated. | 500 | 457 | A5.1.1.1 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances | 5.1.1.1 Sanitary appliance: details to be stated.
5.1.1.1 | Sanitary appliance: details to be stated. | 500 | 450 | A5.1.1.1 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances | 5.1.1.1 Sanitary appliance: details to be stated.
5.1.1.2 | Testing of installations. |  | 0 | A5.1.1.2 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances | 5.1.1.2 Testing of installations.
5.1.1.3 | Commissioning of installations. |  | 0 | A5.1.1.3 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.1 Sanitary appliances | 5.1.1.3 Commissioning of installations.
5.1.2 | Sanitary ancillaries |  | 0 | A5.1.2 | 2 | 5 SERVICES | 5.1 Sanitary installations | 5.1.2 Sanitary ancillaries
5.1.2.1 | Fittings: details to be stated. |  | 0 | A5.1.2.1 | 3 | 5 SERVICES | 5.1 Sanitary installations | 5.1.2 Sanitary ancillaries | 5.1.2.1 Fittings: details to be stated.
5.2 | Services equipment |  | 0 | A5.2 | 1 | 5 SERVICES | 5.2 Services equipment
5.2.1 | Services equipment |  | 0 | A5.2.1 | 2 | 5 SERVICES | 5.2 Services equipment | 5.2.1 Services equipment
5.2.1.1 | Services equipment: details to be stated. |  | 0 | A5.2.1.1 | 3 | 5 SERVICES | 5.2 Services equipment | 5.2.1 Services equipment | 5.2.1.1 Services equipment: details to be stated.
5.2.1.2 | Testing of installations. |  | 0 | A5.2.1.2 | 3 | 5 SERVICES | 5.2 Services equipment | 5.2.1 Services equipment | 5.2.1.2 Testing of installations.
5.1.2.3 | Commissioning of installations. |  | 0 | A5.1.2.3 | 3 | 5 SERVICES | 5.2 Services equipment | 5.2.1 Services equipment | 5.1.2.3 Commissioning of installations.
5.3 | Disposal installations |  | 0 | A5.3 | 1 | 5 SERVICES | 5.3 Disposal installations
5.2.2 | Foul drainage above ground |  | 0 | A5.2.2 | 2 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground
5.2.2.1 | Drainage to sanitary appliance: details to be stated. | 500 | 545 | A5.2.2.1 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.1 Drainage to sanitary appliance: details to be stated.
5.2.2.1 | Drainage to sanitary appliance: details to be stated. | 500 | 473 | A5.2.2.1 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.1 Drainage to sanitary appliance: details to be stated.
5.2.2.1 | Drainage to sanitary appliance: details to be stated. | 500 | 483 | A5.2.2.1 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.1 Drainage to sanitary appliance: details to be stated.
5.2.2.1 | Drainage to sanitary appliance: details to be stated. | 500 | 529 | A5.2.2.1 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.1 Drainage to sanitary appliance: details to be stated.
5.2.2.1 | Drainage to sanitary appliance: details to be stated. | 500 | 464 | A5.2.2.1 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.1 Drainage to sanitary appliance: details to be stated.
5.2.2.2 | Drainage to services equipment: details to be stated. |  | 0 | A5.2.2.2 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.2 Drainage to services equipment: details to be stated.
5.2.2.3 | Testing of installations. |  | 0 | A5.2.2.3 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.3 Testing of installations.
5.2.2.4 | Commissioning of installations. |  | 0 | A5.2.2.4 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.2 Foul drainage above ground | 5.2.2.4 Commissioning of installations.
5.2.3 | Chemical, toxic and industrial liquid waste drainage |  | 0 | A5.2.3 | 2 | 5 SERVICES | 5.3 Disposal installations | 5.2.3 Chemical, toxic and industrial liquid waste drainage
5.2.3.1 | Drainage to appliance or equipment: details to be stated. |  | 0 | A5.2.3.1 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.3 Chemical, toxic and industrial liquid waste drainage | 5.2.3.1 Drainage to appliance or equipment: details to be stated.
5.2.3.2 | Testing of installations. |  | 0 | A5.2.3.2 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.3 Chemical, toxic and industrial liquid waste drainage | 5.2.3.2 Testing of installations.
5.2.3.3 | Commissioning of installations. |  | 0 | A5.2.3.3 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.3 Chemical, toxic and industrial liquid waste drainage | 5.2.3.3 Commissioning of installations.
5.2.4 | Refuse disposal |  | 0 | A5.2.4 | 2 | 5 SERVICES | 5.3 Disposal installations | 5.2.4 Refuse disposal
5.2.4.1 | Refuse disposal installation: details to be stated. |  | 0 | A5.2.4.1 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.4 Refuse disposal | 5.2.4.1 Refuse disposal installation: details to be stated.
5.2.4.2 | Testing of installations. |  | 0 | A5.2.4.2 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.4 Refuse disposal | 5.2.4.2 Testing of installations.
5.2.4.3 | Commissioning of installations. |  | 0 | A5.2.4.3 | 3 | 5 SERVICES | 5.3 Disposal installations | 5.2.4 Refuse disposal | 5.2.4.3 Commissioning of installations.
5.4 | Water installations |  | 0 | A5.4 | 1 | 5 SERVICES | 5.4 Water installations
5.4.1 | Mains water supply |  | 0 | A5.4.1 | 2 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply
5.4.1.1 | Mains water supply: details, including the number of draw-off points (nr), to be stated. | 715 | 655 | A5.4.1.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply | 5.4.1.1 Mains water supply: details, including the number of draw-off points (nr), to be stated.
5.4.1.1 | Mains water supply: details, including the number of draw-off points (nr), to be stated. | 715 | 660 | A5.4.1.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply | 5.4.1.1 Mains water supply: details, including the number of draw-off points (nr), to be stated.
5.4.1.1 | Mains water supply: details, including the number of draw-off points (nr), to be stated. | 715 | 748 | A5.4.1.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply | 5.4.1.1 Mains water supply: details, including the number of draw-off points (nr), to be stated.
5.4.1.1 | Mains water supply: details, including the number of draw-off points (nr), to be stated. | 715 | 734 | A5.4.1.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply | 5.4.1.1 Mains water supply: details, including the number of draw-off points (nr), to be stated.
5.4.1.1 | Mains water supply: details, including the number of draw-off points (nr), to be stated. | 715 | 733 | A5.4.1.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply | 5.4.1.1 Mains water supply: details, including the number of draw-off points (nr), to be stated.
5.4.1.2 | Testing of installations. |  | 0 | A5.4.1.2 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply | 5.4.1.2 Testing of installations.
5.4.1.3 | Commissioning of installations. |  | 0 | A5.4.1.3 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.1 Mains water supply | 5.4.1.3 Commissioning of installations.
5.4.2 | Cold water distribution |  | 0 | A5.4.2 | 2 | 5 SERVICES | 5.4 Water installations | 5.4.2 Cold water distribution
5.4.2.1 | Cold water distribution: details, including the number of draw-off points (nr), to be stated. |  | 0 | A5.4.2.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.2 Cold water distribution | 5.4.2.1 Cold water distribution: details, including the number of draw-off points (nr), to be stated.
5.4.2.2 | Storage tanks: details, including type, material and capacity, to be stated. |  | 0 | A5.4.2.2 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.2 Cold water distribution | 5.4.2.2 Storage tanks: details, including type, material and capacity, to be stated.
5.4.2.3 | Rainwater harvesting systems: details to be stated. |  | 0 | A5.4.2.3 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.2 Cold water distribution | 5.4.2.3 Rainwater harvesting systems: details to be stated.
5.4.2.4 | Testing of installations. |  | 0 | A5.4.2.4 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.2 Cold water distribution | 5.4.2.4 Testing of installations.
5.4.2.5 | Commissioning of installations. |  | 0 | A5.4.2.5 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.2 Cold water distribution | 5.4.2.5 Commissioning of installations.
5.4.3 | Hot water distribution |  | 0 | A5.4.3 | 2 | 5 SERVICES | 5.4 Water installations | 5.4.3 Hot water distribution
5.4.3.1 | Hot water distribution: details, including the number of draw-off points (nr), to be stated. |  | 0 | A5.4.3.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.3 Hot water distribution | 5.4.3.1 Hot water distribution: details, including the number of draw-off points (nr), to be stated.
5.4.3.2 | Testing of installations. |  | 0 | A5.4.3.2 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.3 Hot water distribution | 5.4.3.2 Testing of installations.
5.4.3.3 | Commissioning of installations. |  | 0 | A5.4.3.3 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.3 Hot water distribution | 5.4.3.3 Commissioning of installations.
5.4.4 | Local hot water distribution |  | 0 | A5.4.4 | 2 | 5 SERVICES | 5.4 Water installations | 5.4.4 Local hot water distribution
5.4.4.1 | Water heaters: details to be stated. |  | 0 | A5.4.4.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.4 Local hot water distribution | 5.4.4.1 Water heaters: details to be stated.
5.4.4.2 | Testing of installations. |  | 0 | A5.4.4.2 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.4 Local hot water distribution | 5.4.4.2 Testing of installations.
5.4.4.3 | Commissioning of installations. |  | 0 | A5.4.4.3 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.4 Local hot water distribution | 5.4.4.3 Commissioning of installations.
5.4.5 | Steam and condensate distribution |  | 0 | A5.4.5 | 2 | 5 SERVICES | 5.4 Water installations | 5.4.5 Steam and condensate distribution
5.4.5.1 | Steam and condensate distribution: details, including number of draw-off points (nr), to be stated. |  | 0 | A5.4.5.1 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.5 Steam and condensate distribution | 5.4.5.1 Steam and condensate distribution: details, including number of draw-off points (nr), to be stated.
5.4.5.2 | Testing of installations. |  | 0 | A5.4.5.2 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.5 Steam and condensate distribution | 5.4.5.2 Testing of installations.
5.4.5.3 | Commissioning of installations. |  | 0 | A5.4.5.3 | 3 | 5 SERVICES | 5.4 Water installations | 5.4.5 Steam and condensate distribution | 5.4.5.3 Commissioning of installations.
5.5 | Heat source |  | 0 | A5.5 | 1 | 5 SERVICES | 5.5 Heat source
5.5.1 | Heat source |  | 0 | A5.5.1 | 2 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source
5.5.1.1 | Heat source (nr): details, including output of heat source (kW), to be stated. | 1000 | 1025 | A5.5.1.1 | 3 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source | 5.5.1.1 Heat source (nr): details, including output of heat source (kW), to be stated.
5.5.1.1 | Heat source (nr): details, including output of heat source (kW), to be stated. | 1000 | 1042 | A5.5.1.1 | 3 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source | 5.5.1.1 Heat source (nr): details, including output of heat source (kW), to be stated.
5.5.1.1 | Heat source (nr): details, including output of heat source (kW), to be stated. | 1000 | 1006 | A5.5.1.1 | 3 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source | 5.5.1.1 Heat source (nr): details, including output of heat source (kW), to be stated.
5.5.1.1 | Heat source (nr): details, including output of heat source (kW), to be stated. | 1000 | 958 | A5.5.1.1 | 3 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source | 5.5.1.1 Heat source (nr): details, including output of heat source (kW), to be stated.
5.5.1.1 | Heat source (nr): details, including output of heat source (kW), to be stated. | 1000 | 918 | A5.5.1.1 | 3 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source | 5.5.1.1 Heat source (nr): details, including output of heat source (kW), to be stated.
5.5.1.2 | Testing of installations. |  | 0 | A5.5.1.2 | 3 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source | 5.5.1.2 Testing of installations.
5.5.1.3 | Commissioning of installations. |  | 0 | A5.5.1.3 | 3 | 5 SERVICES | 5.5 Heat source | 5.5.1 Heat source | 5.5.1.3 Commissioning of installations.
5.6 | Space heating and air conditioning |  | 0 | A5.6 | 1 | 5 SERVICES | 5.6 Space heating and air conditioning
5.6.1 | Central heating |  | 0 | A5.6.1 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating
5.6.1.1 | Central heating systems: details to be stated. | 2000 | 1824 | A5.6.1.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating | 5.6.1.1 Central heating systems: details to be stated.
5.6.1.1 | Central heating systems: details to be stated. | 2000 | 1877 | A5.6.1.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating | 5.6.1.1 Central heating systems: details to be stated.
5.6.1.1 | Central heating systems: details to be stated. | 2000 | 2111 | A5.6.1.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating | 5.6.1.1 Central heating systems: details to be stated.
5.6.1.1 | Central heating systems: details to be stated. | 2000 | 2176 | A5.6.1.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating | 5.6.1.1 Central heating systems: details to be stated.
5.6.1.1 | Central heating systems: details to be stated. | 2000 | 1941 | A5.6.1.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating | 5.6.1.1 Central heating systems: details to be stated.
5.6.1.2 | Testing of installations. |  | 0 | A5.6.1.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating | 5.6.1.2 Testing of installations.
5.6.1.3 | Commissioning of installations. |  | 0 | A5.6.1.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.1 Central heating | 5.6.1.3 Commissioning of installations.
5.6.2 | Local heating |  | 0 | A5.6.2 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.2 Local heating
5.6.2.1 | Heaters: details to be stated. |  | 0 | A5.6.2.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.2 Local heating | 5.6.2.1 Heaters: details to be stated.
5.6.2.2 | Testing of installations. |  | 0 | A5.6.2.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.2 Local heating | 5.6.2.2 Testing of installations.
5.6.2.3 | Commissioning of installations. |  | 0 | A5.6.2.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.2 Local heating | 5.6.2.3 Commissioning of installations.
5.6.3 | Central cooling |  | 0 | A5.6.3 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.3 Central cooling
5.6.3.1 | Central cooling systems: details to be stated. |  | 0 | A5.6.3.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.3 Central cooling | 5.6.3.1 Central cooling systems: details to be stated.
5.6.3.2 | Testing of installations. |  | 0 | A5.6.3.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.3 Central cooling | 5.6.3.2 Testing of installations.
5.6.3.3 | Commissioning of installations. |  | 0 | A5.6.3.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.3 Central cooling | 5.6.3.3 Commissioning of installations.
5.6.4 | Local cooling |  | 0 | A5.6.4 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.4 Local cooling
5.6.4.1 | Cooling units: details to be stated. |  | 0 | A5.6.4.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.4 Local cooling | 5.6.4.1 Cooling units: details to be stated.
5.6.4.2 | Testing of installations. |  | 0 | A5.6.4.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.4 Local cooling | 5.6.4.2 Testing of installations.
5.6.4.3 | Commissioning of installations. |  | 0 | A5.6.4.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.4 Local cooling | 5.6.4.3 Commissioning of installations.
5.6.5 | Central heating and cooling |  | 0 | A5.6.5 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.5 Central heating and cooling
5.6.5.1 | Combined central heating and cooling systems: details to be stated. |  | 0 | A5.6.5.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.5 Central heating and cooling | 5.6.5.1 Combined central heating and cooling systems: details to be stated.
5.6.5.2 | Testing of installations. |  | 0 | A5.6.5.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.5 Central heating and cooling | 5.6.5.2 Testing of installations.
5.6.5.3 | Commissioning of installations. |  | 0 | A5.6.5.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.5 Central heating and cooling | 5.6.5.3 Commissioning of installations.
5.6.6 | Local heating and cooling |  | 0 | A5.6.6 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.6 Local heating and cooling
5.6.6.1 | Local heating and cooling units: details to be stated. |  | 0 | A5.6.6.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.6 Local heating and cooling | 5.6.6.1 Local heating and cooling units: details to be stated.
5.6.6.2 | Testing of installations. |  | 0 | A5.6.6.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.6 Local heating and cooling | 5.6.6.2 Testing of installations.
5.6.6.3 | Commissioning of installations. |  | 0 | A5.6.6.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.6 Local heating and cooling | 5.6.6.3 Commissioning of installations.
5.6.7 | Central air conditioning |  | 0 | A5.6.7 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.7 Central air conditioning
5.6.7.1 | Central air conditioning system: details to be stated. |  | 0 | A5.6.7.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.7 Central air conditioning | 5.6.7.1 Central air conditioning system: details to be stated.
5.6.7.2 | Testing of installations. |  | 0 | A5.6.7.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.7 Central air conditioning | 5.6.7.2 Testing of installations.
5.6.7.3 | Commissioning of installations. |  | 0 | A5.6.7.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.7 Central air conditioning | 5.6.7.3 Commissioning of installations.
5.6.8 | Local air conditioning |  | 0 | A5.6.8 | 2 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.8 Local air conditioning
5.6.8.1 | Self-contained air conditioning units: details to be stated. |  | 0 | A5.6.8.1 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.8 Local air conditioning | 5.6.8.1 Self-contained air conditioning units: details to be stated.
5.6.8.2 | Other local air conditioning systems: details to be stated. |  | 0 | A5.6.8.2 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.8 Local air conditioning | 5.6.8.2 Other local air conditioning systems: details to be stated.
5.6.8.3 | Testing of installations. |  | 0 | A5.6.8.3 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.8 Local air conditioning | 5.6.8.3 Testing of installations.
5.6.8.4 | Commissioning of installations. |  | 0 | A5.6.8.4 | 3 | 5 SERVICES | 5.6 Space heating and air conditioning | 5.6.8 Local air conditioning | 5.6.8.4 Commissioning of installations.
5.7 | Ventilation |  | 0 | A5.7 | 1 | 5 SERVICES | 5.7 Ventilation
5.7.1 | Central ventilation |  | 0 | A5.7.1 | 2 | 5 SERVICES | 5.7 Ventilation | 5.7.1 Central ventilation
5.7.1.1 | Central ventilation systems: details to be stated. |  | 0 | A5.7.1.1 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.1 Central ventilation | 5.7.1.1 Central ventilation systems: details to be stated.
5.7.1.2 | Testing of installations. |  | 0 | A5.7.1.2 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.1 Central ventilation | 5.7.1.2 Testing of installations.
5.7.1.3 | Commissioning of installations. |  | 0 | A5.7.1.3 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.1 Central ventilation | 5.7.1.3 Commissioning of installations.
5.7.2 | Local and special ventilation |  | 0 | A5.7.2 | 2 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation
5.7.2.1 | Toilet/bathroom ventilation units: details to be stated. |  | 0 | A5.7.2.1 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.1 Toilet/bathroom ventilation units: details to be stated.
5.7.2.2 | Kitchen ventilation units: details to be stated. |  | 0 | A5.7.2.2 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.2 Kitchen ventilation units: details to be stated.
5.7.2.3 | Safety cabinet and fume cupboard extracts: details to be stated. |  | 0 | A5.7.2.3 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.3 Safety cabinet and fume cupboard extracts: details to be stated.
5.7.2.4 | Fume extracts: details to be stated. |  | 0 | A5.7.2.4 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.4 Fume extracts: details to be stated.
5.7.2.5 | Dust collection units: details to be stated. |  | 0 | A5.7.2.5 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.5 Dust collection units: details to be stated.
5.7.2.6 | Anaesthetic gas extracts: details to be stated. |  | 0 | A5.7.2.6 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.6 Anaesthetic gas extracts: details to be stated.
5.7.2.7 | Cyclone systems: details to be stated. |  | 0 | A5.7.2.7 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.7 Cyclone systems: details to be stated.
5.7.2.8 | Unit extract fans: details to be stated. |  | 0 | A5.7.2.8 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.8 Unit extract fans: details to be stated.
5.7.2.9 | Rotating ventilators: details to be stated. |  | 0 | A5.7.2.9 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.9 Rotating ventilators: details to be stated.
5.7.2.10 | Roof mounted ventilation units: details to be stated. |  | 0 | A5.7.2.10 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.10 Roof mounted ventilation units: details to be stated.
5.7.2.11 | Car parking ventilation: details to be stated. |  | 0 | A5.7.2.11 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.11 Car parking ventilation: details to be stated.
5.7.2.12 | Car parking ventilation: details to be stated. |  | 0 | A5.7.2.12 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.12 Car parking ventilation: details to be stated.
5.7.2.13 | Other local and special ventilation systems: details to be stated. |  | 0 | A5.7.2.13 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.13 Other local and special ventilation systems: details to be stated.
5.7.2.14 | Testing of installations. |  | 0 | A5.7.2.14 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.14 Testing of installations.
5.7.2.15 | Commissioning of installations. |  | 0 | A5.7.2.15 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.2 Local and special ventilation | 5.7.2.15 Commissioning of installations.
5.7.3 | Smoke extract/control |  | 0 | A5.7.3 | 2 | 5 SERVICES | 5.7 Ventilation | 5.7.3 Smoke extract/control
5.7.3.1 | Smoke extract/control systems: details to be stated. |  | 0 | A5.7.3.1 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.3 Smoke extract/control | 5.7.3.1 Smoke extract/control systems: details to be stated.
5.7.3.2 | Testing of installations. |  | 0 | A5.7.3.2 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.3 Smoke extract/control | 5.7.3.2 Testing of installations.
5.7.3.3 | Commissioning of installations. |  | 0 | A5.7.3.3 | 3 | 5 SERVICES | 5.7 Ventilation | 5.7.3 Smoke extract/control | 5.7.3.3 Commissioning of installations.
5.8 | Electrical installations |  | 0 | A5.8 | 1 | 5 SERVICES | 5.8 Electrical installations
5.8.1 | Electrical mains and sub-mains distribution |  | 0 | A5.8.1 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution
5.8.1.1 | Electrical mains and sub-mains distribution: details to be stated. | 200000 | 186761 | A5.8.1.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution | 5.8.1.1 Electrical mains and sub-mains distribution: details to be stated.
5.8.1.1 | Electrical mains and sub-mains distribution: details to be stated. | 200000 | 196005 | A5.8.1.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution | 5.8.1.1 Electrical mains and sub-mains distribution: details to be stated.
5.8.1.1 | Electrical mains and sub-mains distribution: details to be stated. | 200000 | 195521 | A5.8.1.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution | 5.8.1.1 Electrical mains and sub-mains distribution: details to be stated.
5.8.1.1 | Electrical mains and sub-mains distribution: details to be stated. | 200000 | 204450 | A5.8.1.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution | 5.8.1.1 Electrical mains and sub-mains distribution: details to be stated.
5.8.1.1 | Electrical mains and sub-mains distribution: details to be stated. | 200000 | 190382 | A5.8.1.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution | 5.8.1.1 Electrical mains and sub-mains distribution: details to be stated.
5.8.1.2 | Testing of installations. |  | 0 | A5.8.1.2 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution | 5.8.1.2 Testing of installations.
5.8.1.3 | Commissioning of installations. |  | 0 | A5.8.1.3 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.1 Electrical mains and sub-mains distribution | 5.8.1.3 Commissioning of installations.
5.8.2 | Power installations |  | 0 | A5.8.2 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.2 Power installations
5.8.2.1 | Power installation: details to be stated. |  | 0 | A5.8.2.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.2 Power installations | 5.8.2.1 Power installation: details to be stated.
5.8.2.2 | Testing of installations. |  | 0 | A5.8.2.2 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.2 Power installations | 5.8.2.2 Testing of installations.
5.8.2.3 | Commissioning of installations. |  | 0 | A5.8.2.3 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.2 Power installations | 5.8.2.3 Commissioning of installations.
5.8.3 | Lighting installations |  | 0 | A5.8.3 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations
5.8.3.1 | Lighting installation: details to be stated. | 200000 | 185601 | A5.8.3.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations | 5.8.3.1 Lighting installation: details to be stated.
5.8.3.1 | Lighting installation: details to be stated. | 200000 | 184560 | A5.8.3.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations | 5.8.3.1 Lighting installation: details to be stated.
5.8.3.1 | Lighting installation: details to be stated. | 200000 | 207681 | A5.8.3.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations | 5.8.3.1 Lighting installation: details to be stated.
5.8.3.1 | Lighting installation: details to be stated. | 200000 | 192194 | A5.8.3.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations | 5.8.3.1 Lighting installation: details to be stated.
5.8.3.1 | Lighting installation: details to be stated. | 200000 | 216630 | A5.8.3.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations | 5.8.3.1 Lighting installation: details to be stated.
5.8.3.2 | Testing of installations. |  | 0 | A5.8.3.2 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations | 5.8.3.2 Testing of installations.
5.8.3.3 | Commissioning of installations. |  | 0 | A5.8.3.3 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.3 Lighting installations | 5.8.3.3 Commissioning of installations.
5.8.4 | Specialist lighting installations |  | 0 | A5.8.4 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.4 Specialist lighting installations
5.8.4.1 | Specialist lighting installation: details to be stated. |  | 0 | A5.8.4.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.4 Specialist lighting installations | 5.8.4.1 Specialist lighting installation: details to be stated.
5.8.4.2 | Testing of installations. |  | 0 | A5.8.4.2 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.4 Specialist lighting installations | 5.8.4.2 Testing of installations.
5.8.4.3 | Commissioning of installations. |  | 0 | A5.8.4.3 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.4 Specialist lighting installations | 5.8.4.3 Commissioning of installations.
5.8.5 | Local electricity generation systems |  | 0 | A5.8.5 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Local electricity generation systems
5.8.5 | Local generation equipment: |  | 0 | A5.8.5 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Local generation equipment:
5.8.5.1 | Electricity generation systems: details to be stated. |  | 0 | A5.8.5.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Local generation equipment: | 5.8.5.1 Electricity generation systems: details to be stated.
5.8.5.2 | Testing of installations. |  | 0 | A5.8.5.2 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Local generation equipment: | 5.8.5.2 Testing of installations.
5.8.5.3 | Commissioning of installations. |  | 0 | A5.8.5.3 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Local generation equipment: | 5.8.5.3 Commissioning of installations.
5.8.5 | Transformation devices: |  | 0 | A5.8.5 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Transformation devices:
5.8.5.4 | Wind turbines: details, including output (kW), to be stated. |  | 0 | A5.8.5.4 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Transformation devices: | 5.8.5.4 Wind turbines: details, including output (kW), to be stated.
5.8.5.5 | Photovoltaic devices: details, including surface area of units (m2) and output (kW), to be stated. |  | 0 | A5.8.5.5 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Transformation devices: | 5.8.5.5 Photovoltaic devices: details, including surface area of units (m2) and output (kW), to be stated.
5.8.5.6 | Other transformation devices: details, including output (kW), to be stated. |  | 0 | A5.8.5.6 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Transformation devices: | 5.8.5.6 Other transformation devices: details, including output (kW), to be stated.
5.8.5.7 | Testing of installations. |  | 0 | A5.8.5.7 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Transformation devices: | 5.8.5.7 Testing of installations.
5.8.5.8 | Commissioning of installations. |  | 0 | A5.8.5.8 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.5 Transformation devices: | 5.8.5.8 Commissioning of installations.
5.8.6 | Earthing and bonding systems |  | 0 | A5.8.6 | 2 | 5 SERVICES | 5.8 Electrical installations | 5.8.6 Earthing and bonding systems
5.8.6.1 | Earthing and bonding systems: details to be stated. |  | 0 | A5.8.6.1 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.6 Earthing and bonding systems | 5.8.6.1 Earthing and bonding systems: details to be stated.
5.8.6.2 | Testing of installations. |  | 0 | A5.8.6.2 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.6 Earthing and bonding systems | 5.8.6.2 Testing of installations.
5.8.6.3 | Commissioning of installations. |  | 0 | A5.8.6.3 | 3 | 5 SERVICES | 5.8 Electrical installations | 5.8.6 Earthing and bonding systems | 5.8.6.3 Commissioning of installations.
5.9 | Fuel installations |  | 0 | A5.9 | 1 | 5 SERVICES | 5.9 Fuel installations
5.9.1 | Fuel storage |  | 0 | A5.9.1 | 2 | 5 SERVICES | 5.9 Fuel installations | 5.9.1 Fuel storage
5.9.1.1 | Fuel storage: details to be stated. |  | 0 | A5.9.1.1 | 3 | 5 SERVICES | 5.9 Fuel installations | 5.9.1 Fuel storage | 5.9.1.1 Fuel storage: details to be stated.
5.9.1.2 | Testing of installations. |  | 0 | A5.9.1.2 | 3 | 5 SERVICES | 5.9 Fuel installations | 5.9.1 Fuel storage | 5.9.1.2 Testing of installations.
5.9.1.3 | Commissioning of installations. |  | 0 | A5.9.1.3 | 3 | 5 SERVICES | 5.9 Fuel installations | 5.9.1 Fuel storage | 5.9.1.3 Commissioning of installations.
5.9.2 | Fuel distribution systems |  | 0 | A5.9.2 | 2 | 5 SERVICES | 5.9 Fuel installations | 5.9.2 Fuel distribution systems
5.9.2.1 | Piped distribution systems: details to be stated. |  | 0 | A5.9.2.1 | 3 | 5 SERVICES | 5.9 Fuel installations | 5.9.2 Fuel distribution systems | 5.9.2.1 Piped distribution systems: details to be stated.
5.9.2.2 | Testing of installations. |  | 0 | A5.9.2.2 | 3 | 5 SERVICES | 5.9 Fuel installations | 5.9.2 Fuel distribution systems | 5.9.2.2 Testing of installations.
5.9.2.3 | Commissioning of installations. |  | 0 | A5.9.2.3 | 3 | 5 SERVICES | 5.9 Fuel installations | 5.9.2 Fuel distribution systems | 5.9.2.3 Commissioning of installations.
5.10 | Lift and conveyor installations |  | 0 | A5.10 | 1 | 5 SERVICES | 5.10 Lift and conveyor installations
5.10.1 | Lifts and enclosed hoists |  | 0 | A5.10.1 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Lifts and enclosed hoists
5.10.1 | Lifts: |  | 0 | A5.10.1 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Lifts:
5.10.1.1 | Passenger lifts: details, including capacity (i.e. number of persons), speed (in m/sec), number of doors (nr), door heights and number of levels serviced (nr), to be stated. |  | 0 | A5.10.1.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Lifts: | 5.10.1.1 Passenger lifts: details, including capacity (i.e. number of persons), speed (in m/sec), number of doors (nr), door heights and number of levels serviced (nr), to be stated.
5.10.1.2 | Wall climbing lifts: details, including capacity (in kg), number of persons, speed (in m/sec) and number of levels serviced (nr), to be stated. |  | 0 | A5.10.1.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Lifts: | 5.10.1.2 Wall climbing lifts: details, including capacity (in kg), number of persons, speed (in m/sec) and number of levels serviced (nr), to be stated.
5.10.1.3 | Goods lifts: details, including capacity (in kg), number of doors, door heights and number of levels serviced (nr), to be stated. |  | 0 | A5.10.1.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Lifts: | 5.10.1.3 Goods lifts: details, including capacity (in kg), number of doors, door heights and number of levels serviced (nr), to be stated.
5.10.1.4 | Testing of lift installations. |  | 0 | A5.10.1.4 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Lifts: | 5.10.1.4 Testing of lift installations.
5.10.1.5 | Commissioning of lift installations. |  | 0 | A5.10.1.5 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Lifts: | 5.10.1.5 Commissioning of lift installations.
5.10.1 | Enclosed hoists: |  | 0 | A5.10.1 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Enclosed hoists:
5.10.1.6 | Enclosed hoists: details, including capacity (in kg) and number of levels (nr) serviced, to be stated. |  | 0 | A5.10.1.6 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Enclosed hoists: | 5.10.1.6 Enclosed hoists: details, including capacity (in kg) and number of levels (nr) serviced, to be stated.
5.10.1.7 | Testing of enclosed hoist installations. |  | 0 | A5.10.1.7 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Enclosed hoists: | 5.10.1.7 Testing of enclosed hoist installations.
5.10.1.8 | Commissioning of enclosed hoist installations. |  | 0 | A5.10.1.8 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.1 Enclosed hoists: | 5.10.1.8 Commissioning of enclosed hoist installations.
5.10.2 | Escalators |  | 0 | A5.10.2 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.2 Escalators
5.10.2.1 | Escalators: details, including, number of flights served (nr), angle of rise (in degrees), rise (m) and step width (mm), to be stated. |  | 0 | A5.10.2.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.2 Escalators | 5.10.2.1 Escalators: details, including, number of flights served (nr), angle of rise (in degrees), rise (m) and step width (mm), to be stated.
5.10.2.2 | Testing of installations. |  | 0 | A5.10.2.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.2 Escalators | 5.10.2.2 Testing of installations.
5.10.2.3 | Commissioning of installations. |  | 0 | A5.10.2.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.2 Escalators | 5.10.2.3 Commissioning of installations.
5.10.3 | Moving pavements |  | 0 | A5.10.3 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.3 Moving pavements
5.10.3.1 | Moving pavements: details, including, length (m) and width (mm), to be stated. |  | 0 | A5.10.3.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.3 Moving pavements | 5.10.3.1 Moving pavements: details, including, length (m) and width (mm), to be stated.
5.10.3.2 | Testing of installations. |  | 0 | A5.10.3.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.3 Moving pavements | 5.10.3.2 Testing of installations.
5.10.3.3 | Commissioning of installations. |  | 0 | A5.10.3.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.3 Moving pavements | 5.10.3.3 Commissioning of installations.
5.10.4 | Powered stairlifts |  | 0 | A5.10.4 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.4 Powered stairlifts
5.10.4.1 | Powered stairlifts: details to be stated. |  | 0 | A5.10.4.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.4 Powered stairlifts | 5.10.4.1 Powered stairlifts: details to be stated.
5.10.4.2 | Testing of installations. |  | 0 | A5.10.4.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.4 Powered stairlifts | 5.10.4.2 Testing of installations.
5.10.4.3 | Commissioning of installations. |  | 0 | A5.10.4.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.4 Powered stairlifts | 5.10.4.3 Commissioning of installations.
5.10.5 | Conveyors |  | 0 | A5.10.5 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.5 Conveyors
5.10.5.1 | People conveyors: details, including, length (m) and width (mm), to be stated. |  | 0 | A5.10.5.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.5 Conveyors | 5.10.5.1 People conveyors: details, including, length (m) and width (mm), to be stated.
5.10.5.2 | Goods conveyors: details, including, length (m) and width (mm), to be stated. |  | 0 | A5.10.5.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.5 Conveyors | 5.10.5.2 Goods conveyors: details, including, length (m) and width (mm), to be stated.
5.10.5.3 | Testing of installations. |  | 0 | A5.10.5.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.5 Conveyors | 5.10.5.3 Testing of installations.
5.10.5.4 | Commissioning of installations. |  | 0 | A5.10.5.4 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.5 Conveyors | 5.10.5.4 Commissioning of installations.
5.10.6 | Dock levellers and scissor lifts |  | 0 | A5.10.6 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.6 Dock levellers and scissor lifts
5.10.6.1 | Dock levellers and scissor lifts: details, including total rise (m), to be stated. |  | 0 | A5.10.6.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.6 Dock levellers and scissor lifts | 5.10.6.1 Dock levellers and scissor lifts: details, including total rise (m), to be stated.
5.10.6.2 | Scissor lifts: details, including total rise (m), to be stated. |  | 0 | A5.10.6.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.6 Dock levellers and scissor lifts | 5.10.6.2 Scissor lifts: details, including total rise (m), to be stated.
5.10.6.3 | Testing of installations. |  | 0 | A5.10.6.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.6 Dock levellers and scissor lifts | 5.10.6.3 Testing of installations.
5.10.6.4 | Commissioning of installations. |  | 0 | A5.10.6.4 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.6 Dock levellers and scissor lifts | 5.10.6.4 Commissioning of installations.
5.10.7 | Cranes and unenclosed hoists |  | 0 | A5.10.7 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.7 Cranes and unenclosed hoists
5.10.7.1 | Cranes: details including design load (kN) and total rise (m), to be stated. |  | 0 | A5.10.7.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.7 Cranes and unenclosed hoists | 5.10.7.1 Cranes: details including design load (kN) and total rise (m), to be stated.
5.10.7.2 | Travelling cranes: details, including design load (kN), to be stated. |  | 0 | A5.10.7.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.7 Cranes and unenclosed hoists | 5.10.7.2 Travelling cranes: details, including design load (kN), to be stated.
5.10.7.3 | Unenclosed hoists: details, including total rise (m), to be stated. |  | 0 | A5.10.7.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.7 Cranes and unenclosed hoists | 5.10.7.3 Unenclosed hoists: details, including total rise (m), to be stated.
5.10.7.4 | Testing of installations. |  | 0 | A5.10.7.4 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.7 Cranes and unenclosed hoists | 5.10.7.4 Testing of installations.
5.10.7.5 | Commissioning of installations. |  | 0 | A5.10.7.5 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.7 Cranes and unenclosed hoists | 5.10.7.5 Commissioning of installations.
5.10.8 | Car lifts, car stacking systems, turntables and the like |  | 0 | A5.10.8 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.8 Car lifts, car stacking systems, turntables and the like
5.10.8.1 | Car lifts: details, including number of floors served (nr), to be stated. |  | 0 | A5.10.8.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.8 Car lifts, car stacking systems, turntables and the like | 5.10.8.1 Car lifts: details, including number of floors served (nr), to be stated.
5.10.8.2 | Car stacking systems: details, including capacity (i.e. number of cars - nr), to be stated. |  | 0 | A5.10.8.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.8 Car lifts, car stacking systems, turntables and the like | 5.10.8.2 Car stacking systems: details, including capacity (i.e. number of cars - nr), to be stated.
5.10.8.3 | Vehicle turntables: details to be stated. |  | 0 | A5.10.8.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.8 Car lifts, car stacking systems, turntables and the like | 5.10.8.3 Vehicle turntables: details to be stated.
5.10.8.4 | Testing of installations. |  | 0 | A5.10.8.4 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.8 Car lifts, car stacking systems, turntables and the like | 5.10.8.4 Testing of installations.
5.10.8.5 | Commissioning of installations. |  | 0 | A5.10.8.5 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.8 Car lifts, car stacking systems, turntables and the like | 5.10.8.5 Commissioning of installations.
5.10.9 | Document handling systems |  | 0 | A5.10.9 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.9 Document handling systems
5.10.9.1 | Document handling/delivery systems: details to be stated. |  | 0 | A5.10.9.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.9 Document handling systems | 5.10.9.1 Document handling/delivery systems: details to be stated.
5.10.9.2 | Warehouse picking systems: details to be stated. |  | 0 | A5.10.9.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.9 Document handling systems | 5.10.9.2 Warehouse picking systems: details to be stated.
5.10.9.3 | Other systems: details to be stated. |  | 0 | A5.10.9.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.9 Document handling systems | 5.10.9.3 Other systems: details to be stated.
5.10.9.4 | Testing of installations. |  | 0 | A5.10.9.4 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.9 Document handling systems | 5.10.9.4 Testing of installations.
5.10.9.5 | Commissioning of installations. |  | 0 | A5.10.9.5 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.9 Document handling systems | 5.10.9.5 Commissioning of installations.
5.10.10 | Other lift and conveyor installations |  | 0 | A5.10.10 | 2 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.10 Other lift and conveyor installations
5.10.10.1 | Other lift and conveyor installations: details to be stated. |  | 0 | A5.10.10.1 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.10 Other lift and conveyor installations | 5.10.10.1 Other lift and conveyor installations: details to be stated.
5.10.10.2 | Testing of installations. |  | 0 | A5.10.10.2 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.10 Other lift and conveyor installations | 5.10.10.2 Testing of installations.
5.10.10.3 | Commissioning of installations. |  | 0 | A5.10.10.3 | 3 | 5 SERVICES | 5.10 Lift and conveyor installations | 5.10.10 Other lift and conveyor installations | 5.10.10.3 Commissioning of installations.
5.11 | Fire and lightning protection |  | 0 | A5.11 | 1 | 5 SERVICES | 5.11 Fire and lightning protection
5.11 | Fire and lightning protection |  | 0 | A5.11 | 1 | 5 SERVICES | 5.11 Fire and lightning protection
5.11.1 | Fire fighting systems |  | 0 | A5.11.1 | 2 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems
5.11.1.1 | Fire hose reels: details of each type of system to be stated. |  | 0 | A5.11.1.1 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems | 5.11.1.1 Fire hose reels: details of each type of system to be stated.
5.11.1.2 | Dry risers: details to be stated. |  | 0 | A5.11.1.2 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems | 5.11.1.2 Dry risers: details to be stated.
5.11.1.3 | Wet risers: details to be stated. |  | 0 | A5.11.1.3 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems | 5.11.1.3 Wet risers: details to be stated.
5.11.1.4 | Fire and smoke protection curtains: details of each type of system to be stated. |  | 0 | A5.11.1.4 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems | 5.11.1.4 Fire and smoke protection curtains: details of each type of system to be stated.
5.11.1.5 | Other fire fighting systems: details of each type of system to be stated. |  | 0 | A5.11.1.5 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems | 5.11.1.5 Other fire fighting systems: details of each type of system to be stated.
5.11.1.6 | Testing of installations. |  | 0 | A5.11.1.6 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems | 5.11.1.6 Testing of installations.
5.11.1.7 | Commissioning of installations. |  | 0 | A5.11.1.7 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.1 Fire fighting systems | 5.11.1.7 Commissioning of installations.
5.11.2 | Fire suppression systems |  | 0 | A5.11.2 | 2 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.2 Fire suppression systems
5.11.2.1 | Deluge systems: details of each type of system to be stated. |  | 0 | A5.11.2.1 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.2 Fire suppression systems | 5.11.2.1 Deluge systems: details of each type of system to be stated.
5.11.2.2 | Gas fire fighting systems: details of each type of system to be stated. |  | 0 | A5.11.2.2 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.2 Fire suppression systems | 5.11.2.2 Gas fire fighting systems: details of each type of system to be stated.
5.11.2.3 | Foam fire fighting systems: details of each type of system to be stated. |  | 0 | A5.11.2.3 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.2 Fire suppression systems | 5.11.2.3 Foam fire fighting systems: details of each type of system to be stated.
5.11.2.4 | Other fire suppression systems: details of each type of system to be stated. |  | 0 | A5.11.2.4 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.2 Fire suppression systems | 5.11.2.4 Other fire suppression systems: details of each type of system to be stated.
5.11.2.5 | Testing of installations. |  | 0 | A5.11.2.5 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.2 Fire suppression systems | 5.11.2.5 Testing of installations.
5.11.2.6 | Commissioning of installations. |  | 0 | A5.11.2.6 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.2 Fire suppression systems | 5.11.2.6 Commissioning of installations.
5.11.3 | Lightning protection |  | 0 | A5.11.3 | 2 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.3 Lightning protection
5.11.3.1 | Lightning protection installations (m2): details of each type of system to be stated. |  | 0 | A5.11.3.1 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.3 Lightning protection | 5.11.3.1 Lightning protection installations (m2): details of each type of system to be stated.
5.11.3.2 | Testing of installations. |  | 0 | A5.11.3.2 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.3 Lightning protection | 5.11.3.2 Testing of installations.
5.11.3.3 | Commissioning of installations. |  | 0 | A5.11.3.3 | 3 | 5 SERVICES | 5.11 Fire and lightning protection | 5.11.3 Lightning protection | 5.11.3.3 Commissioning of installations.
5.12 | Communication, security and control systems |  | 0 | A5.12 | 1 | 5 SERVICES | 5.12 Communication, security and control systems
5.12.1 | Communication systems |  | 0 | A5.12.1 | 2 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems
5.12.1.1 | Telecommunication systems: details of each type of system to be stated. |  | 0 | A5.12.1.1 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.1 Telecommunication systems: details of each type of system to be stated.
5.12.1.2 | Data transmission systems: details of each type of system to be stated. |  | 0 | A5.12.1.2 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.2 Data transmission systems: details of each type of system to be stated.
5.12.1.3 | Paging and emergency call systems: details of each type of system to be stated. |  | 0 | A5.12.1.3 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.3 Paging and emergency call systems: details of each type of system to be stated.
5.12.1.4 | Public address and conference audio systems: details of each type of system to be stated. |  | 0 | A5.12.1.4 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.4 Public address and conference audio systems: details of each type of system to be stated.
5.12.1.5 | Radio systems: details of each type of system to be stated. |  | 0 | A5.12.1.5 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.5 Radio systems: details of each type of system to be stated.
5.12.1.6 | Projection systems: details of each type of system to be stated. |  | 0 | A5.12.1.6 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.6 Projection systems: details of each type of system to be stated.
5.12.1.7 | Fire detection and alarm systems: details of each type of system to be stated. |  | 0 | A5.12.1.7 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.7 Fire detection and alarm systems: details of each type of system to be stated.
5.12.1.8 | Smoke detection and alarm systems: details of each type of system to be stated. |  | 0 | A5.12.1.8 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.8 Smoke detection and alarm systems: details of each type of system to be stated.
5.12.1.9 | Liquid detection systems: details of each type of system to be stated. |  | 0 | A5.12.1.9 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.9 Liquid detection systems: details of each type of system to be stated.
5.12.1.10 | Clocks, card clocks, flexitime installations: details of each type of system to be stated. |  | 0 | A5.12.1.10 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.10 Clocks, card clocks, flexitime installations: details of each type of system to be stated.
5.12.1.11 | Door entry systems: details of each type of system to be stated. |  | 0 | A5.12.1.11 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.11 Door entry systems: details of each type of system to be stated.
5.12.1.12 | Radio and televisions: details of each type of system to be stated. |  | 0 | A5.12.1.12 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.12 Radio and televisions: details of each type of system to be stated.
5.12.1.13 | Television systems: details of each type of system to be stated. |  | 0 | A5.12.1.13 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.13 Television systems: details of each type of system to be stated.
5.12.1.14 | TV monitors: details of each type of system to be stated. |  | 0 | A5.12.1.14 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.14 TV monitors: details of each type of system to be stated.
5.12.1.15 | Pneumatic message systems: details of each type of system to be stated. |  | 0 | A5.12.1.15 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.15 Pneumatic message systems: details of each type of system to be stated.
5.12.1.16 | Other communication systems: details of each type of system to be stated. |  | 0 | A5.12.1.16 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.16 Other communication systems: details of each type of system to be stated.
5.12.1.17 | Testing of installations. |  | 0 | A5.12.1.17 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.17 Testing of installations.
5.12.1.18 | Commissioning of installations. |  | 0 | A5.12.1.18 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.1 Communication systems | 5.12.1.18 Commissioning of installations.
5.12.2 | Security systems |  | 0 | A5.12.2 | 2 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems
5.12.2.1 | Surveillance equipment: details of each type of system to be stated. |  | 0 | A5.12.2.1 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.1 Surveillance equipment: details of each type of system to be stated.
5.12.2.2 | Security detection equipment: details of each type of system to be stated. |  | 0 | A5.12.2.2 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.2 Security detection equipment: details of each type of system to be stated.
5.12.2.3 | Security alarm equipment: details of each type of system to be stated. |  | 0 | A5.12.2.3 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.3 Security alarm equipment: details of each type of system to be stated.
5.12.2.4 | JHLess control systems: details of each type of system to be stated. |  | 0 | A5.12.2.4 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.4 JHLess control systems: details of each type of system to be stated.
5.12.2.5 | Burglar and security alarms: details of each type of system to be stated. |  | 0 | A5.12.2.5 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.5 Burglar and security alarms: details of each type of system to be stated.
5.12.2.6 | Door entry systems: details of each type of system to be stated. |  | 0 | A5.12.2.6 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.6 Door entry systems: details of each type of system to be stated.
5.12.2.7 | Security lights and lighting systems: details of each type of system to be stated. |  | 0 | A5.12.2.7 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.7 Security lights and lighting systems: details of each type of system to be stated.
5.12.2.8 | Other security systems: details of each type of system to be stated. |  | 0 | A5.12.2.8 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.8 Other security systems: details of each type of system to be stated.
5.12.2.9 | Testing of installations. |  | 0 | A5.12.2.9 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.9 Testing of installations.
5.12.2.10 | Commissioning of installations. |  | 0 | A5.12.2.10 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.2 Security systems | 5.12.2.10 Commissioning of installations.
5.12.3 | Central control/building management systems |  | 0 | A5.12.3 | 2 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.3 Central control/building management systems
5.12.3.1 | Central control/building management systems: details of each type of system to be stated. |  | 0 | A5.12.3.1 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.3 Central control/building management systems | 5.12.3.1 Central control/building management systems: details of each type of system to be stated.
5.12.3.2 | Computer aided facilities manage system: details of each type of system to be stated. |  | 0 | A5.12.3.2 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.3 Central control/building management systems | 5.12.3.2 Computer aided facilities manage system: details of each type of system to be stated.
5.12.3.3 | Testing of installations. |  | 0 | A5.12.3.3 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.3 Central control/building management systems | 5.12.3.3 Testing of installations.
5.12.3.4 | Commissioning of installations. |  | 0 | A5.12.3.4 | 3 | 5 SERVICES | 5.12 Communication, security and control systems | 5.12.3 Central control/building management systems | 5.12.3.4 Commissioning of installations.
5.13 | Specialist installations |  | 0 | A5.13 | 1 | 5 SERVICES | 5.13 Specialist installations
5.13.1 | Specialist piped supply installations |  | 0 | A5.13.1 | 2 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations
5.13.1.1 | Medical and laboratory gas supply systems: details of each type of system to be stated. |  | 0 | A5.13.1.1 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.1 Medical and laboratory gas supply systems: details of each type of system to be stated.
5.13.1.2 | Centralised vacuum cleaning systems: details of each type of system to be stated. |  | 0 | A5.13.1.2 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.2 Centralised vacuum cleaning systems: details of each type of system to be stated.
5.13.1.3 | Treated water systems: details of each type of system to be stated. |  | 0 | A5.13.1.3 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.3 Treated water systems: details of each type of system to be stated.
5.13.1.4 | Swimming pool water treatment systems: details of each type of system to be stated. |  | 0 | A5.13.1.4 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.4 Swimming pool water treatment systems: details of each type of system to be stated.
5.13.1.5 | Compressed air systems: details of each type of system to be stated. |  | 0 | A5.13.1.5 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.5 Compressed air systems: details of each type of system to be stated.
5.13.1.6 | Vacuum installations: details of each type of system to be stated. |  | 0 | A5.13.1.6 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.6 Vacuum installations: details of each type of system to be stated.
5.13.1.7 | Other specialist piped supply systems: details of each type of system to be stated. |  | 0 | A5.13.1.7 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.7 Other specialist piped supply systems: details of each type of system to be stated.
5.13.1.8 | Testing of installations. |  | 0 | A5.13.1.8 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.8 Testing of installations.
5.13.1.9 | Commissioning of installations. |  | 0 | A5.13.1.9 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.1 Specialist piped supply installations | 5.13.1.9 Commissioning of installations.
5.13.2 | Specialist refrigeration systems |  | 0 | A5.13.2 | 2 | 5 SERVICES | 5.13 Specialist installations | 5.13.2 Specialist refrigeration systems
5.13.2.1 | Cold rooms: details of each type of system to be stated. |  | 0 | A5.13.2.1 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.2 Specialist refrigeration systems | 5.13.2.1 Cold rooms: details of each type of system to be stated.
5.13.2.2 | Ice pads: details to be stated. |  | 0 | A5.13.2.2 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.2 Specialist refrigeration systems | 5.13.2.2 Ice pads: details to be stated.
5.13.2.3 | Other specialist refrigeration systems: details of each type of system to be stated. |  | 0 | A5.13.2.3 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.2 Specialist refrigeration systems | 5.13.2.3 Other specialist refrigeration systems: details of each type of system to be stated.
5.13.2.4 | Testing of installations. |  | 0 | A5.13.2.4 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.2 Specialist refrigeration systems | 5.13.2.4 Testing of installations.
5.13.2.5 | Commissioning of installations. |  | 0 | A5.13.2.5 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.2 Specialist refrigeration systems | 5.13.2.5 Commissioning of installations.
5.13.3 | Specialist mechanical installations |  | 0 | A5.13.3 | 2 | 5 SERVICES | 5.13 Specialist installations | 5.13.3 Specialist mechanical installations
5.13.3.1 | Other specialist installations: details of each type of system to be stated. |  | 0 | A5.13.3.1 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.3 Specialist mechanical installations | 5.13.3.1 Other specialist installations: details of each type of system to be stated.
5.13.3.2 | Testing of installations. |  | 0 | A5.13.3.2 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.3 Specialist mechanical installations | 5.13.3.2 Testing of installations.
5.13.3.3 | Commissioning of installations. |  | 0 | A5.13.3.3 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.3 Specialist mechanical installations | 5.13.3.3 Commissioning of installations.
5.13.4 | Specialist electrical/electronic installations |  | 0 | A5.13.4 | 2 | 5 SERVICES | 5.13 Specialist installations | 5.13.4 Specialist electrical/electronic installations
5.13.4.1 | Specialist electrical and electronic installation or and systems: details to be stated. |  | 0 | A5.13.4.1 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.4 Specialist electrical/electronic installations | 5.13.4.1 Specialist electrical and electronic installation or and systems: details to be stated.
5.13.4.2 | Testing of installations. |  | 0 | A5.13.4.2 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.4 Specialist electrical/electronic installations | 5.13.4.2 Testing of installations.
5.13.4.3 | Commissioning of installations. |  | 0 | A5.13.4.3 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.4 Specialist electrical/electronic installations | 5.13.4.3 Commissioning of installations.
5.13.5 | Water features |  | 0 | A5.13.5 | 2 | 5 SERVICES | 5.13 Specialist installations | 5.13.5 Water features
5.13.5.1 | Water Feature: details to be stated. |  | 0 | A5.13.5.1 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.5 Water features | 5.13.5.1 Water Feature: details to be stated.
5.13.5.2 | Testing of installations. |  | 0 | A5.13.5.2 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.5 Water features | 5.13.5.2 Testing of installations.
5.13.5.3 | Commissioning of installations. |  | 0 | A5.13.5.3 | 3 | 5 SERVICES | 5.13 Specialist installations | 5.13.5 Water features | 5.13.5.3 Commissioning of installations.
5.14 | Builder's work in connection with services |  | 0 | A5.14 | 1 | 5 SERVICES | 5.14 Builder's work in connection with services
5.14.1 | Builder's work in connection with services |  | 0 | A5.14.1 | 2 | 5 SERVICES | 5.14 Builder's work in connection with services | 5.14.1 Builder's work in connection with services
5.14.1.1 | Builder's work in general areas: details to be stated. |  | 0 | A5.14.1.1 | 3 | 5 SERVICES | 5.14 Builder's work in connection with services | 5.14.1 Builder's work in connection with services | 5.14.1.1 Builder's work in general areas: details to be stated.
5.14.1.2 | Builder's work to landlord areas: details to be stated. |  | 0 | A5.14.1.2 | 3 | 5 SERVICES | 5.14 Builder's work in connection with services | 5.14.1 Builder's work in connection with services | 5.14.1.2 Builder's work to landlord areas: details to be stated.
5.14.1.3 | Builder's work to plant rooms: details to be stated. |  | 0 | A5.14.1.3 | 3 | 5 SERVICES | 5.14 Builder's work in connection with services | 5.14.1 Builder's work in connection with services | 5.14.1.3 Builder's work to plant rooms: details to be stated.
5.14.1.4 | Large plant and equipment bases: details, including overall size (in m), to be stated. |  | 0 | A5.14.1.4 | 3 | 5 SERVICES | 5.14 Builder's work in connection with services | 5.14.1 Builder's work in connection with services | 5.14.1.4 Large plant and equipment bases: details, including overall size (in m), to be stated.
5.14.1.5 | Fuel bunds: details, including construction and overall size (in m), to be stated. |  | 0 | A5.14.1.5 | 3 | 5 SERVICES | 5.14 Builder's work in connection with services | 5.14.1 Builder's work in connection with services | 5.14.1.5 Fuel bunds: details, including construction and overall size (in m), to be stated.
6 | PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 0 | A6 | 0 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS
6.1.1 | Complete buildings |  | 0 | A6.1.1 | 2 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.1 Complete buildings
6.1.1.1 | Prefabricated modular buildings: details to be stated. |  | 0 | A6.1.1.1 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.1 Complete buildings | 6.1.1.1 Prefabricated modular buildings: details to be stated.
6.1.1.2 | On-site testing of installations. |  | 0 | A6.1.1.2 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.1 Complete buildings | 6.1.1.2 On-site testing of installations.
6.1.1.3 | On-site commissioning of installations. |  | 0 | A6.1.1.3 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.1 Complete buildings | 6.1.1.3 On-site commissioning of installations.
6.1.2 | Building units |  | 0 | A6.1.2 | 2 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.2 Building units
6.1.2.1 | Prefabricated room units, including type of unit, GIFA of unit (in m2), construction of unit and content of units, to be stated. |  | 0 | A6.1.2.1 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.2 Building units | 6.1.2.1 Prefabricated room units, including type of unit, GIFA of unit (in m2), construction of unit and content of units, to be stated.
6.1.2.2 | On-site testing of installations. |  | 0 | A6.1.2.2 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.2 Building units | 6.1.2.2 On-site testing of installations.
6.1.2.3 | On-site commissioning of installations. |  | 0 | A6.1.2.3 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.2 Building units | 6.1.2.3 On-site commissioning of installations.
6.1.3 | Pods |  | 0 | A6.1.3 | 2 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.3 Pods
6.1.3.1 | Prefabricated bathroom pods: details to be stated. |  | 0 | A6.1.3.1 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.3 Pods | 6.1.3.1 Prefabricated bathroom pods: details to be stated.
6.1.3.2 | Prefabricated toilet pods: details to be stated. |  | 0 | A6.1.3.2 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.3 Pods | 6.1.3.2 Prefabricated toilet pods: details to be stated.
6.1.3.3 | Prefabricated shower room pods: details to be stated. |  | 0 | A6.1.3.3 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.3 Pods | 6.1.3.3 Prefabricated shower room pods: details to be stated.
6.1.3.4 | On-site testing of installations. |  | 0 | A6.1.3.4 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.3 Pods | 6.1.3.4 On-site testing of installations.
6.1.3.5 | On-site commissioning of installations. |  | 0 | A6.1.3.5 | 3 | 6 PREFABRICATED BUILDINGS AND BUILDING UNITS |  | 6.1.3 Pods | 6.1.3.5 On-site commissioning of installations.
7 | WORK TO EXISTING BUILDINGS |  | 0 | A7 | 0 | 7 WORK TO EXISTING BUILDINGS
7.1 | Minor demolition and alteration works |  | 0 | A7.1 | 1 | 7 WORK TO EXISTING BUILDINGS | 7.1 Minor demolition and alteration works
7.1.1 | Minor demolition and alteration works |  | 0 | A7.1.1 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.1 Minor demolition and alteration works | 7.1.1 Minor demolition and alteration works
7.1.1.1 | Spot items: details to be stated. |  | 0 | A7.1.1.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.1 Minor demolition and alteration works | 7.1.1 Minor demolition and alteration works | 7.1.1.1 Spot items: details to be stated.
7.1.1.2 | Minor demolition works: details to be stated. |  | 0 | A7.1.1.2 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.1 Minor demolition and alteration works | 7.1.1 Minor demolition and alteration works | 7.1.1.2 Minor demolition works: details to be stated.
7.1.1.3 | Removal: details to be stated. |  | 0 | A7.1.1.3 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.1 Minor demolition and alteration works | 7.1.1 Minor demolition and alteration works | 7.1.1.3 Removal: details to be stated.
7.1.1.4 | Alteration works: details to be stated. |  | 0 | A7.1.1.4 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.1 Minor demolition and alteration works | 7.1.1 Minor demolition and alteration works | 7.1.1.4 Alteration works: details to be stated.
7.2 | Repairs to existing services |  | 0 | A7.2 | 1 | 7 WORK TO EXISTING BUILDINGS | 7.2 Repairs to existing services
7.2.1 | Repairs to existing services |  | 0 | A7.2.1 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.2 Repairs to existing services | 7.2.1 Repairs to existing services
7.2.1.1 | Equipment/plant repairs: details to be stated. |  | 0 | A7.2.1.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.2 Repairs to existing services | 7.2.1 Repairs to existing services | 7.2.1.1 Equipment/plant repairs: details to be stated.
7.2.1.2 | Overhauling services installations/systems: details to be stated. |  | 0 | A7.2.1.2 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.2 Repairs to existing services | 7.2.1 Repairs to existing services | 7.2.1.2 Overhauling services installations/systems: details to be stated.
7.2.1.3 | Testing of equipment/plant and/or installations. |  | 0 | A7.2.1.3 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.2 Repairs to existing services | 7.2.1 Repairs to existing services | 7.2.1.3 Testing of equipment/plant and/or installations.
7.2.1.4 | Commissioning of equipment/plant and/or installations. |  | 0 | A7.2.1.4 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.2 Repairs to existing services | 7.2.1 Repairs to existing services | 7.2.1.4 Commissioning of equipment/plant and/or installations.
7.3 | Damp-proof courses/fungus and beetle eradication |  | 0 | A7.3 | 1 | 7 WORK TO EXISTING BUILDINGS | 7.3 Damp-proof courses/fungus and beetle eradication
7.3.1 | Damp-proof courses |  | 0 | A7.3.1 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.3 Damp-proof courses/fungus and beetle eradication | 7.3.1 Damp-proof courses
7.3.1.1 | Damp-proof courses: details to be stated. |  | 0 | A7.3.1.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.3 Damp-proof courses/fungus and beetle eradication | 7.3.1 Damp-proof courses | 7.3.1.1 Damp-proof courses: details to be stated.
7.3.2 | Fungus/beetle eradication |  | 0 | A7.3.2 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.3 Damp-proof courses/fungus and beetle eradication | 7.3.2 Fungus/beetle eradication
7.3.2.1 | Eradication treatment: details to be stated. |  | 0 | A7.3.2.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.3 Damp-proof courses/fungus and beetle eradication | 7.3.2 Fungus/beetle eradication | 7.3.2.1 Eradication treatment: details to be stated.
7.4 | Facade retention |  | 0 | A7.4 | 1 | 7 WORK TO EXISTING BUILDINGS | 7.4 Facade retention
7.4.1 | Facade retention |  | 0 | A7.4.1 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.4 Facade retention | 7.4.1 Facade retention
7.4.1.1 | Support structures: details to be stated. |  | 0 | A7.4.1.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.4 Facade retention | 7.4.1 Facade retention | 7.4.1.1 Support structures: details to be stated.
7.4.1.2 | Periodic technical inspections of support structures: details to be stated. |  | 0 | A7.4.1.2 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.4 Facade retention | 7.4.1 Facade retention | 7.4.1.2 Periodic technical inspections of support structures: details to be stated.
7.4.1.3 | Removing support structures: details to be stated. |  | 0 | A7.4.1.3 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.4 Facade retention | 7.4.1 Facade retention | 7.4.1.3 Removing support structures: details to be stated.
7.5 | Cleaning existing surfaces |  | 0 | A7.5 | 1 | 7 WORK TO EXISTING BUILDINGS | 7.5 Cleaning existing surfaces
7.5.1 | Cleaning |  | 0 | A7.5.1 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.5 Cleaning existing surfaces | 7.5.1 Cleaning
7.5.1.1 | Cleaning existing surfaces: details to be stated. |  | 0 | A7.5.1.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.5 Cleaning existing surfaces | 7.5.1 Cleaning | 7.5.1.1 Cleaning existing surfaces: details to be stated.
7.5.2 | Protective coatings |  | 0 | A7.5.2 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.5 Cleaning existing surfaces | 7.5.2 Protective coatings
7.5.2.1 | Protective coatings to existing surfaces: details to be stated. |  | 0 | A7.5.2.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.5 Cleaning existing surfaces | 7.5.2 Protective coatings | 7.5.2.1 Protective coatings to existing surfaces: details to be stated.
7.6 | Renovation works |  | 0 | A7.6 | 1 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works
7.6.1 | Masonry repairs |  | 0 | A7.6.1 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.1 Masonry repairs
7.6.1.1 | Masonry repairs: details to be stated. |  | 0 | A7.6.1.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.1 Masonry repairs | 7.6.1.1 Masonry repairs: details to be stated.
7.6.2 | Concrete repairs |  | 0 | A7.6.2 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.2 Concrete repairs
7.6.2.1 | Concrete repairs: details to be stated. |  | 0 | A7.6.2.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.2 Concrete repairs | 7.6.2.1 Concrete repairs: details to be stated.
7.6.3 | Metal repairs |  | 0 | A7.6.3 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.3 Metal repairs
7.6.3.1 | Metal repairs: details to be stated. |  | 0 | A7.6.3.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.3 Metal repairs | 7.6.3.1 Metal repairs: details to be stated.
7.6.4 | Timber repairs |  | 0 | A7.6.4 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.4 Timber repairs
7.6.4.1 | Timber repairs: details to be stated. |  | 0 | A7.6.4.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.4 Timber repairs | 7.6.4.1 Timber repairs: details to be stated.
7.6.5 | Plastics repairs |  | 0 | A7.6.5 | 2 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.5 Plastics repairs
7.6.5.1 | Plastics repairs: details to be stated. |  | 0 | A7.6.5.1 | 3 | 7 WORK TO EXISTING BUILDINGS | 7.6 Renovation works | 7.6.5 Plastics repairs | 7.6.5.1 Plastics repairs: details to be stated.
8 | EXTERNAL WORKS |  | 0 | A8 | 0 | 8 EXTERNAL WORKS
8.1 | Site preparation works |  | 0 | A8.1 | 1 | 8 EXTERNAL WORKS | 8.1 Site preparation works
8.1.1 | Site clearance |  | 0 | A8.1.1 | 2 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.1 Site clearance
8.1.1.1 | Clearing vegetation: details to be stated. | 50000 | 53169 | A8.1.1.1 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.1 Site clearance | 8.1.1.1 Clearing vegetation: details to be stated.
8.1.1.2 | Taking down trees: details to be stated. | 750 | 679 | A8.1.1.2 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.1 Site clearance | 8.1.1.2 Taking down trees: details to be stated.
8.1.1.3 | Removing tree stumps and roots: details to be stated. |  | 0 | A8.1.1.3 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.1 Site clearance | 8.1.1.3 Removing tree stumps and roots: details to be stated.
8.1.1.4 | Tree protection: details to be stated. |  | 0 | A8.1.1.4 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.1 Site clearance | 8.1.1.4 Tree protection: details to be stated.
8.1.1.5 | Minor demolition works: details to be stated. |  | 0 | A8.1.1.5 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.1 Site clearance | 8.1.1.5 Minor demolition works: details to be stated.
8.1.1.6 | Applying herbicides: details to be stated. |  | 0 | A8.1.1.6 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.1 Site clearance | 8.1.1.6 Applying herbicides: details to be stated.
8.1.2 | Preparatory groundworks |  | 0 | A8.1.2 | 2 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks
8.1.2.1 | Forming new site contours and adjusting existing site levels: details to be stated. | 75000 | 79717 | A8.1.2.1 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks | 8.1.2.1 Forming new site contours and adjusting existing site levels: details to be stated.
8.1.2.2 | Breaking out existing substructures: details to be stated. |  | 0 | A8.1.2.2 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks | 8.1.2.2 Breaking out existing substructures: details to be stated.
8.1.2.3 | Breaking out existing hard pavings: details to be stated. |  | 0 | A8.1.2.3 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks | 8.1.2.3 Breaking out existing hard pavings: details to be stated.
8.1.2.4 | Grubbing up old drainage pipelines: details to be stated. |  | 0 | A8.1.2.4 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks | 8.1.2.4 Grubbing up old drainage pipelines: details to be stated.
8.1.2.5 | Grubbing up old manholes and the like: details to be stated. |  | 0 | A8.1.2.5 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks | 8.1.2.5 Grubbing up old manholes and the like: details to be stated.
8.1.2.6 | Filling disused manholes and the like: details to be stated. |  | 0 | A8.1.2.6 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks | 8.1.2.6 Filling disused manholes and the like: details to be stated.
8.1.2.7 | Removing existing underground storage tanks, including disposal: details to be stated. |  | 0 | A8.1.2.7 | 3 | 8 EXTERNAL WORKS | 8.1 Site preparation works | 8.1.2 Preparatory groundworks | 8.1.2.7 Removing existing underground storage tanks, including disposal: details to be stated.
8.2 | Roads, paths, pavings and surfacings |  | 0 | A8.2 | 1 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings
8.2.1 | Roads, paths and pavings |  | 0 | A8.2.1 | 2 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings
8.2.1.1 | Roads: details, including width, to be stated. | 20000 | 20587 | A8.2.1.1 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.1 Roads: details, including width, to be stated.
8.2.1.2 | Paths: details, including width, to be stated. |  | 0 | A8.2.1.2 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.2 Paths: details, including width, to be stated.
8.2.1.3 | Paved areas, hardstandings and the like: details to be stated. |  | 0 | A8.2.1.3 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.3 Paved areas, hardstandings and the like: details to be stated.
8.2.1.4 | Roundabouts: details to be stated. |  | 0 | A8.2.1.4 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.4 Roundabouts: details to be stated.
8.2.1.5 | Road crossings: details to be stated. |  | 0 | A8.2.1.5 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.5 Road crossings: details to be stated.
8.2.1.6 | Steps: details to be stated. |  | 0 | A8.2.1.6 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.6 Steps: details to be stated.
8.2.1.7 | Ramps: details to be stated. |  | 0 | A8.2.1.7 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.7 Ramps: details to be stated.
8.2.1.8 | Traffic calming JHLessories: details to be stated. |  | 0 | A8.2.1.8 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.8 Traffic calming JHLessories: details to be stated.
8.2.1.9 | Tree grilles: details to be stated. |  | 0 | A8.2.1.9 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.9 Tree grilles: details to be stated.
8.2.1.10 | Vehicle protection barriers: details to be stated. |  | 0 | A8.2.1.10 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.10 Vehicle protection barriers: details to be stated.
8.2.1.11 | Bumpers: details to be stated. |  | 0 | A8.2.1.11 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.11 Bumpers: details to be stated.
8.2.1.12 | Pavement markings: details to be stated. |  | 0 | A8.2.1.12 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.12 Pavement markings: details to be stated.
8.2.1.13 | Repairs to existing roads, paths and pavings: details to be stated. |  | 0 | A8.2.1.13 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.1 Roads, paths and pavings | 8.2.1.13 Repairs to existing roads, paths and pavings: details to be stated.
8.2.2 | Special surfacings and pavings |  | 0 | A8.2.2 | 2 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.2 Special surfacings and pavings
8.2.2.1 | Surfacings and pavings: details to be stated. |  | 0 | A8.2.2.1 | 3 | 8 EXTERNAL WORKS | 8.2 Roads, paths, pavings and surfacings | 8.2.2 Special surfacings and pavings | 8.2.2.1 Surfacings and pavings: details to be stated.
8.3 | Soft landscapes, planting and irrigation systems |  | 0 | A8.3 | 1 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems
8.3.1 | Seeding and turfing |  | 0 | A8.3.1 | 2 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.1 Seeding and turfing
8.3.1.1 | Grassed areas: details to be stated. | 60000 | 61612 | A8.3.1.1 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.1 Seeding and turfing | 8.3.1.1 Grassed areas: details to be stated.
8.3.1.2 | Reinforced grass proprietary systems: details to be stated. |  | 0 | A8.3.1.2 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.1 Seeding and turfing | 8.3.1.2 Reinforced grass proprietary systems: details to be stated.
8.3.1.3 | Marking out of grass sports pitches: details to be stated. |  | 0 | A8.3.1.3 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.1 Seeding and turfing | 8.3.1.3 Marking out of grass sports pitches: details to be stated.
8.3.1.4 | Work to existing grassed areas: details to be stated. |  | 0 | A8.3.1.4 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.1 Seeding and turfing | 8.3.1.4 Work to existing grassed areas: details to be stated.
8.3.1.5 | Maintenance of grassed areas: details, including time period (weeks) to be stated. |  | 0 | A8.3.1.5 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.1 Seeding and turfing | 8.3.1.5 Maintenance of grassed areas: details, including time period (weeks) to be stated.
8.3.2 | External planting |  | 0 | A8.3.2 | 2 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting
8.3.2.1 | Planting: details to be stated. |  | 0 | A8.3.2.1 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.1 Planting: details to be stated.
8.3.2.2 | Planting reed beds: details to be stated. |  | 0 | A8.3.2.2 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.2 Planting reed beds: details to be stated.
8.3.2.3 | Hedges: details to be stated. |  | 0 | A8.3.2.3 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.3 Hedges: details to be stated.
8.3.2.4 | Trees: details to be stated. |  | 0 | A8.3.2.4 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.4 Trees: details to be stated.
8.3.2.5 | Woodland planting: details to be stated. |  | 0 | A8.3.2.5 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.5 Woodland planting: details to be stated.
8.3.2.6 | Tree surgery, thinning and pruning: details to be stated. |  | 0 | A8.3.2.6 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.6 Tree surgery, thinning and pruning: details to be stated.
8.3.2.7 | Maintenance work to plants and shrubs and planting beds: details, including time period (weeks), to be stated. |  | 0 | A8.3.2.7 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.7 Maintenance work to plants and shrubs and planting beds: details, including time period (weeks), to be stated.
8.3.2.8 | Maintenance work to trees: details, including number of occasions and time period (weeks), to be stated. |  | 0 | A8.3.2.8 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.8 Maintenance work to trees: details, including number of occasions and time period (weeks), to be stated.
8.3.2.9 | Maintenance work to hedges: details, including time period (weeks), to be stated. |  | 0 | A8.3.2.9 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.2 External planting | 8.3.2.9 Maintenance work to hedges: details, including time period (weeks), to be stated.
8.3.3 | Irrigation systems |  | 0 | A8.3.3 | 2 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.3 Irrigation systems
8.3.3.1 | Irrigation systems: details to be stated. |  | 0 | A8.3.3.1 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.3 Irrigation systems | 8.3.3.1 Irrigation systems: details to be stated.
8.3.3.2 | Testing of installations. |  | 0 | A8.3.3.2 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.3 Irrigation systems | 8.3.3.2 Testing of installations.
8.3.3.3 | Commissioning of installations. |  | 0 | A8.3.3.3 | 3 | 8 EXTERNAL WORKS | 8.3 Soft landscapes, planting and irrigation systems | 8.3.3 Irrigation systems | 8.3.3.3 Commissioning of installations.
8.4 | Fencing, railings and walls |  | 0 | A8.4 | 1 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls
8.4.1 | Fencing and railings |  | 0 | A8.4.1 | 2 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.1 Fencing and railings
8.4.1.1 | Fencing: details, including height (m), to be stated. | 67500 | 72179 | A8.4.1.1 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.1 Fencing and railings | 8.4.1.1 Fencing: details, including height (m), to be stated.
8.4.1.2 | Railings: details, including height (m), to be stated. |  | 0 | A8.4.1.2 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.1 Fencing and railings | 8.4.1.2 Railings: details, including height (m), to be stated.
8.4.1.3 | Gates: details to be stated. | 2250 | 2206 | A8.4.1.3 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.1 Fencing and railings | 8.4.1.3 Gates: details to be stated.
8.4.2 | Walls and screens |  | 0 | A8.4.2 | 2 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.2 Walls and screens
8.4.2.1 | Walls: details, including height (m), to be stated. |  | 0 | A8.4.2.1 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.2 Walls and screens | 8.4.2.1 Walls: details, including height (m), to be stated.
8.4.2.2 | Screens: details, including height (m), to be stated. |  | 0 | A8.4.2.2 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.2 Walls and screens | 8.4.2.2 Screens: details, including height (m), to be stated.
8.4.2.3 | Gates: details to be stated. |  | 0 | A8.4.2.3 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.2 Walls and screens | 8.4.2.3 Gates: details to be stated.
8.4.3 | Retaining walls |  | 0 | A8.4.3 | 2 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.3 Retaining walls
8.4.3.1 | Retaining walls: details, including height (m) above ground, to be stated. |  | 0 | A8.4.3.1 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.3 Retaining walls | 8.4.3.1 Retaining walls: details, including height (m) above ground, to be stated.
8.4.4 | Barriers and guardrails |  | 0 | A8.4.4 | 2 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.4 Barriers and guardrails
8.4.4.1 | Vehicle restraint systems: details to be stated. |  | 0 | A8.4.4.1 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.4 Barriers and guardrails | 8.4.4.1 Vehicle restraint systems: details to be stated.
8.4.4.2 | Pedestrian restraint systems: details to be stated. |  | 0 | A8.4.4.2 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.4 Barriers and guardrails | 8.4.4.2 Pedestrian restraint systems: details to be stated.
8.4.4.3 | Vehicle and pedestrian control barriers and gates: details to be stated. |  | 0 | A8.4.4.3 | 3 | 8 EXTERNAL WORKS | 8.4 Fencing, railings and walls | 8.4.4 Barriers and guardrails | 8.4.4.3 Vehicle and pedestrian control barriers and gates: details to be stated.
8.5 | External fixtures |  | 0 | A8.5 | 1 | 8 EXTERNAL WORKS | 8.5 External fixtures
8.5.1 | Site/street furniture and equipment |  | 0 | A8.5.1 | 2 | 8 EXTERNAL WORKS | 8.5 External fixtures | 8.5.1 Site/street furniture and equipment
8.5.1.1 | Component: details to be stated. |  | 0 | A8.5.1.1 | 3 | 8 EXTERNAL WORKS | 8.5 External fixtures | 8.5.1 Site/street furniture and equipment | 8.5.1.1 Component: details to be stated.
8.5.2 | Ornamental features |  | 0 | A8.5.2 | 2 | 8 EXTERNAL WORKS | 8.5 External fixtures | 8.5.2 Ornamental features
8.5.2.1 | Water features: details to be stated. |  | 0 | A8.5.2.1 | 3 | 8 EXTERNAL WORKS | 8.5 External fixtures | 8.5.2 Ornamental features | 8.5.2.1 Water features: details to be stated.
8.5.2.2 | Other features: details to be stated. |  | 0 | A8.5.2.2 | 3 | 8 EXTERNAL WORKS | 8.5 External fixtures | 8.5.2 Ornamental features | 8.5.2.2 Other features: details to be stated.
8.6 | External drainage |  | 0 | A8.6 | 1 | 8 EXTERNAL WORKS | 8.6 External drainage
8.6.1 | Surface water and foul water drainage |  | 0 | A8.6.1 | 2 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage
8.6.1.1 | Connections to statutory undertaker's sewers: details to be stated. | 5000 | 4646 | A8.6.1.1 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.1 Connections to statutory undertaker's sewers: details to be stated.
8.6.1.2 | Drainage runs; below ground: details, including depth of trench (m) and nominal size of pipe (mm), to be stated. |  | 0 | A8.6.1.2 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.2 Drainage runs; below ground: details, including depth of trench (m) and nominal size of pipe (mm), to be stated.
8.6.1.3 | Drainage runs; above ground: details, including height above ground (m), nominal size of pipe (mm), to be stated. |  | 0 | A8.6.1.3 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.3 Drainage runs; above ground: details, including height above ground (m), nominal size of pipe (mm), to be stated.
8.6.1.4 | Prefabricated channels: details, including nominal size, to be stated. |  | 0 | A8.6.1.4 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.4 Prefabricated channels: details, including nominal size, to be stated.
8.6.1.5 | Manholes and the like: details, including depth (m), to be stated. | 9000 | 8907 | A8.6.1.5 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.5 Manholes and the like: details, including depth (m), to be stated.
8.6.1.6 | Alterations to existing external drainage systems: details to be stated. |  | 0 | A8.6.1.6 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.6 Alterations to existing external drainage systems: details to be stated.
8.6.1.7 | Work to existing manholes or the like: details to be stated. |  | 0 | A8.6.1.7 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.7 Work to existing manholes or the like: details to be stated.
8.6.1.8 | Clearing existing drains: details to be stated. |  | 0 | A8.6.1.8 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.8 Clearing existing drains: details to be stated.
8.6.1.9 | Sealing redundant drains: details to be stated. |  | 0 | A8.6.1.9 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.9 Sealing redundant drains: details to be stated.
8.6.1.10 | Filling disused manholes or the like: details to be stated. |  | 0 | A8.6.1.10 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.10 Filling disused manholes or the like: details to be stated.
8.6.1.11 | Testing of installations. | 1400 | 1352 | A8.6.1.11 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.11 Testing of installations.
8.6.1.12 | Commissioning of installations. | 1400 | 1531 | A8.6.1.12 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.1 Surface water and foul water drainage | 8.6.1.12 Commissioning of installations.
8.6.2 | Ancillary drainage systems |  | 0 | A8.6.2 | 2 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems
8.6.2.1 | Pumping stations: details to be stated. |  | 0 | A8.6.2.1 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.1 Pumping stations: details to be stated.
8.6.2.2 | Ejector stations: details to be stated. |  | 0 | A8.6.2.2 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.2 Ejector stations: details to be stated.
8.6.2.3 | Storage/retention tanks and vessels: details to be stated. |  | 0 | A8.6.2.3 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.3 Storage/retention tanks and vessels: details to be stated.
8.6.2.4 | Sewage treatment systems: details to be stated. |  | 0 | A8.6.2.4 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.4 Sewage treatment systems: details to be stated.
8.6.2.5 | Enzyme systems: details to be stated. |  | 0 | A8.6.2.5 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.5 Enzyme systems: details to be stated.
8.6.2.6 | Sustainable urban drainage schemes: details to be stated. |  | 0 | A8.6.2.6 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.6 Sustainable urban drainage schemes: details to be stated.
8.6.2.7 | Testing of installations. |  | 0 | A8.6.2.7 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.7 Testing of installations.
8.6.2.8 | Commissioning of installations. |  | 0 | A8.6.2.8 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.2 Ancillary drainage systems | 8.6.2.8 Commissioning of installations.
8.6.3 | External chemical, toxic and industrial liquid waste drainage |  | 0 | A8.6.3 | 2 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.3 External chemical, toxic and industrial liquid waste drainage
8.6.3.1 | Drainage runs; below ground: details, including depth of trench (m) and nominal size of pipe (mm), to be stated. |  | 0 | A8.6.3.1 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.3 External chemical, toxic and industrial liquid waste drainage | 8.6.3.1 Drainage runs; below ground: details, including depth of trench (m) and nominal size of pipe (mm), to be stated.
8.6.3.2 | Drainage runs; above ground: details, including height above ground (m) and nominal size of pipe (mm), to be stated. |  | 0 | A8.6.3.2 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.3 External chemical, toxic and industrial liquid waste drainage | 8.6.3.2 Drainage runs; above ground: details, including height above ground (m) and nominal size of pipe (mm), to be stated.
8.6.3.3 | Equipment and plant: details to be stated. |  | 0 | A8.6.3.3 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.3 External chemical, toxic and industrial liquid waste drainage | 8.6.3.3 Equipment and plant: details to be stated.
8.6.3.4 | Testing of installations. |  | 0 | A8.6.3.4 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.3 External chemical, toxic and industrial liquid waste drainage | 8.6.3.4 Testing of installations.
8.6.3.5 | Commissioning of installations. |  | 0 | A8.6.3.5 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.3 External chemical, toxic and industrial liquid waste drainage | 8.6.3.5 Commissioning of installations.
8.6.4 | Land drainage |  | 0 | A8.6.4 | 2 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.4 Land drainage
8.6.4.1 | Drainage runs; below ground: details, including depth of trench (m) and nominal size of pipe (mm), to be stated. |  | 0 | A8.6.4.1 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.4 Land drainage | 8.6.4.1 Drainage runs; below ground: details, including depth of trench (m) and nominal size of pipe (mm), to be stated.
8.6.4.2 | Manholes and the like: details, including depth (m), to be stated. |  | 0 | A8.6.4.2 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.4 Land drainage | 8.6.4.2 Manholes and the like: details, including depth (m), to be stated.
8.6.4.3 | Drainage blankets: details to be stated. |  | 0 | A8.6.4.3 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.4 Land drainage | 8.6.4.3 Drainage blankets: details to be stated.
8.6.4.4 | Land drainage to parkland: details, including centres of main runs (m) and laterals (m), to be stated. |  | 0 | A8.6.4.4 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.4 Land drainage | 8.6.4.4 Land drainage to parkland: details, including centres of main runs (m) and laterals (m), to be stated.
8.6.4.5 | Testing of installations. |  | 0 | A8.6.4.5 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.4 Land drainage | 8.6.4.5 Testing of installations.
8.6.4.6 | Commissioning of installations. |  | 0 | A8.6.4.6 | 3 | 8 EXTERNAL WORKS | 8.6 External drainage | 8.6.4 Land drainage | 8.6.4.6 Commissioning of installations.
8.7 | External services |  | 0 | A8.7 | 1 | 8 EXTERNAL WORKS | 8.7 External services
8.7.1 | Water mains supply |  | 0 | A8.7.1 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply
8.7.1.1 | Connections to statutory undertaker's water main: details to be stated. | 5000 | 5160 | A8.7.1.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply | 8.7.1.1 Connections to statutory undertaker's water main: details to be stated.
8.7.1.2 | Connections to external plant and equipment: details to be stated. |  | 0 | A8.7.1.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply | 8.7.1.2 Connections to external plant and equipment: details to be stated.
8.7.1.3 | Service runs: details to be stated. |  | 0 | A8.7.1.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply | 8.7.1.3 Service runs: details to be stated.
8.7.1.4 | Rainwater harvesting systems: details, including the number of collection points (nr), to be stated. |  | 0 | A8.7.1.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply | 8.7.1.4 Rainwater harvesting systems: details, including the number of collection points (nr), to be stated.
8.7.1.5 | Grey water systems: details, including the number of collection points (nr), to be stated. |  | 0 | A8.7.1.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply | 8.7.1.5 Grey water systems: details, including the number of collection points (nr), to be stated.
8.7.1.6 | Testing of installations. | 250 | 256 | A8.7.1.6 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply | 8.7.1.6 Testing of installations.
8.7.1.7 | Commissioning of installations. | 250 | 254 | A8.7.1.7 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.1 Water mains supply | 8.7.1.7 Commissioning of installations.
8.7.2 | Electricity mains supply |  | 0 | A8.7.2 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.2 Electricity mains supply
8.7.2.1 | Connections to statutory undertaker's electricity main: details to be stated. | 1500 | 1391 | A8.7.2.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.2 Electricity mains supply | 8.7.2.1 Connections to statutory undertaker's electricity main: details to be stated.
8.7.2.2 | Service runs: details to be stated. | 7000 | 6562 | A8.7.2.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.2 Electricity mains supply | 8.7.2.2 Service runs: details to be stated.
8.7.2.3 | Transformer sub-stations: details to be stated. |  | 0 | A8.7.2.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.2 Electricity mains supply | 8.7.2.3 Transformer sub-stations: details to be stated.
8.7.2.4 | External electricity generation installation/plant: details to be stated. |  | 0 | A8.7.2.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.2 Electricity mains supply | 8.7.2.4 External electricity generation installation/plant: details to be stated.
8.7.3 | External transformation devices |  | 0 | A8.7.3 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.3 External transformation devices
8.7.3.1 | Wind turbines: details to be stated. |  | 0 | A8.7.3.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.3 External transformation devices | 8.7.3.1 Wind turbines: details to be stated.
8.7.3.2 | Photovoltaic devices: details, including surface area of units (m2), to be stated. |  | 0 | A8.7.3.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.3 External transformation devices | 8.7.3.2 Photovoltaic devices: details, including surface area of units (m2), to be stated.
8.7.3.3 | Other transformation devices: details to be stated. |  | 0 | A8.7.3.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.3 External transformation devices | 8.7.3.3 Other transformation devices: details to be stated.
8.7.3.4 | Testing of installations. | 0 | 0 | A8.7.3.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.3 External transformation devices | 8.7.3.4 Testing of installations.
8.7.3.5 | Commissioning of installations. |  | 0 | A8.7.3.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.3 External transformation devices | 8.7.3.5 Commissioning of installations.
8.7.4 | Electricity distribution to external plant and equipment |  | 0 | A8.7.4 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.4 Electricity distribution to external plant and equipment
8.7.4.1 | Connections to external plant or equipment: details to be stated. |  | 0 | A8.7.4.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.4 Electricity distribution to external plant and equipment | 8.7.4.1 Connections to external plant or equipment: details to be stated.
8.7.4.2 | Connections to external equipment: details to be stated. |  | 0 | A8.7.4.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.4 Electricity distribution to external plant and equipment | 8.7.4.2 Connections to external equipment: details to be stated.
8.7.4.3 | Service runs: details to be stated. |  | 0 | A8.7.4.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.4 Electricity distribution to external plant and equipment | 8.7.4.3 Service runs: details to be stated.
8.7.4.4 | Testing of installations. |  | 0 | A8.7.4.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.4 Electricity distribution to external plant and equipment | 8.7.4.4 Testing of installations.
8.7.4.5 | Commissioning of installations. |  | 0 | A8.7.4.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.4 Electricity distribution to external plant and equipment | 8.7.4.5 Commissioning of installations.
8.7.5 | Gas mains supply |  | 0 | A8.7.5 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.5 Gas mains supply
8.7.5.1 | Connections to statutory undertaker's gas main: details to be stated. | 1000 | 1009 | A8.7.5.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.5 Gas mains supply | 8.7.5.1 Connections to statutory undertaker's gas main: details to be stated.
8.7.5.2 | Service runs: details to be stated. | 25000 | 23567 | A8.7.5.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.5 Gas mains supply | 8.7.5.2 Service runs: details to be stated.
8.7.5.3 | Governing stations: details to be stated. | 1300 | 1207 | A8.7.5.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.5 Gas mains supply | 8.7.5.3 Governing stations: details to be stated.
8.7.5.4 | Testing of installations. | 1300 | 1330 | A8.7.5.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.5 Gas mains supply | 8.7.5.4 Testing of installations.
8.7.5.5 | Commissioning of installations. | 1300 | 1252 | A8.7.5.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.5 Gas mains supply | 8.7.5.5 Commissioning of installations.
8.7.6 | Telecommunications and other communication system connections |  | 0 | A8.7.6 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.6 Telecommunications and other communication system connections
8.7.6.1 | Telecommunication connections: details to be stated. |  | 0 | A8.7.6.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.6 Telecommunications and other communication system connections | 8.7.6.1 Telecommunication connections: details to be stated.
8.7.6.2 | Cable television connections: details to be stated. |  | 0 | A8.7.6.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.6 Telecommunications and other communication system connections | 8.7.6.2 Cable television connections: details to be stated.
8.7.6.3 | Other communication connections: details to be stated. |  | 0 | A8.7.6.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.6 Telecommunications and other communication system connections | 8.7.6.3 Other communication connections: details to be stated.
8.7.6.4 | Service runs: details to be stated. |  | 0 | A8.7.6.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.6 Telecommunications and other communication system connections | 8.7.6.4 Service runs: details to be stated.
8.7.6.5 | Testing of installations. |  | 0 | A8.7.6.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.6 Telecommunications and other communication system connections | 8.7.6.5 Testing of installations.
8.7.6.6 | Commissioning of installations. |  | 0 | A8.7.6.6 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.6 Telecommunications and other communication system connections | 8.7.6.6 Commissioning of installations.
8.7.7 | External fuel storage and piped distribution systems |  | 0 | A8.7.7 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.7 External fuel storage and piped distribution systems
8.7.7.1 | Fuel storage and piped distribution systems: details to be stated. |  | 0 | A8.7.7.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.7 External fuel storage and piped distribution systems | 8.7.7.1 Fuel storage and piped distribution systems: details to be stated.
8.7.7.2 | Service runs: details to be stated. |  | 0 | A8.7.7.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.7 External fuel storage and piped distribution systems | 8.7.7.2 Service runs: details to be stated.
8.7.7.3 | Testing of installations. |  | 0 | A8.7.7.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.7 External fuel storage and piped distribution systems | 8.7.7.3 Testing of installations.
8.7.7.4 | Commissioning of installations. |  | 0 | A8.7.7.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.7 External fuel storage and piped distribution systems | 8.7.7.4 Commissioning of installations.
8.7.8 | External security systems |  | 0 | A8.7.8 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems
8.7.8.1 | Surveillance equipment: details of each type of system to be stated. |  | 0 | A8.7.8.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.1 Surveillance equipment: details of each type of system to be stated.
8.7.8.2 | Security detection equipment: details of each type of system to be stated. |  | 0 | A8.7.8.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.2 Security detection equipment: details of each type of system to be stated.
8.7.8.3 | Security alarm equipment: details of each type of system to be stated. |  | 0 | A8.7.8.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.3 Security alarm equipment: details of each type of system to be stated.
8.7.8.4 | Gate JHLess control systems: details of each type of system to be stated. |  | 0 | A8.7.8.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.4 Gate JHLess control systems: details of each type of system to be stated.
8.7.8.5 | Gate entry systems: details of each type of system to be stated. |  | 0 | A8.7.8.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.5 Gate entry systems: details of each type of system to be stated.
8.7.8.6 | Security lights and lighting systems: details of each type of system to be stated. |  | 0 | A8.7.8.6 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.6 Security lights and lighting systems: details of each type of system to be stated.
8.7.8.7 | Other security systems: details of each type of system to be stated. |  | 0 | A8.7.8.7 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.7 Other security systems: details of each type of system to be stated.
8.7.8.8 | Service runs: details to be stated. |  | 0 | A8.7.8.8 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.8 Service runs: details to be stated.
8.7.8.9 | Testing of installations. |  | 0 | A8.7.8.9 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.9 Testing of installations.
8.7.8.10 | Commissioning of installations. |  | 0 | A8.7.8.10 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.8 External security systems | 8.7.8.10 Commissioning of installations.
8.7.9 | External street lighting systems |  | 0 | A8.7.9 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.9 External street lighting systems
8.7.9.1 | External lighting to pedestrian areas: details to be stated. | 25000 | 24785 | A8.7.9.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.9 External street lighting systems | 8.7.9.1 External lighting to pedestrian areas: details to be stated.
8.7.9.2 | External lighting to paths: details to be stated. |  | 0 | A8.7.9.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.9 External street lighting systems | 8.7.9.2 External lighting to paths: details to be stated.
8.7.9.3 | External lighting to roads: details to be stated. |  | 0 | A8.7.9.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.9 External street lighting systems | 8.7.9.3 External lighting to roads: details to be stated.
8.7.9.4 | Illuminated traffic signs: details to be stated. |  | 0 | A8.7.9.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.9 External street lighting systems | 8.7.9.4 Illuminated traffic signs: details to be stated.
8.7.9.5 | Testing of installations. |  | 0 | A8.7.9.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.9 External street lighting systems | 8.7.9.5 Testing of installations.
8.7.9.6 | Commissioning of installations. |  | 0 | A8.7.9.6 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.9 External street lighting systems | 8.7.9.6 Commissioning of installations.
8.7.10 | Local/district heating installations |  | 0 | A8.7.10 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.10 Local/district heating installations
8.7.10.1 | Heat source associated plant and equipment: details to be stated. |  | 0 | A8.7.10.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.10 Local/district heating installations | 8.7.10.1 Heat source associated plant and equipment: details to be stated.
8.7.10.2 | Service runs: details to be stated. |  | 0 | A8.7.10.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.10 Local/district heating installations | 8.7.10.2 Service runs: details to be stated.
8.7.10.3 | External heating ducts and duct JHLess covers: details to be stated. |  | 0 | A8.7.10.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.10 Local/district heating installations | 8.7.10.3 External heating ducts and duct JHLess covers: details to be stated.
8.7.10.4 | Testing of installations. |  | 0 | A8.7.10.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.10 Local/district heating installations | 8.7.10.4 Testing of installations.
8.7.10.5 | Commissioning of installations. |  | 0 | A8.7.10.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.10 Local/district heating installations | 8.7.10.5 Commissioning of installations.
8.7.11 | Builder's work in connection with external services |  | 0 | A8.7.11 | 2 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services
8.7.11.1 | Ducts and the like: details to be stated. | 35000 | 35795 | A8.7.11.1 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.1 Ducts and the like: details to be stated.
8.7.11.2 | Supports to external storage tanks, vessels and the like: details to be stated. |  | 0 | A8.7.11.2 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.2 Supports to external storage tanks, vessels and the like: details to be stated.
8.7.11.3 | Fuel bunds and the like to storage/retention tanks and vessels: details to be stated. |  | 0 | A8.7.11.3 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.3 Fuel bunds and the like to storage/retention tanks and vessels: details to be stated.
8.7.11.4 | Protective compounds, fencing, storage racks associated with LPG installations and the like: details to be stated. |  | 0 | A8.7.11.4 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.4 Protective compounds, fencing, storage racks associated with LPG installations and the like: details to be stated.
8.7.11.5 | Protective compounds, connected with transformer sub-stations and the like: details to be stated. |  | 0 | A8.7.11.5 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.5 Protective compounds, connected with transformer sub-stations and the like: details to be stated.
8.7.11.6 | Bases for services equipment: details, including size, to be stated. |  | 0 | A8.7.11.6 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.6 Bases for services equipment: details, including size, to be stated.
8.7.11.7 | Other builder's work in connection with external services: details to be stated. | 3500 | 3461 | A8.7.11.7 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.7 Other builder's work in connection with external services: details to be stated.
8.7.11.8 | Testing of installations. | 175 | 167 | A8.7.11.8 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.8 Testing of installations.
8.7.11.9 | Commissioning of installations. | 1750 | 1754 | A8.7.11.9 | 3 | 8 EXTERNAL WORKS | 8.7 External services | 8.7.11 Builder's work in connection with external services | 8.7.11.9 Commissioning of installations.
8.8 | Minor building works and ancillary buildings |  | 0 | A8.8 | 1 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings
8.8.1 | Minor building works |  | 0 | A8.8.1 | 2 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.1 Minor building works
8.8.1.1 | Refurbishment of existing ancillary buildings: details, including GIFA (m2), to be stated. |  | 0 | A8.8.1.1 | 3 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.1 Minor building works | 8.8.1.1 Refurbishment of existing ancillary buildings: details, including GIFA (m2), to be stated.
8.8.1.2 | Overhauling existing mechanical and electrical plant and equipment: details to be stated. |  | 0 | A8.8.1.2 | 3 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.1 Minor building works | 8.8.1.2 Overhauling existing mechanical and electrical plant and equipment: details to be stated.
8.8.1.3 | Repairs to existing fences, railings, walls and screen walls: details to be stated. |  | 0 | A8.8.1.3 | 3 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.1 Minor building works | 8.8.1.3 Repairs to existing fences, railings, walls and screen walls: details to be stated.
8.8.2 | Ancillary buildings and structures |  | 0 | A8.8.2 | 2 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.2 Ancillary buildings and structures
8.8.2.1 | Minor ancillary building - built: details, including GIFA (m2), to be stated. |  | 0 | A8.8.2.1 | 3 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.2 Ancillary buildings and structures | 8.8.2.1 Minor ancillary building - built: details, including GIFA (m2), to be stated.
8.8.2.2 | Minor ancillary building - prefabricated/proprietary: details to be stated. |  | 0 | A8.8.2.2 | 3 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.2 Ancillary buildings and structures | 8.8.2.2 Minor ancillary building - prefabricated/proprietary: details to be stated.
8.8.3 | Underpinning to external site boundary walls |  | 0 | A8.8.3 | 2 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.3 Underpinning to external site boundary walls
8.8.3.1 | Underpinning to external site boundary walls and the like: details to be stated. |  | 0 | A8.8.3.1 | 3 | 8 EXTERNAL WORKS | 8.8 Minor building works and ancillary buildings | 8.8.3 Underpinning to external site boundary walls | 8.8.3.1 Underpinning to external site boundary walls and the like: details to be stated.
9 | MAIN CONTRACTOR'S PRELIMINARIES |  | 0 | A9 | 0 | 9 MAIN CONTRACTOR'S PRELIMINARIES
9.1 | Employer's requirements |  | 0 | A9.1 | 1 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements
9.1.1 | Site JHLommodation |  | 0 | A9.1.1 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation
9.1.1.1 | Site JHLommodation |  | 0 | A9.1.1.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.1.1 Site JHLommodation
9.1.1.2 | Furniture and equipment |  | 0 | A9.1.1.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.1.2 Furniture and equipment
9.1.1.3 | Telecommunication and IT systems |  | 0 | A9.1.1.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.1.3 Telecommunication and IT systems
9.1.2.1 | Site records |  | 0 | A9.1.2.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.2.1 Site records
9.1.2.1.1 | Operation and maintenance manuals (paper and electronic copies on CD Rom/DVD/USB). |  | 0 | A9.1.2.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.2.1 Site records
9.1.2.1.2 | Compilation of health and safety file (if required by main contractor - paper and electronic copies on CD Rom/DVD/USB)). |  | 0 | A9.1.2.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.2.1 Site records
9.1.2.1.3 | Web-based documentation project management systems for the collation, review and delivery of critical operation and maintenance requirements; commissioning; asset; and other facilities management-related information, and health and safety file: |  | 0 | A9.1.2.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.2.1 Site records
9.1.2.1.3 | - Programme software and installation |  | 0 | A9.1.2.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.2.1 Site records
9.1.2.1.3 | - Hardware (e.g. computers. Monitors, printers, etc) |  | 0 | A9.1.2.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.2.1 Site records
9.1.2.1.3 | - Uploading data and initial implementation and training of building management team by system provider |  | 0 | A9.1.2.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.1 Site JHLommodation | 9.1.2.1 Site records
9.1.3 | Completion and post-completion requirements |  | 0 | A9.1.3 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.3 Completion and post-completion requirements
9.1.3.1 | Handover requirements |  | 0 | A9.1.3.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.3 Completion and post-completion requirements | 9.1.3.1 Handover requirements
9.1.3.1.2 | Provision of spare parts for maintenance of building engineering services. |  | 0 | A9.1.3.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.3 Completion and post-completion requirements | 9.1.3.1 Handover requirements
9.1.3.1.3 | Provision of tools and portable indicating instruments for the operation and maintenance of building engineering services systems. |  | 0 | A9.1.3.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.3 Completion and post-completion requirements | 9.1.3.1 Handover requirements
9.1.3.2 | Operation and maintenance services |  | 0 | A9.1.3.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.3 Completion and post-completion requirements | 9.1.3.2 Operation and maintenance services
9.1.3.2.1 | Operation and maintenance of building engineering services installations, mechanical plant and equipment and the like during the defects liability period, period for rectifying defects, maintenance period or other specified period (i.e. additional services to that normally required by the contract). |  | 0 | A9.1.3.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.1 Employer's requirements | 9.1.3 Completion and post-completion requirements | 9.1.3.2 Operation and maintenance services
9.2 | Main contractor's cost items |  | 0 | A9.2 | 1 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items
9.2.1 | Management and staff | 240069 | 235423 | A9.2.1 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.1 Management and staff
9.2.2 | Site establishment |  | 0 | A9.2.2 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment
9.2.2.1 | Site JHLommodation |  | 0 | A9.2.2.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Site JHLommodation
9.2.2.1 | Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified: |  | 0 | A9.2.2.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.1 | Purchase charges. |  | 0 | A9.2.2.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.2 | Hire and purchase per week |  | 0 | A9.2.2.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.3 | Delivery of temporary site JHLommodation to site, erection, construction and removal. |  | 0 | A9.2.2.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.4 | Temporary JHLommodation made available by the employer. |  | 0 | A9.2.2.1.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.5 | Intruder alarms. |  | 0 | A9.2.2.1.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.6 | Land/property rental where site JHLommodation located off-site. |  | 0 | A9.2.2.1.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.7 | Alterations and adaptations to site JHLommodation, including partitioning, doors, painting and decorating, and the like. |  | 0 | A9.2.2.1.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.8 | Relocation and alterations of temporary JHLommodation during construction stage. |  | 0 | A9.2.2.1.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.9 | Reinstating temporary site JHLommodation to original condition prior to removal from site. |  | 0 | A9.2.2.1.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.1.10 | Removal of site JHLommodation and temporary works in connection with site JHLommodation. |  | 0 | A9.2.2.1.10 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.1 Main contractor's and common user temporary site JHLommodation such as: offices, conference/meeting rooms, canteens and kitchens, drying rooms, toilets and washrooms, first aid room, laboratories, workshops, secure stores, compounds, including containers for material storage, security control room, stairs and office staging, Employer's JHLommodation, where an integral part of the main contractor's site JHLommodation. Type and extent of JHLommodation to be provided to be stated, with each type separately quantified:
9.2.2.2 | Temporary works in connection with site establishment |  | 0 | A9.2.2.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.2 Temporary works in connection with site establishment
9.2.2.2.1 | Temporary bases and foundations for site JHLommodation, including maintenance, removal and reinstatement of all disturbed existing surfaces on completion of the works. |  | 0 | A9.2.2.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.2 Temporary works in connection with site establishment
9.2.2.2.2 | Connections to temporary service, including maintenance, removal and reinstatement of all disturbed existing surfaces on completion of the works. |  | 0 | A9.2.2.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.2 Temporary works in connection with site establishment
9.2.2.2.3 | Connections to temporary drainage including maintenance, removal and reinstatement of all disturbed existing surfaces on completion of the works. |  | 0 | A9.2.2.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.2 Temporary works in connection with site establishment
9.2.2.2.4 | Temporary site roads, paths and pavings (including on-site car parking), including maintenance, removal and reinstatement of all disturbed existing surfaces on completion of the works. |  | 0 | A9.2.2.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.2 Temporary works in connection with site establishment
9.2.2.2.5 | Temporary surface water drainage to temporary site roads, paths and pavements, including maintenance, removal and reinstatement of all disturbed existing surfaces on completion of the works. |  | 0 | A9.2.2.2.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.2 Temporary works in connection with site establishment
9.2.2.3 | Furniture and equipment |  | 0 | A9.2.2.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.1 | Workstations for staff, including maintenance. |  | 0 | A9.2.2.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.2 | General office furniture, including maintenance. |  | 0 | A9.2.2.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.3 | Conference/meeting room furniture, including maintenance. |  | 0 | A9.2.2.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.4 | Photocopiers, including purchase/rental, maintenance and other running costs. |  | 0 | A9.2.2.3.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.5 | Canteen furniture, including maintenance. |  | 0 | A9.2.2.3.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.6 | Canteen equipment, including purchase/rental, maintenance and other running costs. |  | 0 | A9.2.2.3.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.7 | Floor coverings, including maintenance. |  | 0 | A9.2.2.3.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.8 | Water dispensers, including purchase/rental, maintenance and other running costs. |  | 0 | A9.2.2.3.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.9 | Heaters, including maintenance of heaters. |  | 0 | A9.2.2.3.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.10 | Other office equipment, including maintenance. |  | 0 | A9.2.2.3.10 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.11 | Removal of furniture and equipment. |  | 0 | A9.2.2.3.11 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.3.12 | Maintenance furniture and floor covering. |  | 0 | A9.2.2.3.12 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.3 Furniture and equipment
9.2.2.4 | IT systems |  | 0 | A9.2.2.4 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.1 | Computer hardware, including purchase/rental, installation, initial set up, maintenance and running costs, such as: - desktop computers and laptop computers - CAD stations - server and network equipment - printers and plotters - other computer system hardware. |  | 0 | A9.2.2.4.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.2 | Software and software licences. |  | 0 | A9.2.2.4.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.3 | Modem lines, modems and connections (i.e. email and internet capability). |  | 0 | A9.2.2.4.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.4 | WAN lines and connections (if on WAN). |  | 0 | A9.2.2.4.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.5 | Line rental charges. |  | 0 | A9.2.2.4.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.6 | Internet/website addresses. |  | 0 | A9.2.2.4.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.7 | Internet service provider (ISP) charges. |  | 0 | A9.2.2.4.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.8 | Line calls charges. |  | 0 | A9.2.2.4.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.4.9 | IT support and maintenance. |  | 0 | A9.2.2.4.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.4 IT systems
9.2.2.5 | Consumables and services |  | 0 | A9.2.2.5 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.1 | Stationery. |  | 0 | A9.2.2.5.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.2 | Computer and printer consumables (e.g. ink cartridges). |  | 0 | A9.2.2.5.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.3 | Postage. |  | 0 | A9.2.2.5.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.4 | Courier charges. |  | 0 | A9.2.2.5.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.5 | Tea, coffee, water bottles and the like. |  | 0 | A9.2.2.5.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.6 | First aid consumables. |  | 0 | A9.2.2.5.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.7 | Photocopier consumables (e.g. paper and toners). |  | 0 | A9.2.2.5.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.8 | Fax consumables (e.g. paper and toners). |  | 0 | A9.2.2.5.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.5.9 | Drawing printer consumables (e.g. ink cartridges). |  | 0 | A9.2.2.5.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.5 Consumables and services
9.2.2.6 | Brought in services |  | 0 | A9.2.2.6 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Brought in services
9.2.2.6 | Services outsourced by the main contractor such as: |  | 0 | A9.2.2.6 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.1 | Catering. |  | 0 | A9.2.2.6.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.2 | Equipment maintenance. |  | 0 | A9.2.2.6.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.3 | Document management, including electronic data management systems (EDMS). |  | 0 | A9.2.2.6.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.4 | Printing (purchasing), including reports and drawings. |  | 0 | A9.2.2.6.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.5 | Staff transport. |  | 0 | A9.2.2.6.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.6 | Off-site parking charges. |  | 0 | A9.2.2.6.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.7 | Meeting room facilities. |  | 0 | A9.2.2.6.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.6.8 | Photographic services. |  | 0 | A9.2.2.6.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.6 Services outsourced by the main contractor such as:
9.2.2.7 | Sundries |  | 0 | A9.2.2.7 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.2.7.1 | Main contractor's signboards. |  | 0 | A9.2.2.7.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.2.7.2 | Safety and information notice boards. |  | 0 | A9.2.2.7.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.2.7.3 | Fire points. |  | 0 | A9.2.2.7.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.2.7.4 | Shelters. |  | 0 | A9.2.2.7.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.2.7.5 | Tool stores. |  | 0 | A9.2.2.7.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.2.7.6 | Crane signage. |  | 0 | A9.2.2.7.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.2.7.7 | Employer's composite signboards. |  | 0 | A9.2.2.7.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.2 Site establishment | 9.2.2.7 Sundries
9.2.3 | Temporary services |  | 0 | A9.2.3 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services
9.2.3.1 | Temporary water supply |  | 0 | A9.2.3.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.1 Temporary water supply
9.2.3.1.1 | Temporary connections. |  | 0 | A9.2.3.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.1 Temporary water supply
9.2.3.1.2 | Distribution equipment, installation and adaptations. |  | 0 | A9.2.3.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.1 Temporary water supply
9.2.3.1.3 | Meter charges. |  | 0 | A9.2.3.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.1 Temporary water supply
9.2.3.2 | Temporary gas supply |  | 0 | A9.2.3.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.2 Temporary gas supply
9.2.3.2.1 | Gas connection. |  | 0 | A9.2.3.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.2 Temporary gas supply
9.2.3.2.2 | Distribution equipment, installation and adaptations. |  | 0 | A9.2.3.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.2 Temporary gas supply
9.2.3.2.3 | Charges. |  | 0 | A9.2.3.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.2 Temporary gas supply
9.2.3.2.4 | Bottled gas. |  | 0 | A9.2.3.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.2 Temporary gas supply
9.2.3.3 | Temporary electricity supply |  | 0 | A9.2.3.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.1 | Temporary connections. |  | 0 | A9.2.3.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.2 | Temporary electrical supply for tower cranes. |  | 0 | A9.2.3.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.3 | Charges - power consumption for site establishment. |  | 0 | A9.2.3.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.4 | Charges - power consumption for the works. |  | 0 | A9.2.3.3.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.5 | Distribution equipment, installation and adaptations. |  | 0 | A9.2.3.3.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.6 | Attendance. |  | 0 | A9.2.3.3.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.7 | Uninterrupted power supply (UPS). |  | 0 | A9.2.3.3.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.3.8 | Temporary substation modifications. |  | 0 | A9.2.3.3.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.3 Temporary electricity supply
9.2.3.4 | Temporary telecommunication systems |  | 0 | A9.2.3.4 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.4 Temporary telecommunication systems
9.2.3.4.1 | Landlines (including connection and rental charges), including: telephone and fax lines, ISDN lines. |  | 0 | A9.2.3.4.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.4 Temporary telecommunication systems
9.2.3.4.2 | Telephone and facsimile equipment (including connection and rental charges), including: PABX equipment, handsets, including purchase or rental, fax machines, including purchase or rental, installation of equipment, maintenance of equipment. |  | 0 | A9.2.3.4.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.4 Temporary telecommunication systems
9.2.3.4.3 | Mobile (cellular) phones, including: mobile phones, including purchase or rental and connection charges, spare batteries, mobile phone charges. |  | 0 | A9.2.3.4.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.4 Temporary telecommunication systems
9.2.3.4.4 | Telephone charges, including: telephone call charges, fax charges, fax and telephone consumables. |  | 0 | A9.2.3.4.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.4 Temporary telecommunication systems
9.2.3.4.5 | Radios (including purchase or rental charges), including: base set, handsets and chargers, repairs and maintenance, licences, spare batteries. |  | 0 | A9.2.3.4.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.4 Temporary telecommunication systems
9.2.3.5 | Temporary drainage |  | 0 | A9.2.3.5 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.1 | Temporary mains. |  | 0 | A9.2.3.5.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.2 | Septic tanks. |  | 0 | A9.2.3.5.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.3 | On-site treatment plant. |  | 0 | A9.2.3.5.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.4 | Holding tanks. |  | 0 | A9.2.3.5.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.5 | Sewage pumping. |  | 0 | A9.2.3.5.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.6 | Distribution pipework, etc. |  | 0 | A9.2.3.5.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.7 | Drainage installation and adaptations. |  | 0 | A9.2.3.5.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.8 | Disposal charges (i.e. rates). |  | 0 | A9.2.3.5.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.3.5.9 | Disposal costs (i.e. tanker charges). |  | 0 | A9.2.3.5.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.3 Temporary services | 9.2.3.5 Temporary drainage
9.2.4 | Security |  | 0 | A9.2.4 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security
9.2.4.1 | Security staff |  | 0 | A9.2.4.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.1 Security staff
9.2.4.1.1 | Security guards (day and night). |  | 0 | A9.2.4.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.1 Security staff
9.2.4.1.2 | Watchmen (day and night). |  | 0 | A9.2.4.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.1 Security staff
9.2.4.2 | Security equipment |  | 0 | A9.2.4.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.2 Security equipment
9.2.4.2.1 | Site pass issue equipment. |  | 0 | A9.2.4.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.2 Security equipment
9.2.4.2.2 | Site pass consumables. |  | 0 | A9.2.4.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.2 Security equipment
9.2.4.2.3 | CCTV surveillance installation, including cameras. |  | 0 | A9.2.4.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.2 Security equipment
9.2.4.2.4 | Temporary vehicle control barriers. |  | 0 | A9.2.4.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.2 Security equipment
9.2.4.3 | Hoardings, fences and gates |  | 0 | A9.2.4.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.3 Hoardings, fences and gates
9.2.4.3.1 | Perimeter hoardings and fencing and the like to site boundaries and to form site compounds. |  | 0 | A9.2.4.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.3 Hoardings, fences and gates
9.2.4.3.2 | JHLess gates, including frames and ironmongery. |  | 0 | A9.2.4.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.3 Hoardings, fences and gates
9.2.4.3.3 | Painting of hoardings, fencing, gates, and the like. |  | 0 | A9.2.4.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.3 Hoardings, fences and gates
9.2.4.3.4 | Temporary doors. |  | 0 | A9.2.4.3.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.3 Hoardings, fences and gates
9.2.4.3.5 | Modification to line of hoarding and fencing during construction. |  | 0 | A9.2.4.3.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.3 Hoardings, fences and gates
9.2.4.3.6 | Dismantling and removal of hoarding, fencing, gates, and the like. |  | 0 | A9.2.4.3.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.4 Security | 9.2.4.3 Hoardings, fences and gates
9.2.5 | Safety and environmental protection |  | 0 | A9.2.5 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection
9.2.5.1 | Safety programme |  | 0 | A9.2.5.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Safety programme
9.2.5.1 | Works required to satisfy requirements of CDM Regulations. |  | 0 | A9.2.5.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.1 | Health and safety manager/officers. |  | 0 | A9.2.5.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.2 | Safety audits, including safety audits carried out by external consultant. |  | 0 | A9.2.5.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.3 | Staff safety training. |  | 0 | A9.2.5.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.4 | Site safety incentive scheme. |  | 0 | A9.2.5.1.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.5 | Notices and information to neighbours. |  | 0 | A9.2.5.1.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.6 | Personal protective equipment (PPE), including for employer and consultants. |  | 0 | A9.2.5.1.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.7 | Personal protective equipment (PPE) for multi-service gangs. |  | 0 | A9.2.5.1.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.8 | Fire points. |  | 0 | A9.2.5.1.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.9 | Temporary fire alarms. |  | 0 | A9.2.5.1.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.10 | Fire extinguishers. |  | 0 | A9.2.5.1.10 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.11 | Statutory safety signage. |  | 0 | A9.2.5.1.11 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.12 | Nurse. |  | 0 | A9.2.5.1.12 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.13 | Traffic marshals. |  | 0 | A9.2.5.1.13 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.1.14 | Temporary traffic lights. |  | 0 | A9.2.5.1.14 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.1 Works required to satisfy requirements of CDM Regulations.
9.2.5.2 | Barriers and safety scaffolding |  | 0 | A9.2.5.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.1 | Guard rails and edge protection (e.g. to edges of suspended slabs and roofs), including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.2 | Temporary staircase balustrades (i.e. to new staircases during construction), including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.3 | Lift shaft protection, including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.4 | Protection to holes and openings in ground floor slabs, suspended slabs and the like, including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.5 | Debris netting/plastic sheeting, including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.6 | Fan protection, including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.7 | Scaffold inspections. |  | 0 | A9.2.5.2.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.8 | Hoist run-offs, including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.9 | Protective walkways, including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.2.10 | Other safety measures, including supply, erection, maintenance and dismantling on completion of the works. |  | 0 | A9.2.5.2.10 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.2 Barriers and safety scaffolding
9.2.5.3 | Environmental protection measures |  | 0 | A9.2.5.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.3 Environmental protection measures
9.2.5.3.1 | Control of pollution. |  | 0 | A9.2.5.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.3 Environmental protection measures
9.2.5.3.2 | Residual control of noise. |  | 0 | A9.2.5.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.3 Environmental protection measures
9.2.5.3.3 | Environmental manager/consultant. |  | 0 | A9.2.5.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.3 Environmental protection measures
9.2.5.3.4 | Environmental audits, including safety audits carried out by external consultant. |  | 0 | A9.2.5.3.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.5 Safety and environmental protection | 9.2.5.3 Environmental protection measures
9.2.6 | Control and protection |  | 0 | A9.2.6 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection
9.2.6.1 | Surveys, inspections and monitoring |  | 0 | A9.2.6.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.1.1 | Surveys. |  | 0 | A9.2.6.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.1.2 | Topographical survey. |  | 0 | A9.2.6.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.1.3 | Non-employer dilapidation survey. |  | 0 | A9.2.6.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.1.4 | Structural/dilapidations survey adjoining buildings. |  | 0 | A9.2.6.1.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.1.5 | Environmental surveys. |  | 0 | A9.2.6.1.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.1.6 | Movement monitoring. |  | 0 | A9.2.6.1.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.1.7 | Maintenance and inspection costs. |  | 0 | A9.2.6.1.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.1 Surveys, inspections and monitoring
9.2.6.2 | Setting out |  | 0 | A9.2.6.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.2 Setting out
9.2.6.2.1 | Setting out primary grids. |  | 0 | A9.2.6.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.2 Setting out
9.2.6.2.2 | Grid transfers and level checks. |  | 0 | A9.2.6.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.2 Setting out
9.2.6.2.3 | Maintenance of grids. |  | 0 | A9.2.6.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.2 Setting out
9.2.6.2.4 | Take over control and independent checks (i.e. on change of subcontractors). |  | 0 | A9.2.6.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.2 Setting out
9.2.6.2.5 | Instruments for setting out. |  | 0 | A9.2.6.2.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.2 Setting out
9.2.6.3 | Protection of works |  | 0 | A9.2.6.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.3.1 | Protection of finished works to project handover. |  | 0 | A9.2.6.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.3.2 | Protection of stairs, balustrades and the like works to project handover. |  | 0 | A9.2.6.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.3.3 | Protection of fittings and furnishings works to project handover. |  | 0 | A9.2.6.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.3.4 | Protection of entrance doors and frames works to project handover. |  | 0 | A9.2.6.3.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.3.5 | Protection of lift cars and doors works to project handover. |  | 0 | A9.2.6.3.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.3.6 | Protection of specifically vulnerable products to project handover. |  | 0 | A9.2.6.3.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.3.7 | Protection of all sundry items. |  | 0 | A9.2.6.3.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.3 Protection of works
9.2.6.4 | Samples |  | 0 | A9.2.6.4 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.4 Samples
9.2.6.4.1 | Provision of samples. |  | 0 | A9.2.6.4.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.4 Samples
9.2.6.4.2 | Provision of sample room. |  | 0 | A9.2.6.4.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.4 Samples
9.2.6.4.3 | Mock ups and sample panels. |  | 0 | A9.2.6.4.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.4 Samples
9.2.6.4.4 | Testing of samples/mock ups, including testing fees. |  | 0 | A9.2.6.4.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.4 Samples
9.2.6.4.5 | On site laboratory equipment. |  | 0 | A9.2.6.4.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.4 Samples
9.2.6.4.6 | Mock ups of complete units (e.g. residential units, student JHLommodation units, hotel JHLommodation and the like). |  | 0 | A9.2.6.4.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.4 Samples
9.2.6.5 | Environmental control of building |  | 0 | A9.2.6.5 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.5 Environmental control of building
9.2.6.5.1 | Dry out building. |  | 0 | A9.2.6.5.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.5 Environmental control of building
9.2.6.5.2 | Temporary heating/cooling. |  | 0 | A9.2.6.5.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.5 Environmental control of building
9.2.6.5.3 | Temporary waterproofing, including over roofs. |  | 0 | A9.2.6.5.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.5 Environmental control of building
9.2.6.5.4 | Temporary enclosures. |  | 0 | A9.2.6.5.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.6 Control and protection | 9.2.6.5 Environmental control of building
9.2.7 | Mechanical plant |  | 0 | A9.2.7 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant
9.2.7.1 | Generally |  | 0 | A9.2.7.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.1 Generally
9.2.7.1.1 | Common user mechanical plant and equipment used in construction operations. |  | 0 | A9.2.7.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.1 Generally
9.2.7.2 | Tower cranes |  | 0 | A9.2.7.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Tower cranes
9.2.7.2 | Type of craneage to be provided shall be stated; with each type separately quantified. |  | 0 | A9.2.7.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.1 | Hire charges (type of tower crane to be stated, including type and length of jib, and lifting capacity). |  | 0 | A9.2.7.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.2 | Crane operator. |  | 0 | A9.2.7.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.3 | Overtime for crane and operator. |  | 0 | A9.2.7.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.4 | Piles for tower crane bases including installation and removal on completion of the works (size of base in m2, and number of piles supporting base, to be stated). |  | 0 | A9.2.7.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.5 | Temporary bases and or ground anchors for tower cranes, including installation, maintenance, removal and reinstatement of all disturbed surfaces on completion of the works (size of base in m2 to be stated). |  | 0 | A9.2.7.2.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.6 | Ties. |  | 0 | A9.2.7.2.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.7 | Connections to temporary electrical supply. |  | 0 | A9.2.7.2.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.8 | Bring to site, erection, test and commission. |  | 0 | A9.2.7.2.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.9 | Periodic safety checks/inspections. |  | 0 | A9.2.7.2.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.10 | Dismantling and removing from site. |  | 0 | A9.2.7.2.10 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.11 | Other costs specific to tower crane such as: chain pack and sundries, relief operator, banksman, man cage. |  | 0 | A9.2.7.2.11 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.2.12 | Temporary voids in building structure for craneage, hoists and the like including filling voids after removal. |  | 0 | A9.2.7.2.12 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.2 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.3 | Mobile cranes |  | 0 | A9.2.7.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.3 Mobile cranes
9.2.7.3 | Type of craneage to be provided shall be stated; with each type separately quantified. |  | 0 | A9.2.7.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.3 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.3.1 | Mobile crane hire charges, including driver/operator charges (type of mobile crane to be stated) |  | 0 | A9.2.7.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.3 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.3.2 | Attendance. |  | 0 | A9.2.7.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.3 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.3.3 | Other costs specific to mobile crane hire. |  | 0 | A9.2.7.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.3 Type of craneage to be provided shall be stated; with each type separately quantified.
9.2.7.4 | Hoists |  | 0 | A9.2.7.4 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Hoists
9.2.7.4 | Type of hoist to be provided shall be stated; with each type separately quantified: |  | 0 | A9.2.7.4 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.1 | Goods and passenger hoists, including protection cages and embedment frames. |  | 0 | A9.2.7.4.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.2 | Hoist bases. |  | 0 | A9.2.7.4.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.3 | Bringing to site, erecting, testing and commissioning. |  | 0 | A9.2.7.4.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.4 | Dismantling and removing from site. |  | 0 | A9.2.7.4.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.5 | Protection systems. |  | 0 | A9.2.7.4.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.6 | Hoist operator, including overtime. |  | 0 | A9.2.7.4.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.7 | Beam hoists. |  | 0 | A9.2.7.4.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.8 | Periodic safety checks/inspections. |  | 0 | A9.2.7.4.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.4.9 | Other costs specific to temporary hoist installations. |  | 0 | A9.2.7.4.9 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.4 Type of hoist to be provided shall be stated; with each type separately quantified:
9.2.7.5 | JHLess plant |  | 0 | A9.2.7.5 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.5 JHLess plant
9.2.7.5.1 | Fork lifts. |  | 0 | A9.2.7.5.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.5 JHLess plant
9.2.7.5.2 | Scissor lifts. |  | 0 | A9.2.7.5.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.5 JHLess plant
9.2.7.5.3 | Loading platforms. |  | 0 | A9.2.7.5.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.5 JHLess plant
9.2.7.5.4 | Maintenance of mechanical JHLess equipment. |  | 0 | A9.2.7.5.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.5 JHLess plant
9.2.7.5.5 | Other costs specific to mechanical JHLess equipment. |  | 0 | A9.2.7.5.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.5 JHLess plant
9.2.7.6 | Concrete plant |  | 0 | A9.2.7.6 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.1 | Concrete plant. |  | 0 | A9.2.7.6.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.2 | Plant operator. |  | 0 | A9.2.7.6.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.3 | Overtime for plant and operator. |  | 0 | A9.2.7.6.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.4 | Bases for concrete plant, including installation, maintenance, removal and reinstatement of disturbed surfaces on completion of the works (size in m2 to be stated). |  | 0 | A9.2.7.6.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.5 | Power connections, including cabling and statutory undertaker's charges for temporary connection to their supply. |  | 0 | A9.2.7.6.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.6 | Bringing concrete plant to site, erecting, testing and commissioning. |  | 0 | A9.2.7.6.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.7 | Maintenance of concrete plant. |  | 0 | A9.2.7.6.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.6.8 | Dismantling and removing from site. |  | 0 | A9.2.7.6.8 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.6 Concrete plant
9.2.7.7 | Other plant |  | 0 | A9.2.7.7 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.7 Other plant
9.2.7.7.1 | Small plant and tools. |  | 0 | A9.2.7.7.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.7 Mechanical plant | 9.2.7.7 Other plant
9.2.8 | Temporary works |  | 0 | A9.2.8 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works
9.2.8.1 | JHLess scaffolding |  | 0 | A9.2.8.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.1 JHLess scaffolding
9.2.8.1 | Common user JHLess scaffolding (type of JHLess scaffolding to be specified): - JHLess scaffolding to elevations, lift shafts and the like, including fans, mesh screens, - structural scaffolding (e.g. to party walls), - birdcage scaffolding, - cantilever JHLess scaffolding, - staircase platforms, - primary loading platforms, - travelling JHLess platforms. |  | 0 | A9.2.8.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.1 Common user JHLess scaffolding (type of JHLess scaffolding to be specified): - JHLess scaffolding to elevations, lift shafts and the like, including fans, mesh screens, - structural scaffolding (e.g. to party walls), - birdcage scaffolding, - cantilever JHLess scaffolding, - staircase platforms, - primary loading platforms, - travelling JHLess platforms.
9.2.8.1.1 | Bringing to site, erecting and initial safety checks. |  | 0 | A9.2.8.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.1 Common user JHLess scaffolding (type of JHLess scaffolding to be specified): - JHLess scaffolding to elevations, lift shafts and the like, including fans, mesh screens, - structural scaffolding (e.g. to party walls), - birdcage scaffolding, - cantilever JHLess scaffolding, - staircase platforms, - primary loading platforms, - travelling JHLess platforms.
9.2.8.1.2 | Hire charges. |  | 0 | A9.2.8.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.1 Common user JHLess scaffolding (type of JHLess scaffolding to be specified): - JHLess scaffolding to elevations, lift shafts and the like, including fans, mesh screens, - structural scaffolding (e.g. to party walls), - birdcage scaffolding, - cantilever JHLess scaffolding, - staircase platforms, - primary loading platforms, - travelling JHLess platforms.
9.2.8.1.3 | Altering and adapting during construction. |  | 0 | A9.2.8.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.1 Common user JHLess scaffolding (type of JHLess scaffolding to be specified): - JHLess scaffolding to elevations, lift shafts and the like, including fans, mesh screens, - structural scaffolding (e.g. to party walls), - birdcage scaffolding, - cantilever JHLess scaffolding, - staircase platforms, - primary loading platforms, - travelling JHLess platforms.
9.2.8.1.4 | Dismantling and removing from site. |  | 0 | A9.2.8.1.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.1 Common user JHLess scaffolding (type of JHLess scaffolding to be specified): - JHLess scaffolding to elevations, lift shafts and the like, including fans, mesh screens, - structural scaffolding (e.g. to party walls), - birdcage scaffolding, - cantilever JHLess scaffolding, - staircase platforms, - primary loading platforms, - travelling JHLess platforms.
9.2.8.2 | Temporary works |  | 0 | A9.2.8.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.2 Temporary works
9.2.8.2 | Common user temporary works: - support scaffolding and propping, - crash decks, - temporary protection to existing trees and/or vegetation, - floodlights. |  | 0 | A9.2.8.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.2 Common user temporary works: - support scaffolding and propping, - crash decks, - temporary protection to existing trees and/or vegetation, - floodlights.
9.2.8.2.1 | Bringing to site, erecting and initial safety checks. |  | 0 | A9.2.8.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.2 Common user temporary works: - support scaffolding and propping, - crash decks, - temporary protection to existing trees and/or vegetation, - floodlights.
9.2.8.2.2 | Hire charges. |  | 0 | A9.2.8.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.2 Common user temporary works: - support scaffolding and propping, - crash decks, - temporary protection to existing trees and/or vegetation, - floodlights.
9.2.8.2.3 | Altering and adapting during construction. |  | 0 | A9.2.8.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.2 Common user temporary works: - support scaffolding and propping, - crash decks, - temporary protection to existing trees and/or vegetation, - floodlights.
9.2.8.2.4 | Dismantling and removing from site. |  | 0 | A9.2.8.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.8 Temporary works | 9.2.8.2 Common user temporary works: - support scaffolding and propping, - crash decks, - temporary protection to existing trees and/or vegetation, - floodlights.
9.2.9 | Site records |  | 0 | A9.2.9 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.9 Site records
9.2.9.1 | Site records |  | 0 | A9.2.9.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.9 Site records | 9.2.9.1 Site records
9.2.9.1 | Unless otherwise indicated, costs associated with the following shall be deemed to be included in management and staff costs: |  | 0 | A9.2.9.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.9 Site records | 9.2.9.1 Unless otherwise indicated, costs associated with the following shall be deemed to be included in management and staff costs:
9.2.9.1.1 | Photography: - camera purchase, - consumables, - printing and presentation |  | 0 | A9.2.9.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.9 Site records | 9.2.9.1 Unless otherwise indicated, costs associated with the following shall be deemed to be included in management and staff costs:
9.2.9.1.2 | Works records: - progress reporting, - site setting out drawings, - condition surveys and reports, - operation and maintenance manuals, - as-built/installed drawings and schedules, - co-ordinating, gathering and compiling health and safety information and presentation to CDM co-ordinator, - compilation of health and safety file (if required) |  | 0 | A9.2.9.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.9 Site records | 9.2.9.1 Unless otherwise indicated, costs associated with the following shall be deemed to be included in management and staff costs:
9.2.9.2 | Web-based documentation management systems |  | 0 | A9.2.9.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.9 Site records | 9.2.9.2 Web-based documentation management systems
9.2.9.2.1 | Attendance on system provider. |  | 0 | A9.2.9.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.9 Site records | 9.2.9.2 Web-based documentation management systems
9.2.10 | Completion and post-completion requirements |  | 0 | A9.2.10 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements
9.2.10.1 | Testing and commissioning plan |  | 0 | A9.2.10.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.1 Testing and commissioning plan
9.2.10.1 | Costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs: |  | 0 | A9.2.10.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.1 Costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.1.1 | Preparation of Commissioning Plan. |  | 0 | A9.2.10.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.1 Costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.2 | Handover |  | 0 | A9.2.10.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Handover
9.2.10.2 | Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs: |  | 0 | A9.2.10.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.2.1 | Preparation of Handover Plan. |  | 0 | A9.2.10.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.2.2 | Training of building user's staff in the operation and maintenance of the building engineering services systems. |  | 0 | A9.2.10.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.2.3 | Provision of spare parts for maintenance of building engineering services. |  | 0 | A9.2.10.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.2.4 | Provision of tools and portable indicating instruments for the operation and maintenance of building engineering services systems. |  | 0 | A9.2.10.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.2.5 | Pre-completion inspections. |  | 0 | A9.2.10.2.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.2.6 | Final inspections. |  | 0 | A9.2.10.2.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.2 Unless otherwise indicated, costs associated with the following shall be deemed to be included in sub-element 9.2.1: Management and staff costs:
9.2.10.3 | Post-completion services |  | 0 | A9.2.10.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.3 Post-completion services
9.2.10.3.1 | Supervisory staff (employer/tenant care). |  | 0 | A9.2.10.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.3 Post-completion services
9.2.10.3.2 | Handyman. |  | 0 | A9.2.10.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.3 Post-completion services
9.2.10.3.3 | Minor materials and sundry items. |  | 0 | A9.2.10.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.3 Post-completion services
9.2.10.3.4 | Insurances. |  | 0 | A9.2.10.3.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.3 Post-completion services
9.2.10.3.5 | Other post-construction staff. |  | 0 | A9.2.10.3.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.10 Completion and post-completion requirements | 9.2.10.3 Post-completion services
9.2.11 | Cleaning |  | 0 | A9.2.11 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning
9.2.11.1 | Site tidy |  | 0 | A9.2.11.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.1 Site tidy
9.2.11.1.1 | Cleaning site JHLommodation - internal, including cleaning telephone handsets, other office furniture and equipment and window cleaning. |  | 0 | A9.2.11.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.1 Site tidy
9.2.11.1.2 | Periodic maintenance of site JHLommodation, including redecoration (internal and external). |  | 0 | A9.2.11.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.1 Site tidy
9.2.11.1.3 | Waste management, including rubbish disposal (including compactor visits; skips and waste bins; roll-off, roll-on waste bins) and other disposal. |  | 0 | A9.2.11.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.1 Site tidy
9.2.11.1.4 | Pest control. |  | 0 | A9.2.11.1.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.1 Site tidy
9.2.11.2 | Maintenance of roads, paths and pavings |  | 0 | A9.2.11.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.2 Maintenance of roads, paths and pavings
9.2.11.2.1 | Maintenance of temporary site roads, paths and pavements. |  | 0 | A9.2.11.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.2 Maintenance of roads, paths and pavings
9.2.11.2.2 | Maintenance of public and private roads, including wheel spinners and road sweepers. |  | 0 | A9.2.11.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.2 Maintenance of roads, paths and pavings
9.2.11.3 | Building clean |  | 0 | A9.2.11.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.3 Building clean
9.2.11.3.1 | Final builder's clean. |  | 0 | A9.2.11.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.11 Cleaning | 9.2.11.3 Building clean
9.2.12 | Fees and charges |  | 0 | A9.2.12 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges
9.2.12.1 | Fees |  | 0 | A9.2.12.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.1 Fees
9.2.12.1.1 | Building control fees, where not paid by the employer. |  | 0 | A9.2.12.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.1 Fees
9.2.12.1.2 | Oversailing fees, where not paid by the employer. |  | 0 | A9.2.12.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.1 Fees
9.2.12.1.3 | Considerate Constructors' Scheme fees (or alternative scheme operated by local authority). |  | 0 | A9.2.12.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.1 Fees
9.2.12.1.4 | Building scheme registration fees (e.g. NHBC Buildmark) or similar fees, where not paid by the employer. |  | 0 | A9.2.12.1.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.1 Fees
9.2.12.2 | Charges |  | 0 | A9.2.12.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.2 Charges
9.2.12.2.1 | Rates on temporary JHLommodation. |  | 0 | A9.2.12.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.2 Charges
9.2.12.2.2 | Licences in connection with hoardings, scaffolding, gantries and the like. |  | 0 | A9.2.12.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.2 Charges
9.2.12.2.3 | Licences in connection with crossovers, parking permits, parking bay suspensions and the like. |  | 0 | A9.2.12.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.12 Fees and charges | 9.2.12.2 Charges
9.2.13 | Site services |  | 0 | A9.2.13 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services
9.2.13.1 | Temporary works |  | 0 | A9.2.13.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services | 9.2.13.1 Temporary works
9.2.13.1.1 | Temporary works which are not specific to an element. |  | 0 | A9.2.13.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services | 9.2.13.1 Temporary works
9.2.13.2 | Multi-service gang |  | 0 | A9.2.13.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services | 9.2.13.2 Multi-service gang
9.2.13.2.1 | Ganger. |  | 0 | A9.2.13.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services | 9.2.13.2 Multi-service gang
9.2.13.2.2 | Labour. |  | 0 | A9.2.13.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services | 9.2.13.2 Multi-service gang
9.2.13.2.3 | Fork lift driver. |  | 0 | A9.2.13.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services | 9.2.13.2 Multi-service gang
9.2.13.2.4 | Service gang plant and transport. |  | 0 | A9.2.13.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.13 Site services | 9.2.13.2 Multi-service gang
9.2.14 | Insurance, bonds, guarantees and warranties |  | 0 | A9.2.14 | 2 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties
9.2.14.1 | Works insurances |  | 0 | A9.2.14.1 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.1.1 | Contractors 'all risks' (CAR) insurance. |  | 0 | A9.2.14.1.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.1.2 | Contractor's plant and equipment insurance. |  | 0 | A9.2.14.1.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.1.3 | Temporary buildings insurance. |  | 0 | A9.2.14.1.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.1.4 | Terrorism insurance. |  | 0 | A9.2.14.1.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.1.5 | Other insurances in connection with the works. |  | 0 | A9.2.14.1.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.1.6 | Insurance premium tax (IPT). |  | 0 | A9.2.14.1.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.1.7 | Allowance for recovery of all or part of insurance premium excess. |  | 0 | A9.2.14.1.7 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.1 Works insurances
9.2.14.2 | Public liability insurances |  | 0 | A9.2.14.2 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.2 Public liability insurances
9.2.14.2.1 | Non-negligence insurance. |  | 0 | A9.2.14.2.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.2 Public liability insurances
9.2.14.2.2 | Professional indemnity insurance. |  | 0 | A9.2.14.2.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.2 Public liability insurances
9.2.14.2.3 | Insurance premium tax (IPT). |  | 0 | A9.2.14.2.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.2 Public liability insurances
9.2.14.2.4 | Allowance for recovery of all or part of insurance premium excess. |  | 0 | A9.2.14.2.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.2 Public liability insurances
9.2.14.3 | Employer's (main contractor's) liability insurances |  | 0 | A9.2.14.3 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.3 Employer's (main contractor's) liability insurances
9.2.14.3.1 | Management and staff, including administrative staff. |  | 0 | A9.2.14.3.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.3 Employer's (main contractor's) liability insurances
9.2.14.3.2 | Works operatives. |  | 0 | A9.2.14.3.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.3 Employer's (main contractor's) liability insurances
9.2.14.3.3 | Insurance premium tax (IPT). |  | 0 | A9.2.14.3.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.3 Employer's (main contractor's) liability insurances
9.2.14.3.4 | Allowance for recovery of all or part of insurance premium excess. |  | 0 | A9.2.14.3.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.3 Employer's (main contractor's) liability insurances
9.2.14.4 | Other insurances |  | 0 | A9.2.14.4 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.4 Other insurances
9.2.14.4.1 | Employer's loss of liquidated damages. |  | 0 | A9.2.14.4.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.4 Other insurances
9.2.14.4.2 | Latent defects cover. |  | 0 | A9.2.14.4.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.4 Other insurances
9.2.14.4.3 | Motor vehicles. |  | 0 | A9.2.14.4.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.4 Other insurances
9.2.14.4.4 | Other insurances. |  | 0 | A9.2.14.4.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.4 Other insurances
9.2.14.4.5 | Insurance premium tax (IPT). |  | 0 | A9.2.14.4.5 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.4 Other insurances
9.2.14.4.6 | Allowance for recovery of all or part of insurance premium excess. |  | 0 | A9.2.14.4.6 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.4 Other insurances
9.2.14.5 | Bonds |  | 0 | A9.2.14.5 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.5 Bonds
9.2.14.5.1 | Tender bonds (if applicable). |  | 0 | A9.2.14.5.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.5 Bonds
9.2.14.5.2 | Performance bonds. |  | 0 | A9.2.14.5.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.5 Bonds
9.2.14.6 | Guarantees |  | 0 | A9.2.14.6 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.6 Guarantees
9.2.14.6.1 | Parent company guarantees. |  | 0 | A9.2.14.6.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.6 Guarantees
9.2.14.6.2 | Product guarantees, insurance backed. |  | 0 | A9.2.14.6.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.6 Guarantees
9.2.14.7 | Warranties |  | 0 | A9.2.14.7 | 3 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.7 Warranties
9.2.14.7.1 | Collateral warranties. |  | 0 | A9.2.14.7.1 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.7 Warranties
9.2.14.7.2 | Funder's warranties. |  | 0 | A9.2.14.7.2 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.7 Warranties
9.2.14.7.3 | Purchaser's and tenant's warranties. |  | 0 | A9.2.14.7.3 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.7 Warranties
9.2.14.7.4 | Other warranties. |  | 0 | A9.2.14.7.4 | 4 | 9 MAIN CONTRACTOR'S PRELIMINARIES | 9.2 Main contractor's cost items | 9.2.14 Insurance, bonds, guarantees and warranties | 9.2.14.7 Warranties
10 | MAIN CONTRACTOR'S OVERHEADS AND PROFITS |  | 0 | A10 | 0 | 10 MAIN CONTRACTOR'S OVERHEADS AND PROFITS
10.1 | Main contractor's overheads | 67219.32 | 71744 | A10.1 | 1 | 10 MAIN CONTRACTOR'S OVERHEADS AND PROFITS | 10.1 Main contractor's overheads
10.2 | Main contractor's profit | 112032.2 | 117132 | A10.2 | 1 | 10 MAIN CONTRACTOR'S OVERHEADS AND PROFITS | 10.2 Main contractor's profit
11 | PROJECT/DESIGN TEAM FEES |  | 0 | A11 | 0 | 11 PROJECT/DESIGN TEAM FEES
11.1 | Consultants' fees |  | 0 | A11.1 | 1 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees
11.1.1 | Project team and design team consultants' fees | 362984.328 | 389896 | A11.1.1 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees
11.1.1.1 | Professional adviser. |  | 0 | A11.1.1.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.1 Professional adviser.
11.1.1.2 | Project manager. |  | 0 | A11.1.1.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.2 Project manager.
11.1.1.3 | Contract administrator. |  | 0 | A11.1.1.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.3 Contract administrator.
11.1.1.4 | Employer's agent. |  | 0 | A11.1.1.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.4 Employer's agent.
11.1.1.5 | Architect. |  | 0 | A11.1.1.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.5 Architect.
11.1.1.6 | Quantity surveyor/cost manager. |  | 0 | A11.1.1.6 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.6 Quantity surveyor/cost manager.
11.1.1.7 | Building services engineer(s). |  | 0 | A11.1.1.7 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.7 Building services engineer(s).
11.1.1.8 | Structural engineer. |  | 0 | A11.1.1.8 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.8 Structural engineer.
11.1.1.9 | CDM co-ordinator. |  | 0 | A11.1.1.9 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.9 CDM co-ordinator.
11.1.1.10 | Interior designer. |  | 0 | A11.1.1.10 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.10 Interior designer.
11.1.1.11 | Landscape architect. |  | 0 | A11.1.1.11 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.11 Landscape architect.
11.1.1.12 | Infrastructure engineer. |  | 0 | A11.1.1.12 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.12 Infrastructure engineer.
11.1.1.13 | Drainage engineer. |  | 0 | A11.1.1.13 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.13 Drainage engineer.
11.1.1.14 | Construction/logistics/sequencing advisor. |  | 0 | A11.1.1.14 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.1 Project team and design team consultants' fees | 11.1.1.14 Construction/logistics/sequencing advisor.
11.1.2 | Other consultants' fees |  | 0 | A11.1.2 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees
11.1.2.1 | Measuring surveyor (i.e. to carry out topographical survey of site; to verify ground levels/contours, physical features, existing boundaries, adjacent properties and site JHLess). |  | 0 | A11.1.2.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.1 Measuring surveyor (i.e. to carry out topographical survey of site; to verify ground levels/contours, physical features, existing boundaries, adjacent properties and site JHLess).
11.1.2.2 | Drainage and utilities surveyor (i.e. to trace and locate existing drainage and other services, both underground and above ground, on or near the site, including, water, electricity, telecommunications, data lines and oil/fuel pipelines; advising on extent of existing utilities). |  | 0 | A11.1.2.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.2 Drainage and utilities surveyor (i.e. to trace and locate existing drainage and other services, both underground and above ground, on or near the site, including, water, electricity, telecommunications, data lines and oil/fuel pipelines; advising on extent of existing utilities).
11.1.2.3 | Geotechnical engineer (e.g. trial pits, boreholes and borehole logs, geology of site, including underground workings, laboratory and soil tests, groundwater observation and pumping tests, and geophysical surveys). |  | 0 | A11.1.2.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.3 Geotechnical engineer (e.g. trial pits, boreholes and borehole logs, geology of site, including underground workings, laboratory and soil tests, groundwater observation and pumping tests, and geophysical surveys).
11.1.2.4 | Environmental consultant (e.g. environmental audits, contamination surveys for asbestos, methane, toxic waste, chemical waste and radioactive substances; and preparation and management of remediation strategy/action plan). |  | 0 | A11.1.2.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.4 Environmental consultant (e.g. environmental audits, contamination surveys for asbestos, methane, toxic waste, chemical waste and radioactive substances; and preparation and management of remediation strategy/action plan).
11.1.2.5 | Ecologist. |  | 0 | A11.1.2.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.5 Ecologist.
11.1.2.6 | Arboriculturist (i.e. to survey and provide advice on trees and the like). |  | 0 | A11.1.2.6 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.6 Arboriculturist (i.e. to survey and provide advice on trees and the like).
11.1.2.7 | Party wall surveyor (i.e. to prepare party wall notices and awards/agreements). |  | 0 | A11.1.2.7 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.7 Party wall surveyor (i.e. to prepare party wall notices and awards/agreements).
11.1.2.8 | Rights of light surveyor (e.g. rights of light agreements). |  | 0 | A11.1.2.8 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.8 Rights of light surveyor (e.g. rights of light agreements).
11.1.2.9 | Asbestos consultant. |  | 0 | A11.1.2.9 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.9 Asbestos consultant.
11.1.2.10 | Acoustics consultant. |  | 0 | A11.1.2.10 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.10 Acoustics consultant.
11.1.2.11 | Facade consultant. |  | 0 | A11.1.2.11 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.11 Facade consultant.
11.1.2.12 | Facade JHLess consultant. |  | 0 | A11.1.2.12 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.12 Facade JHLess consultant.
11.1.2.13 | Lift consultant. |  | 0 | A11.1.2.13 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.13 Lift consultant.
11.1.2.14 | Fire consultant. |  | 0 | A11.1.2.14 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.14 Fire consultant.
11.1.2.15 | Building control consultant. |  | 0 | A11.1.2.15 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.15 Building control consultant.
11.1.2.16 | Traffic consultant (e.g. to examine traffic records, take traffic count, advise on traffic patterns, carry out computer simulation of existing traffic flows, delay analysis and advise on noise levels). |  | 0 | A11.1.2.16 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.16 Traffic consultant (e.g. to examine traffic records, take traffic count, advise on traffic patterns, carry out computer simulation of existing traffic flows, delay analysis and advise on noise levels).
11.1.2.17 | Invasive weeds specialist (e.g. to survey the site for Japanese Knotweed). |  | 0 | A11.1.2.17 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.17 Invasive weeds specialist (e.g. to survey the site for Japanese Knotweed).
11.1.2.18 | Sustainability consultant (to advise on renewable technologies and sustainability issues). |  | 0 | A11.1.2.18 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.18 Sustainability consultant (to advise on renewable technologies and sustainability issues).
11.1.2.19 | Archaeologist (e.g. to examine existing records and archaeological remains - desktop study). |  | 0 | A11.1.2.19 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.19 Archaeologist (e.g. to examine existing records and archaeological remains - desktop study).
11.1.2.20 | Environmental assessment method assessor (e.g. BREEAM or Code for Sustainable Homes). |  | 0 | A11.1.2.20 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.20 Environmental assessment method assessor (e.g. BREEAM or Code for Sustainable Homes).
11.1.2.21 | Facilities manager (e.g. to advise on operational and maintenance matters). |  | 0 | A11.1.2.21 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.21 Facilities manager (e.g. to advise on operational and maintenance matters).
11.1.2.22 | Value engineering facilitator. |  | 0 | A11.1.2.22 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.22 Value engineering facilitator.
11.1.2.23 | Risk management facilitator. |  | 0 | A11.1.2.23 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.23 Risk management facilitator.
11.1.2.24 | Building surveyor (i.e. to carry out structural/dilapidations survey of adjoining buildings; and carry out condition surveys). |  | 0 | A11.1.2.24 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.24 Building surveyor (i.e. to carry out structural/dilapidations survey of adjoining buildings; and carry out condition surveys).
11.1.2.25 | Unexploded devices consultant (e.g. to research and advise on possibility of unexploded bombs on site). |  | 0 | A11.1.2.25 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.25 Unexploded devices consultant (e.g. to research and advise on possibility of unexploded bombs on site).
11.1.2.26 | Photographer (i.e. to carry out a photographic survey of the site). |  | 0 | A11.1.2.26 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.26 Photographer (i.e. to carry out a photographic survey of the site).
11.1.2.27 | Specialist contractors/consultants (e.g. early advice on viability of ground source heating). |  | 0 | A11.1.2.27 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.27 Specialist contractors/consultants (e.g. early advice on viability of ground source heating).
11.1.2.28 | Other specialist consultants (to be stated). |  | 0 | A11.1.2.28 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.2 Other consultants' fees | 11.1.2.28 Other specialist consultants (to be stated).
11.1.3 | Site investigation fees |  | 0 | A11.1.3 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.3 Site investigation fees
11.1.3.1 | Site investigation. |  | 0 | A11.1.3.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.3 Site investigation fees | 11.1.3.1 Site investigation.
11.1.3.2 | Geotechnical investigation. |  | 0 | A11.1.3.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.3 Site investigation fees | 11.1.3.2 Geotechnical investigation.
11.1.3.3 | Trial pits. |  | 0 | A11.1.3.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.3 Site investigation fees | 11.1.3.3 Trial pits.
11.1.3.4 | Pile probing. |  | 0 | A11.1.3.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.3 Site investigation fees | 11.1.3.4 Pile probing.
11.1.3.5 | Intrusive investigations for toxic or hazardous materials (e.g. for asbestos-containing materials). |  | 0 | A11.1.3.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.3 Site investigation fees | 11.1.3.5 Intrusive investigations for toxic or hazardous materials (e.g. for asbestos-containing materials).
11.1.3.6 | Other site investigations (to be stated). |  | 0 | A11.1.3.6 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.3 Site investigation fees | 11.1.3.6 Other site investigations (to be stated).
11.1.4 | Specialist support consultants' fees |  | 0 | A11.1.4 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees
11.1.4.1 | Planning consultant (i.e. to advise on planning matters and facilitate planning process). |  | 0 | A11.1.4.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.1 Planning consultant (i.e. to advise on planning matters and facilitate planning process).
11.1.4.2 | Political consultants (i.e. to assist with planning application). |  | 0 | A11.1.4.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.2 Political consultants (i.e. to assist with planning application).
11.1.4.3 | Letting agents (e.g. advice on market needs, advice on design proposals and selling). |  | 0 | A11.1.4.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.3 Letting agents (e.g. advice on market needs, advice on design proposals and selling).
11.1.4.4 | Legal advice - property (e.g. to advise on ownership of site, restrictive covenants, easements, boundaries, party wall agreements, highway agreements, local authority agreements and air rights). |  | 0 | A11.1.4.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.4 Legal advice - property (e.g. to advise on ownership of site, restrictive covenants, easements, boundaries, party wall agreements, highway agreements, local authority agreements and air rights).
11.1.4.5 | Legal advice - construction (e.g. to advise on construction contracts, warranties, financial protection measures and the like). |  | 0 | A11.1.4.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.5 Legal advice - construction (e.g. to advise on construction contracts, warranties, financial protection measures and the like).
11.1.4.6 | Legal advice - environmental. |  | 0 | A11.1.4.6 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.6 Legal advice - environmental.
11.1.4.7 | Tax specialist - (e.g. to advise on VAT, availability of capital allowances and recovery thereof, tax relief in respect of land remediation and other specialist tax matters). |  | 0 | A11.1.4.7 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.7 Tax specialist - (e.g. to advise on VAT, availability of capital allowances and recovery thereof, tax relief in respect of land remediation and other specialist tax matters).
11.1.4.8 | Grants advice (e.g. to advise on availability of grants for construction works). |  | 0 | A11.1.4.8 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.8 Grants advice (e.g. to advise on availability of grants for construction works).
11.1.4.9 | Other specialist support consultants (to be stated). |  | 0 | A11.1.4.9 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.1 Consultants' fees | 11.1.4 Specialist support consultants' fees | 11.1.4.9 Other specialist support consultants (to be stated).
11.2 | Main contractor's pre-construction fees |  | 0 | A11.2 | 1 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees
11.2.1 | Management and staff fees |  | 0 | A11.2.1 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff fees
11.2.1 | Management and staff, such as: |  | 0 | A11.2.1 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as:
11.2.1.1 | Project director. |  | 0 | A11.2.1.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.1 Project director.
11.2.1.2 | Project manager. |  | 0 | A11.2.1.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.2 Project manager.
11.2.1.3 | Construction manager. |  | 0 | A11.2.1.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.3 Construction manager.
11.2.1.4 | Commercial manager. |  | 0 | A11.2.1.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.4 Commercial manager.
11.2.1.5 | Quantity surveyors. |  | 0 | A11.2.1.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.5 Quantity surveyors.
11.2.1.6 | Procurement manager. |  | 0 | A11.2.1.6 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.6 Procurement manager.
11.2.1.7 | Planning/programming manager and staff. |  | 0 | A11.2.1.7 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.7 Planning/programming manager and staff.
11.2.1.8 | Design manager. |  | 0 | A11.2.1.8 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.8 Design manager.
11.2.1.9 | Temporary works design engineers. |  | 0 | A11.2.1.9 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.9 Temporary works design engineers.
11.2.1.10 | Works package managers. |  | 0 | A11.2.1.10 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.10 Works package managers.
11.2.1.11 | Building services engineering managers/co-ordinators. |  | 0 | A11.2.1.11 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.11 Building services engineering managers/co-ordinators.
11.2.1.12 | Health and safety manager. |  | 0 | A11.2.1.12 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.12 Health and safety manager.
11.2.1.13 | Secretary/administrative support. |  | 0 | A11.2.1.13 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.13 Secretary/administrative support.
11.2.1.14 | Other pre-construction management and staff. |  | 0 | A11.2.1.14 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.1 Management and staff, such as: | 11.2.1.14 Other pre-construction management and staff.
11.2.2 | Specialist support services fees |  | 0 | A11.2.2 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.2 Specialist support services fees
11.2.2.1 | Legal advice (i.e. solicitors). |  | 0 | A11.2.2.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.2 Specialist support services fees | 11.2.2.1 Legal advice (i.e. solicitors).
11.2.2.2 | Specialist subcontractor advice/participation. |  | 0 | A11.2.2.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.2 Specialist support services fees | 11.2.2.2 Specialist subcontractor advice/participation.
11.2.2.3 | Geotechnical investigations, procured by main contractor as part of pre-construction services. |  | 0 | A11.2.2.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.2 Specialist support services fees | 11.2.2.3 Geotechnical investigations, procured by main contractor as part of pre-construction services.
11.2.2.4 | Site investigations, procured by main contractor as part of pre-construction services. |  | 0 | A11.2.2.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.2 Specialist support services fees | 11.2.2.4 Site investigations, procured by main contractor as part of pre-construction services.
11.2.2.5 | Other pre-construction support services. |  | 0 | A11.2.2.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.2 Specialist support services fees | 11.2.2.5 Other pre-construction support services.
11.2.3 | Temporary JHLommodation, services and facilities charges |  | 0 | A11.2.3 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges
11.2.3.1 | Offices, including rental of temporary office space. |  | 0 | A11.2.3.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.1 Offices, including rental of temporary office space.
11.2.3.2 | Service provider's charges for water, electricity and gas. |  | 0 | A11.2.3.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.2 Service provider's charges for water, electricity and gas.
11.2.3.3 | Rates. |  | 0 | A11.2.3.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.3 Rates.
11.2.3.4 | Furniture and equipment, including workstations. |  | 0 | A11.2.3.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.4 Furniture and equipment, including workstations.
11.2.3.5 | Office equipment, including photocopiers. |  | 0 | A11.2.3.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.5 Office equipment, including photocopiers.
11.2.3.6 | Telecommunications, including internet and intranet JHLess. |  | 0 | A11.2.3.6 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.6 Telecommunications, including internet and intranet JHLess.
11.2.3.7 | IT systems, including hardware, printers, plotters and the like. |  | 0 | A11.2.3.7 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.7 IT systems, including hardware, printers, plotters and the like.
11.2.3.8 | Office consumables. |  | 0 | A11.2.3.8 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.8 Office consumables.
11.2.3.9 | Cleaning. |  | 0 | A11.2.3.9 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.9 Cleaning.
11.2.3.10 | Other costs associated with the provision of pre-construction JHLommodation, services and facilities. |  | 0 | A11.2.3.10 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.10 Other costs associated with the provision of pre-construction JHLommodation, services and facilities.
11.2.3.11 | Reinstating JHLommodation to original condition on completion of pre-construction services. |  | 0 | A11.2.3.11 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.3 Temporary JHLommodation, services and facilities charges | 11.2.3.11 Reinstating JHLommodation to original condition on completion of pre-construction services.
11.2.4 | Main contractor's overheads and profit |  | 0 | A11.2.4 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.4 Main contractor's overheads and profit
11.2.4.1 | Main contractor's overheads and profit associated with pre-construction services. |  | 0 | A11.2.4.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.2 Main contractor's pre-construction fees | 11.2.4 Main contractor's overheads and profit | 11.2.4.1 Main contractor's overheads and profit associated with pre-construction services.
11.3 | Main contractor's design fees |  | 0 | A11.3 | 1 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees
11.3.1 | Main contractor's design consultants' fees |  | 0 | A11.3.1 | 2 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees
11.3.1.1 | Architect. |  | 0 | A11.3.1.1 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.1 Architect.
11.3.1.2 | Building services engineer(s). |  | 0 | A11.3.1.2 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.2 Building services engineer(s).
11.3.1.3 | Structural engineer. |  | 0 | A11.3.1.3 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.3 Structural engineer.
11.3.1.4 | Interior designer. |  | 0 | A11.3.1.4 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.4 Interior designer.
11.3.1.5 | Landscape architect. |  | 0 | A11.3.1.5 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.5 Landscape architect.
11.3.1.6 | Infrastructure engineer. |  | 0 | A11.3.1.6 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.6 Infrastructure engineer.
11.3.1.7 | Drainage engineer. |  | 0 | A11.3.1.7 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.7 Drainage engineer.
11.3.1.8 | Site investigation services (by specialist subcontractor or consultant). |  | 0 | A11.3.1.8 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.8 Site investigation services (by specialist subcontractor or consultant).
11.3.1.9 | Other design consultants or specialist services. |  | 0 | A11.3.1.9 | 3 | 11 PROJECT/DESIGN TEAM FEES | 11.3 Main contractor's design fees | 11.3.1 Main contractor's design consultants' fees | 11.3.1.9 Other design consultants or specialist services.
12 | OTHER DEVELOPMENT/PROJECT COSTS |  | 0 | A12 | 0 | 12 OTHER DEVELOPMENT/PROJECT COSTS
12.1.1 | Land acquisition costs |  | 0 | A12.1.1 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.1 Land acquisition costs
12.1.1.1 | Costs in connection with land acquisition. |  | 0 | A12.1.1.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.1 Land acquisition costs | 12.1.1.1 Costs in connection with land acquisition.
12.1.2 | Employer finance costs |  | 0 | A12.1.2 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.2 Employer finance costs
12.1.2.1 | Costs in connection with funding of building project. |  | 0 | A12.1.2.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.2 Employer finance costs | 12.1.2.1 Costs in connection with funding of building project.
12.1.3 | Fees | 120994.776 | 120009 | A12.1.3 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees
12.1.3.1 | Planning fees. |  | 0 | A12.1.3.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.1 Planning fees.
12.1.3.2 | Building control fees, where not paid by the main contractor. |  | 0 | A12.1.3.2 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.2 Building control fees, where not paid by the main contractor.
12.1.3.3 | Oversailing fees, where not paid by the main contractor. |  | 0 | A12.1.3.3 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.3 Oversailing fees, where not paid by the main contractor.
12.1.3.4 | Fees in connection with party wall awards. |  | 0 | A12.1.3.4 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.4 Fees in connection with party wall awards.
12.1.3.5 | Fees in connection with rights of light agreements. |  | 0 | A12.1.3.5 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.5 Fees in connection with rights of light agreements.
12.1.3.6 | Building scheme registration fees (e.g. NHBC Buildmark) or similar fees, where not paid by the main contractor. |  | 0 | A12.1.3.6 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.6 Building scheme registration fees (e.g. NHBC Buildmark) or similar fees, where not paid by the main contractor.
12.1.3.7 | Fees in connection with other agreements between the employer and neighbours to facilitate the building project. |  | 0 | A12.1.3.7 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.7 Fees in connection with other agreements between the employer and neighbours to facilitate the building project.
12.1.3.8 | Other fees in connection with licences, permits and agreements, where not paid by the main contractor. |  | 0 | A12.1.3.8 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.3 Fees | 12.1.3.8 Other fees in connection with licences, permits and agreements, where not paid by the main contractor.
12.1.4 | Charges |  | 0 | A12.1.4 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.4 Charges
12.1.4.1 | Adoption charges in connection with highways. |  | 0 | A12.1.4.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.4 Charges | 12.1.4.1 Adoption charges in connection with highways.
12.1.4.2 | Maintenance costs in connection with highways. |  | 0 | A12.1.4.2 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.4 Charges | 12.1.4.2 Maintenance costs in connection with highways.
12.1.4.3 | Adoption charges in connection with services (e.g. sewers, water, electricity and gas). |  | 0 | A12.1.4.3 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.4 Charges | 12.1.4.3 Adoption charges in connection with services (e.g. sewers, water, electricity and gas).
12.1.4.4 | Maintenance costs in connection with services. |  | 0 | A12.1.4.4 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.4 Charges | 12.1.4.4 Maintenance costs in connection with services.
12.1.5 | Planning contributions |  | 0 | A12.1.5 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.5 Planning contributions
12.1.5.1 | Direct financial contributions in connection with planning consent (e.g. Section 106 and Section 278 contributions in the UK). |  | 0 | A12.1.5.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.5 Planning contributions | 12.1.5.1 Direct financial contributions in connection with planning consent (e.g. Section 106 and Section 278 contributions in the UK).
12.1.5.2 | Environmental improvement works. |  | 0 | A12.1.5.2 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.5 Planning contributions | 12.1.5.2 Environmental improvement works.
12.1.6 | Insurances |  | 0 | A12.1.6 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.6 Insurances
12.1.6.1 | Insurance for the works - existing buildings. |  | 0 | A12.1.6.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.6 Insurances | 12.1.6.1 Insurance for the works - existing buildings.
12.1.6.2 | Insurance for the works - new buildings, where insurance taken out by the employer. |  | 0 | A12.1.6.2 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.6 Insurances | 12.1.6.2 Insurance for the works - new buildings, where insurance taken out by the employer.
12.1.6.3 | Other insurances in connection with the works. |  | 0 | A12.1.6.3 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.6 Insurances | 12.1.6.3 Other insurances in connection with the works.
12.1.6.4 | Insurance premium tax (IPT). |  | 0 | A12.1.6.4 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.6 Insurances | 12.1.6.4 Insurance premium tax (IPT).
12.1.7 | Archaeological fieldwork |  | 0 | A12.1.7 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.7 Archaeological fieldwork
12.1.7.1 | Fees and charges in connection with fieldwork carried out by an archaeologist. |  | 0 | A12.1.7.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.7 Archaeological fieldwork | 12.1.7.1 Fees and charges in connection with fieldwork carried out by an archaeologist.
12.1.8 | Other specialist fieldwork |  | 0 | A12.1.8 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.8 Other specialist fieldwork
12.1.8.1 | Fees and charges in connection with fieldwork carried out by a specialist. |  | 0 | A12.1.8.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.8 Other specialist fieldwork | 12.1.8.1 Fees and charges in connection with fieldwork carried out by a specialist.
12.1.9 | Decanting and relocation costs |  | 0 | A12.1.9 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.9 Decanting and relocation costs
12.1.9.1 | Temporary relocation costs. |  | 0 | A12.1.9.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.9 Decanting and relocation costs | 12.1.9.1 Temporary relocation costs.
12.1.9.2 | Fit-out of temporary JHLommodation. |  | 0 | A12.1.9.2 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.9 Decanting and relocation costs | 12.1.9.2 Fit-out of temporary JHLommodation.
12.1.9.3 | Rents and other running costs. |  | 0 | A12.1.9.3 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.9 Decanting and relocation costs | 12.1.9.3 Rents and other running costs.
12.1.10 | Fittings, furnishings and equipment |  | 0 | A12.1.10 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.10 Fittings, furnishings and equipment
12.1.10.1 | Fittings, furnishings and equipment which do not form part of a building contract. |  | 0 | A12.1.10.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.10 Fittings, furnishings and equipment | 12.1.10.1 Fittings, furnishings and equipment which do not form part of a building contract.
12.1.11 | Tenant's costs/contributions |  | 0 | A12.1.11 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.11 Tenant's costs/contributions
12.1.11.1 | Tenant's costs. |  | 0 | A12.1.11.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.11 Tenant's costs/contributions | 12.1.11.1 Tenant's costs.
12.1.11.2 | Tenant's contributions. |  | 0 | A12.1.11.2 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.11 Tenant's costs/contributions | 12.1.11.2 Tenant's contributions.
12.1.12 | Marketing costs |  | 0 | A12.1.12 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.12 Marketing costs
12.1.12.1 | Launch event. |  | 0 | A12.1.12.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.12 Marketing costs | 12.1.12.1 Launch event.
12.1.12.2 | Site based advertising (e.g. sales hoardings). |  | 0 | A12.1.12.2 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.12 Marketing costs | 12.1.12.2 Site based advertising (e.g. sales hoardings).
12.1.12.3 | Show unit/marketing suites (i.e. separate or within building to be built). |  | 0 | A12.1.12.3 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.12 Marketing costs | 12.1.12.3 Show unit/marketing suites (i.e. separate or within building to be built).
12.1.12.4 | Operating costs associated with show unit/marketing suites. |  | 0 | A12.1.12.4 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.12 Marketing costs | 12.1.12.4 Operating costs associated with show unit/marketing suites.
12.1.12.5 | Marketing literature. |  | 0 | A12.1.12.5 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.12 Marketing costs | 12.1.12.5 Marketing literature.
12.1.13 | Other employer costs |  | 0 | A12.1.13 | 2 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.13 Other employer costs
12.1.13.1 | Other employer costs in connection with the building project (to be stated). |  | 0 | A12.1.13.1 | 3 | 12 OTHER DEVELOPMENT/PROJECT COSTS |  | 12.1.13 Other employer costs | 12.1.13.1 Other employer costs in connection with the building project (to be stated).
13 | RISKS |  | 0 | A13 | 0 | 13 RISKS
13.1 | Design development risks | 181492.164 | 191568 | A13.1 | 1 | 13 RISKS | 13.1 Design development risks
13.1.1 | Inadequate or unclear project brief. |  | 0 | A13.1.1 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.1 Inadequate or unclear project brief.
13.1.2 | Unclear design team responsibilities. |  | 0 | A13.1.2 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.2 Unclear design team responsibilities.
13.1.3 | Unrealistic design programme. |  | 0 | A13.1.3 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.3 Unrealistic design programme.
13.1.4 | Ineffective quality control procedures. |  | 0 | A13.1.4 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.4 Ineffective quality control procedures.
13.1.5 | Inadequate site investigation. |  | 0 | A13.1.5 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.5 Inadequate site investigation.
13.1.6 | Planning constraints/requirements. |  | 0 | A13.1.6 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.6 Planning constraints/requirements.
13.1.7 | Soundness of design data. |  | 0 | A13.1.7 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.7 Soundness of design data.
13.1.8 | Appropriateness of design (constructionability). |  | 0 | A13.1.8 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.8 Appropriateness of design (constructionability).
13.1.9 | Degree of novelty (i.e. design novelty). |  | 0 | A13.1.9 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.9 Degree of novelty (i.e. design novelty).
13.1.10 | Ineffective design co-ordination. |  | 0 | A13.1.10 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.10 Ineffective design co-ordination.
13.1.11 | Reliability of area schedules. |  | 0 | A13.1.11 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.11 Reliability of area schedules.
13.1.12 | Reliability of estimating data: changes in labour, materials, equipment and plant costs; and inflation (i.e. differential inflation due to market factors and/or timing). |  | 0 | A13.1.12 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.12 Reliability of estimating data: changes in labour, materials, equipment and plant costs; and inflation (i.e. differential inflation due to market factors and/or timing).
13.1.13 | Use of provisional sums (i.e. do not give price certainty). |  | 0 | A13.1.13 | 2 | 13 RISKS | 13.1 Design development risks | 13.1.13 Use of provisional sums (i.e. do not give price certainty).
13.2 | Construction risks | 60497.388 | 56795 | A13.2 | 1 | 13 RISKS | 13.2 Construction risks
13.2.1 | Inadequate site investigation. |  | 0 | A13.2.1 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.1 Inadequate site investigation.
13.2.2 | Archaeological remains. |  | 0 | A13.2.2 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.2 Archaeological remains.
13.2.3 | Underground obstructions. |  | 0 | A13.2.3 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.3 Underground obstructions.
13.2.4 | Contaminated ground. |  | 0 | A13.2.4 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.4 Contaminated ground.
13.2.5 | Adjacent structures (i.e. requiring special precautions). |  | 0 | A13.2.5 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.5 Adjacent structures (i.e. requiring special precautions).
13.2.6 | Geotechnical problems (e.g. mining and subsidence). |  | 0 | A13.2.6 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.6 Geotechnical problems (e.g. mining and subsidence).
13.2.7 | Ground water. |  | 0 | A13.2.7 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.7 Ground water.
13.2.8 | Asbestos and other hazardous materials. |  | 0 | A13.2.8 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.8 Asbestos and other hazardous materials.
13.2.9 | Invasive plant growth. |  | 0 | A13.2.9 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.9 Invasive plant growth.
13.2.10 | Tree preservation orders. |  | 0 | A13.2.10 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.10 Tree preservation orders.
13.2.11 | Ecological issues (e.g. presence of endangered species). |  | 0 | A13.2.11 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.11 Ecological issues (e.g. presence of endangered species).
13.2.12 | Environmental impact. |  | 0 | A13.2.12 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.12 Environmental impact.
13.2.13 | Physical JHLess to site (i.e. restrictions and limitations). |  | 0 | A13.2.13 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.13 Physical JHLess to site (i.e. restrictions and limitations).
13.2.14 | Existing occupancies/users. |  | 0 | A13.2.14 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.14 Existing occupancies/users.
13.2.15 | Restricted working hours/routines. |  | 0 | A13.2.15 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.15 Restricted working hours/routines.
13.2.16 | Maintaining JHLess. |  | 0 | A13.2.16 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.16 Maintaining JHLess.
13.2.17 | Maintaining existing services. |  | 0 | A13.2.17 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.17 Maintaining existing services.
13.2.18 | Additional infrastructure. |  | 0 | A13.2.18 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.18 Additional infrastructure.
13.2.19 | Existing services (i.e. availability, capacity, condition and location). |  | 0 | A13.2.19 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.19 Existing services (i.e. availability, capacity, condition and location).
13.2.20 | Location of existing services. |  | 0 | A13.2.20 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.20 Location of existing services.
13.2.21 | Relocation of existing services. |  | 0 | A13.2.21 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.21 Relocation of existing services.
13.2.22 | Statutory undertakers (i.e. performance). |  | 0 | A13.2.22 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.22 Statutory undertakers (i.e. performance).
13.2.23 | Uncertainty over the source and availability of materials. |  | 0 | A13.2.23 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.23 Uncertainty over the source and availability of materials.
13.2.24 | Appropriateness of specifications. |  | 0 | A13.2.24 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.24 Appropriateness of specifications.
13.2.25 | Incomplete design. |  | 0 | A13.2.25 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.25 Incomplete design.
13.2.26 | Weather and seasonal implications. |  | 0 | A13.2.26 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.26 Weather and seasonal implications.
13.2.27 | Industrial relations. |  | 0 | A13.2.27 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.27 Industrial relations.
13.2.28 | Remote site. |  | 0 | A13.2.28 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.28 Remote site.
13.2.29 | Competence of contractor and subcontractors. |  | 0 | A13.2.29 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.29 Competence of contractor and subcontractors.
13.2.30 | Health and safety. |  | 0 | A13.2.30 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.30 Health and safety.
13.2.31 | Ineffective quality management procedures. |  | 0 | A13.2.31 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.31 Ineffective quality management procedures.
13.2.32 | Phasing requirements (e.g. occupation and decanting). |  | 0 | A13.2.32 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.32 Phasing requirements (e.g. occupation and decanting).
13.2.33 | Ineffective handover procedures. |  | 0 | A13.2.33 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.33 Ineffective handover procedures.
13.2.34 | Disputes and claims. |  | 0 | A13.2.34 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.34 Disputes and claims.
13.2.35 | Effect of changes/variations on construction programme. |  | 0 | A13.2.35 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.35 Effect of changes/variations on construction programme.
13.2.36 | Cumulative effect of numerous changes/variations on construction programme. |  | 0 | A13.2.36 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.36 Cumulative effect of numerous changes/variations on construction programme.
13.2.37 | Defects. |  | 0 | A13.2.37 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.37 Defects.
13.2.38 | JHLidents/injury. |  | 0 | A13.2.38 | 2 | 13 RISKS | 13.2 Construction risks | 13.2.38 JHLidents/injury.
13.3 | Employer change risks | 120994.776 | 118589 | A13.3 | 1 | 13 RISKS | 13.3 Employer change risks
13.3.1 | Specific changes in requirements (i.e. in scope of works or project brief during design, pre-construction and construction stages). |  | 0 | A13.3.1 | 2 | 13 RISKS | 13.3 Employer change risks | 13.3.1 Specific changes in requirements (i.e. in scope of works or project brief during design, pre-construction and construction stages).
13.3.2 | Changes in quality (i.e. specification of materials and workmanship). |  | 0 | A13.3.2 | 2 | 13 RISKS | 13.3 Employer change risks | 13.3.2 Changes in quality (i.e. specification of materials and workmanship).
13.3.3 | Changes in time. |  | 0 | A13.3.3 | 2 | 13 RISKS | 13.3 Employer change risks | 13.3.3 Changes in time.
13.3.4 | Employer driven changes/variations introduced during the construction stage. |  | 0 | A13.3.4 | 2 | 13 RISKS | 13.3 Employer change risks | 13.3.4 Employer driven changes/variations introduced during the construction stage.
13.3.5 | Effect on construction duration (i.e. impact on date for completion). |  | 0 | A13.3.5 | 2 | 13 RISKS | 13.3 Employer change risks | 13.3.5 Effect on construction duration (i.e. impact on date for completion).
13.3.6 | Cumulative effect of numerous changes. |  | 0 | A13.3.6 | 2 | 13 RISKS | 13.3 Employer change risks | 13.3.6 Cumulative effect of numerous changes.
13.4 | Employer other risks | 120994.776 | 121173 | A13.4 | 1 | 13 RISKS | 13.4 Employer other risks
13.4.1 | Project brief: |  | 0 | A13.4.1 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.1 Project brief:
13.4.1 | - End user requirements. |  | 0 | A13.4.1 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.1 - End user requirements.
13.4.1 | - Inadequate or unclear project brief. |  | 0 | A13.4.1 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.1 - Inadequate or unclear project brief.
13.4.1 | - Employer's specific requirements (e.g. functional standards, site or establishment rules and regulations, and standing orders). |  | 0 | A13.4.1 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.1 - Employer's specific requirements (e.g. functional standards, site or establishment rules and regulations, and standing orders).
13.4.2 | Timescales: |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 Timescales:
13.4.2 | - Unrealistic design and construction programmes. |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Unrealistic design and construction programmes.
13.4.2 | - Unrealistic tender period(s). |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Unrealistic tender period(s).
13.4.2 | - Insufficient time allowed for tender evaluation. |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Insufficient time allowed for tender evaluation.
13.4.2 | - Contractual claims. |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Contractual claims.
13.4.2 | - Effects of phased completion requirements (e.g. sectional completion). |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Effects of phased completion requirements (e.g. sectional completion).
13.4.2 | - JHLeleration of construction works. |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - JHLeleration of construction works.
13.4.2 | - Effects of early handover requirements (e.g. requesting partial possession). |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Effects of early handover requirements (e.g. requesting partial possession).
13.4.2 | - Postponement of pre-construction services or construction works. |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Postponement of pre-construction services or construction works.
13.4.2 | - Timescales for decision making. |  | 0 | A13.4.2 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.2 - Timescales for decision making.
13.4.3 | Financial: |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 Financial:
13.4.3 | - Availability of funds. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Availability of funds.
13.4.3 | - Unavailability of grants/grant refusal. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Unavailability of grants/grant refusal.
13.4.3 | - Cash flow effects on timing. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Cash flow effects on timing.
13.4.3 | - Existing liabilities (i.e. liquidated damages or premiums on other contracts due to late provision of JHLommodation). |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Existing liabilities (i.e. liquidated damages or premiums on other contracts due to late provision of JHLommodation).
13.4.3 | - Changing inflation. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Changing inflation.
13.4.3 | - Changing interest rates. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Changing interest rates.
13.4.3 | - Changing exchange rates. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Changing exchange rates.
13.4.3 | - Changes in taxation (e.g. VAT). |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Changes in taxation (e.g. VAT).
13.4.3 | - Unsuitable contract strategy. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Unsuitable contract strategy.
13.4.3 | - Incomplete design before construction commences. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Incomplete design before construction commences.
13.4.3 | - Unconventional contract strategy. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Unconventional contract strategy.
13.4.3 | - Unconventional tender action. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Unconventional tender action.
13.4.3 | - Amendments to standard contract conditions and/or supplementary contract conditions. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Amendments to standard contract conditions and/or supplementary contract conditions.
13.4.3 | - JHLeptance of use of provisional sums (i.e. do not give price certainty). |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - JHLeptance of use of provisional sums (i.e. do not give price certainty).
13.4.3 | - Liquidation/insolvency of main contractor. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Liquidation/insolvency of main contractor.
13.4.3 | - Liquidation/insolvency of consultant. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Liquidation/insolvency of consultant.
13.4.3 | - Delay in payment. |  | 0 | A13.4.3 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.3 - Delay in payment.
13.4.4 | Management: |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 Management:
13.4.4 | - Unclear project organisation and management. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Unclear project organisation and management.
13.4.4 | - Competence of project/design team. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Competence of project/design team.
13.4.4 | - Unclear definition of project/team responsibilities. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Unclear definition of project/team responsibilities.
13.4.4 | - Inadequate or no risk management strategy. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Inadequate or no risk management strategy.
13.4.4 | - Ineffective or no cost control procedures. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Ineffective or no cost control procedures.
13.4.4 | - Inadequate or no design review procedures. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Inadequate or no design review procedures.
13.4.4 | - Ineffective or no procedures for procurement. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Ineffective or no procedures for procurement.
13.4.4 | - Ineffective or no time control procedures. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Ineffective or no time control procedures.
13.4.4 | - Ineffective change control procedures (for both pre-construction and construction stages of building project). |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Ineffective change control procedures (for both pre-construction and construction stages of building project).
13.4.4 | - Ineffective reporting systems. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Ineffective reporting systems.
13.4.4 | - Phasing of decanting and occupation. |  | 0 | A13.4.4 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.4 - Phasing of decanting and occupation.
13.4.5 | Third party: |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 Third party:
13.4.5 | - Requirements relating to planning (e.g. public enquiries, listed building consent and conservation area consent). |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Requirements relating to planning (e.g. public enquiries, listed building consent and conservation area consent).
13.4.5 | - Opposition by local councillor(s). |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Opposition by local councillor(s).
13.4.5 | - Planning refusal. |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Planning refusal.
13.4.5 | - Legal agreements. |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Legal agreements.
13.4.5 | - Works arising out of party wall agreements. |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Works arising out of party wall agreements.
13.4.5 | - Requirements relating to existing rights of way, rights of light, way leaves and noise abatement. |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Requirements relating to existing rights of way, rights of light, way leaves and noise abatement.
13.4.5 | - Requirements relating to listed buildings and/or conservation areas. |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Requirements relating to listed buildings and/or conservation areas.
13.4.5 | - Requirements relating to sites of scientific interest (SSI). |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Requirements relating to sites of scientific interest (SSI).
13.4.5 | - Requirements relating to environmental impact assessments. |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Requirements relating to environmental impact assessments.
13.4.5 | - Requirements relating to social matters (e.g. pressure groups and local protests). |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Requirements relating to social matters (e.g. pressure groups and local protests).
13.4.5 | - Public enquiries. |  | 0 | A13.4.5 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.5 - Public enquiries.
13.4.6 | Other: |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 Other:
13.4.6 | - Insistence on use of local work people. |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 - Insistence on use of local work people.
13.4.6 | - Availability of labour, materials and plant. |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 - Availability of labour, materials and plant.
13.4.6 | - Statutory requirements. |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 - Statutory requirements.
13.4.6 | - Market conditions. |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 - Market conditions.
13.4.6 | - Political change. |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 - Political change.
13.4.6 | - Legislation. |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 - Legislation.
13.4.6 | - Force majeure. |  | 0 | A13.4.6 | 2 | 13 RISKS | 13.4 Employer other risks | 13.4.6 - Force majeure.
14 | INFLATION |  | 0 | A14 | 0 | 14 INFLATION
14.1 | Tender inflation |  | 0 | A14.1 | 1 | 14 INFLATION | 14.1 Tender inflation
14.1.1 | Inflationary price increases during the period from the estimate base date to the date of tender return. | 96795.8208 | 91884 | A14.1.1 | 2 | 14 INFLATION | 14.1 Tender inflation | 14.1.1 Inflationary price increases during the period from the estimate base date to the date of tender return.
14.2 | Construction inflation |  | 0 | A14.2 | 1 | 14 INFLATION | 14.2 Construction inflation
14.2.1 | Inflationary price increases during the period from the date of tender return to the mid-point of the construction period. | 48397.9104 | 51698 | A14.2.1 | 2 | 14 INFLATION | 14.2 Construction inflation | 14.2.1 Inflationary price increases during the period from the date of tender return to the mid-point of the construction period.